

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Activity** | **Start Date** | **End Date** | **Action Party** | **Status** |
| Carry out Investigation of Technology that can be deployed in underwater inspection and identify opportunity. | Jan. 2018 | Jan. 2018 | Tamunoemi Efebeli | Closed |
| Engage Contractor and conduct presentation to team on performance of identified equipment | Feb. 2018 | Feb. 2018 | Tamunoemi Efebeli | Closed |
| Provide Feedback to Management for Support | March 2018 | March 2018 | Tamunoemi Efebeli | Closed |
| Identify current opportunities in SPDC for implementation. | April 2018 | April 2018 | Tamunoemi Efebeli | Closed |
| Purchase and receive UVAS-Sting Ray DVR Equipment | 15 May 2018 | 15 Aug. 2018 | Tamunoemi Efebeli Chinenye Orajaka | Closed |
| Develop Safe Operating Procedure for UVAS equipment including JHA and sign off | 1st July 2018 | 30 April 2019 | Chioke  Kelechukwu | Closed |
| Implement execution for degraded Sheet Pile walls in Bonny Oil and Gas (BOGT) Jetty | 10 May 2019 | 31 May 2019 | Vitalis Mbachu/ Edson Akpotha | Closed |
| Review Results, performance, provide feedback and bank savings. | 3 June 2019 | 30 June 2019 | Forster  Ezenwelu | Closed |