## 31.10.2024 SPDC Opex Report
Workstream Lead: Full Name | Workstream Sponsor: Full Name | Owner: Full Name | Initiative Name | Idn | Yearly Planned value Currency | Yearly Planned value | Yearly Forecast value Currency | Yearly Forecast value | Yearly Actual value Currency | Yearly Actual value | Planned Date | Data filter 1: Asset Name | zPlanned Date(Number)[DO NOT USE] | Overall status | Actual L-Gate | Plan Relevance | L1 Completion Date (Planned) | L2 Completion Date (Planned) | L3 Completion Date (Planned) | L4 Completion Date (Planned) | L5 Completion Date (Planned) | Workstream Name | Formula Data filter 2 | Hashtag # | Created Date | Benefit Type | Date Downloaded
Lasbery Ogofia | CJ Akwaeze | Ikemefuna Okereke | #19248-Lease out of additional office space in Abuja | I-0039769 | USD | 59906.64 | USD | 59906.64 | USD | 33522.04 | 31/12/2024 | Real Estate | 61 | On track | L3 | OP22 Above the Plan not in LE; OP23 Above the Plan not in LE |  | 15/03/2020 | 31/05/2024 | 31/12/2024 | 31/03/2025 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Non Structural / One-off saving | #infrastructure | 2020-02-08 | Other Income | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluwakemi Patrick-Oko | 2024-Cost savings from avoided demurrage on Line Pipe Shipment - PO 4510498667 | I-4814588 | USD | 150000 |  |  |  |  | 30/11/2024 | West Asset | 30 | On track | L2 | OP23 In Plan | 17/10/2024 | 31/10/2024 | 30/11/2024 | 20/12/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving |  | 2024-03-10 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluwakemi Patrick-Oko | 2024-Cost savings from Supply Chain Visibility (SCV) tool | I-3003157 | USD | 150000 | USD | 150000 | USD | 100000 | 30/11/2024 | CP | 30 | On track | L3 | OP23 In Plan | 2024-08-01 | 30/09/2024 | 30/10/2024 | 30/11/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving |  | 16/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluwakemi Patrick-Oko | 2024-PCard Markup line separation and Material procurement cost savings_SPDC | I-3003122 | USD | 564197.4 | USD | 564197.4 | USD | 527937.74 | 30/11/2024 | CP | 30 | On track | L3 | OP23 In Plan | 2024-08-01 | 30/09/2024 | 31/10/2024 | 30/11/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #materials | 15/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Felicia Enechi | 2024-Sale of SPDC Surplus Items | I-3676040 | USD | 100000 | USD | 100000 |  |  | 31/10/2024 | CP | 0 | On track | L3 | OP23 Above the Plan not in LE | 30/04/2024 | 30/06/2024 | 31/08/2024 | 31/10/2024 | 31/01/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #materials | 22/03/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Felicia Enechi | 2024-Sale of SPDC Surplus Items | I-3676058 | [6 empty] | 31/07/2024 | West Asset | -92 | On track | L1 | OP23 Above the Plan in LE | 31/05/2024 | 31/07/2024 | 30/09/2024 | 30/11/2024 | 31/01/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #materials | 22/03/2024 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Felicia Enechi | 2024-Sales of SPDC Scrap Materials | I-3676034 | USD | 90000 |  |  |  |  | 31/08/2024 | West Asset | -61 | On track | L2 | OP23 Above the Plan in LE | 30/04/2024 | 30/06/2024 | 31/08/2024 | 30/10/2024 | 31/01/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #materials | 22/03/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluwakemi Patrick-Oko | 2024-SPDC Cost savings from negotiated contracts_ SC Ops | I-3003126 | USD | 114000 | USD | 114000 | USD | 21538.61 | 30/11/2024 | CP | 30 | On track | L3 | OP23 In Plan | 2024-08-01 | 30/09/2024 | 31/10/2024 | 30/11/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #others | 15/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | John Uduaghan | Auctioning of Decommissioned kitchen Equipment and Furniture in FLBs | I-3041236 | USD | 400000 |  |  |  |  | 2024-01-10 | Real Estate | -30 | On track | L1 | OP23 Above the Plan in LE | 24/09/2024 | 2024-01-10 | 2024-08-10 | 29/10/2024 |  | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Non Structural / One-off saving | #materials | 23/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | odinaka omanukwue | Benchmark sourcing strategies (Contract, Pcard, etc) before placing orders | I-1345389 | USD | 66666.68 | USD | 66666.68 |  |  | 2024-12-12 | Real Estate | 42 | On track | L3 | OP22 In Plan; OP23 In Plan |  | 30/06/2023 | 31/07/2024 | 2024-12-12 | 18/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Avoidance | #others | 2022-01-12 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Joel Oladesemola | Carry out PMs of generators in PHC IA and RA based on condition monitoring. | I-3791326 | USD | 350000 | USD | 350000 | USD | 296412.68 | 30/11/2024 | Real Estate | 30 | On track | L3 | OP23 Above the Plan not in LE | 24/06/2024 | 28/06/2024 | 25/07/2024 | 30/11/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving |  | 18/04/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Bomo Keme | Construction, Replacement and Repair of Flowlines- SPDC Land | I-3870697 | USD | 176000 |  |  |  |  | 31/10/2024 | East Asset | 0 | On track | L1 | OP23 Above the Plan in LE | 30/04/2024 | 31/10/2024 | 30/11/2024 | 31/12/2024 | 31/12/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving |  | 30/04/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Bomo Keme | Construction, Replacement and Repair of Flowlines- SPDC Swamp | I-3870694 | USD | 210000 |  |  |  |  | 31/10/2024 | CP | 0 | On track | L1 | OP23 Above the Plan in LE | 30/04/2024 | 31/10/2024 | 30/11/2024 | 31/12/2024 | 31/12/2025 | Spdc Opex Efficiency - Asset cost |  |  | 30/04/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | odinaka omanukwue | Control Treated water to Golf Course Sprinklers to Save $12k by Dec 2024 | I-3041237 | USD | 12000 | USD | 12000 | USD | 2500 | 30/10/2024 | Real Estate | -1 | On track | L3 | OP23 Above the Plan not in LE | 23/05/2024 | 30/05/2024 | 2024-07-06 | 30/10/2024 | 15/12/2024 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Structural / Recurring saving | #infrastructure | 23/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Olamide Oladipupo | DD&T_Minimum Viable Company_Operations_SPDC | I-3385840 | USD | 350000 | USD | 350000 | USD | 525000 | 30/06/2024 | IT | -123 | On track | L3 | OP23 In Plan | 24/01/2024 | 18/02/2024 | 2024-04-03 | 30/06/2024 | 16/12/2024 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Structural / Recurring saving | #IT | 23/01/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ajiri Ivovi | Deploy Concrete Canvas BundWall Repairs & Road Erosion Control Application -2024 | I-3308951 | [7 empty] | Production Services |  | On track | L0 | OP23 In Plan; OP23 Above the Plan not in LE | [5 empty] | SPDC Opex Efficiency - Asset Cost |  | #mtce | 2024-09-01 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Sotonye Georgewill | Deploy Time-Based Milk run to avoid $0.5m marine cost by Dec 2024 | I-2889175 | USD | 600000 | USD | 600000 | USD | 774729.75 | 28/06/2024 | West Asset | -125 | On track | L4 | OP23 Above the Plan in LE | 2024-07-06 | 2024-11-06 | 13/06/2024 | 24/06/2024 | 28/06/2024 | Spdc Opex Efficiency - Asset cost | Cost Avoidance | #logistics | 25/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Goodi Emoghware | DIY activities in BOGT Q1 2024 | I-2926375 | USD | 144000 | USD | 235758 | USD | 129008 | 31/03/2024 | East Asset | -214 | On track | L3 | OP23 In Plan | 28/02/2024 | 2024-07-03 | 23/03/2024 | 31/03/2024 | 31/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #mtce | 30/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Goodi Emoghware | DIY activities in BOGT Q2 2024 | I-2926380 | USD | 785000 | USD | 147000 | USD | 24000 | 30/06/2024 | East Asset | -123 | On track | L3 | OP23 In Plan | 30/04/2024 | 30/04/2024 | 2024-01-05 | 30/06/2024 | 30/06/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #ops | 30/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Goodi Emoghware | DIY activities in BOGT Q3 2024 | I-2926382 | USD | 61000 | USD | 111000 | USD | 56000 | 30/09/2024 | East Asset | -31 | On track | L3 | OP23 Above the Plan in LE | 2024-05-07 | 2024-09-07 | 14/09/2024 | 30/09/2024 | 31/10/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #mtce | 30/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hope uwaya | DIY activities in FOT Q1 2024 | I-2926854 | USD | 100000 | USD | 100000 | USD | 10000 | 30/03/2024 | West Asset | -215 | On track | L3 | OP23 Above the Plan not in LE | 19/03/2024 | 20/03/2024 | 22/03/2024 | 30/03/2024 | 30/04/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hope uwaya | DIY activities in FOT Q2 2024 | I-2926855 | USD | 150000 | USD | 150000 | USD | 63888 | 23/12/2024 | West Asset | 53 | On track | L3 | OP23 Above the Plan not in LE | 2024-03-05 | 21/05/2024 | 2024-04-06 | 23/12/2024 | 23/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hope uwaya | DIY activities in FOT Q3 2024 | I-2926857 | USD | 200000 | USD | 150000 | USD | 85842.18 | 24/07/2024 | West Asset | -99 | On track | L3 | OP23 Above the Plan not in LE | 18/07/2024 | 22/07/2024 | 23/07/2024 | 24/07/2024 | 26/07/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Goddey Okposo | DIY activities in FOT Q4 2024 | I-2926875 | USD | 100000 |  |  |  |  | 29/10/2024 | West Asset | -2 | On track | L2 | OP23 Above the Plan not in LE | 15/10/2024 | 22/10/2024 | 29/10/2024 | 2024-06-11 | 17/01/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | nelson odien | DIY activities in NBNK PU by Q1 2024 | I-2926860 | USD | 240000 | USD | 240000 | USD | 375060 | 24/12/2024 | West Asset | 54 | On track | L3 | OP23 Above the Plan not in LE | 2024-06-02 | 16/02/2024 | 30/04/2024 | 24/12/2024 | 31/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | nelson odien | DIY activities in NBNK PU by Q2 2024 | I-3911078 | USD | 81000 | USD | 81000 | USD | 85000 | 30/06/2024 | West Asset | -123 | On track | L4 | OP23 Above the Plan in LE | 14/05/2024 | 30/05/2024 | 2024-04-06 | 2024-04-06 | 30/06/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving |  | 2024-07-05 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | nelson odien | DIY activities in NBNK PU by Q3 2024 | I-4373684 | USD | 80000 | USD | 80000 | USD | 111000 | 30/09/2024 | West Asset | -31 | On track | L4 | OP23 In Plan | 30/08/2024 | 2024-11-09 | 24/09/2024 | 26/09/2024 | 30/09/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving |  | 24/07/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | nelson odien | DIY activities in NBNK PU by Q4 2024 | I-4858886 | USD | 85000 |  |  |  |  | 30/10/2024 | West Asset | -1 | On track | L1 | OP23 In Plan | 30/10/2024 | 30/10/2024 | 27/11/2024 | 2024-04-12 | 30/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Avoidance |  | 2024-11-10 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Trust Meindinyo | DIY activities in OTUM PU by Q1 2024 | I-2926876 | USD | 100000 | USD | 100000 | USD | 136000 | 31/03/2024 | West Asset | -214 | On track | L3 | OP23 Above the Plan not in LE | 26/02/2024 | 29/02/2024 | 2024-01-03 | 31/03/2024 | 30/06/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Trust Meindinyo | DIY activities in OTUM PU by Q2 2024 | I-2926872 | USD | 100000 | USD | 100000 | USD | 180000 | 2024-08-07 | West Asset | -115 | On track | L3 | OP23 Above the Plan not in LE | 2024-01-06 | 2024-07-06 | 20/06/2024 | 2024-08-07 | 30/07/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Trust Meindinyo | DIY activities in OTUM PU by Q3 2024 | I-2926873 | USD | 100000 | USD | 100000 |  |  | 2024-10-09 | West Asset | -51 | On track | L3 | OP23 Above the Plan not in LE | 2024-10-07 | 19/07/2024 | 26/07/2024 | 2024-10-09 | 30/09/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | emmanuel chima | DIY activities in OTUM PU by Q4 2024 | I-2926877 | USD | 80000 | [5 empty] | West Asset |  | On track | L0 | OP23 Above the Plan not in LE | [5 empty] | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hyginus njoku | DIY Activities in Tunu Node, Q1 2024. | I-2926868 | USD | 70000 | USD | 70000 | USD | 70000 | 25/02/2024 | West Asset | -249 | On track | L3 | OP23 Above the Plan not in LE | 2024-04-01 | 13/01/2024 | 21/02/2024 | 25/02/2024 | 2024-02-04 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hyginus njoku | DIY Activities in Tunu Node, Q2 2024 | I-2926865 | USD | 38616.42 | USD | 38616.42 | USD | 38616.42 | 30/04/2024 | West Asset | -184 | On track | L3 | OP23 In Plan | 16/04/2024 | 16/04/2024 | 17/04/2024 | 30/04/2024 | 26/05/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hyginus njoku | DIY Activities in Tunu Node, Q3 2024. (Cost Saving) | I-2926869 | USD | 45080 | USD | 174280 | USD | 174280 | 2024-07-07 | West Asset | -116 | On track | L3 | OP23 Above the Plan not in LE | 2024-03-07 | 2024-05-07 | 2024-06-07 | 2024-07-07 | 31/10/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hyginus njoku | DIY Activities in Tunu Node, Q4 2024 | I-2926870 | USD | 81000 |  |  |  |  | 31/10/2024 | West Asset | 0 | On track | L2 | OP23 Above the Plan not in LE | 19/10/2024 | 24/10/2024 | 31/10/2024 | 19/12/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving | #mtce | 2023-02-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ikechukwu Oweh | DIY Initiative NUNR/D Q1 2024 | I-3674900 | USD | 7135 | USD | 7135 | USD | 7135 | 27/03/2024 | East Asset | -218 | On track | L4 | OP23 In Plan | 18/03/2024 | 20/03/2024 | 22/03/2024 | 25/03/2024 | 27/03/2024 | SPDC Opex Efficiency - Asset Cost | Cost Avoidance | #ops | 17/03/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ikechukwu Oweh | DIY Initiative NUNR/D Q2 2024 | I-4036128 | USD | 6831 | USD | 6831 | USD | 6831 | 15/06/2024 | East Asset | -138 | On track | L3 | OP23 In Plan | 29/05/2024 | 2024-04-06 | 2024-09-06 | 15/06/2024 | 25/06/2024 | SPDC Opex Efficiency - Asset Cost | Cost Avoidance |  | 26/05/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ikechukwu Oweh | DIY Initiative NUNR/D Q3 2024 | I-4682492 | USD | 20000 | USD | 20000 | USD | 200000 | 30/11/2024 | East Asset | 30 | On track | L3 | OP23 Above the Plan not in LE | 25/09/2024 | 2024-10-10 | 30/10/2024 | 30/11/2024 | 21/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving |  | 2024-11-09 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ikechukwu Oweh | DIY Initiative NUNR/D Q4 2024 | I-4947079 | [6 empty] | 19/11/2024 | East Asset | 19 | On track | L0 | OP23 Above the Plan not in LE | [5 empty] | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving |  | 20/10/2024 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | odinaka omanukwue | Extend SCPP TG730 from TBO 30k to 40k by PTM Implementation | I-2313541 | [6 empty] | 30/11/2023 | Real Estate | -336 | On track | L2 | OP23 Above the Plan not in LE | 31/07/2023 | 31/08/2023 | 30/11/2023 | 20/12/2023 | 20/12/2023 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving |  | 2023-03-07 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluleke Atanda | Finance download invoice application-FIDA | I-3951097 | USD | 2884.01 | USD | 2884.01 | USD | 2883.99 | 31/12/2024 | CP | 61 | On track | L4 | OP23 Above the Plan in LE | 28/05/2024 | 31/05/2024 | 2024-06-06 | 30/10/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Avoidance |  | 2024-12-05 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Blessing Lumati | Fuel Monitoring System And Vessel Tracking on SPDC Marine Vessels | I-1670935 | USD | 1000000 | USD | 1000000 |  |  | 30/09/2024 | Logistics | -31 | Needs attention | L3 | OP23 In Plan | 15/02/2023 | 19/03/2024 | 16/08/2024 | 30/09/2024 | 31/12/2026 | SPDC Opex Efficiency - Logistics | Cost Saving - Non Structural / One-off saving | #logistics | 2023-07-02 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Rotimi Jaiyeola | GBARAN Q2 DIY 2024 | I-3675404 | USD | 230152 | USD | 230152 | USD | 700000 | 2024-02-08 | East Asset | -90 | On track | L3 | OP23 In Plan | 19/03/2024 | 2024-05-04 | 31/07/2024 | 2024-02-08 | 21/08/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #ops | 19/03/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Chiemezie Ojiabo | GBARAN Q3 DIY 2024 | I-4681946 | USD | 45000 |  |  |  |  | 17/09/2024 | East Asset | -44 | On track | L1 | OP23 Above the Plan not in LE | 2024-11-09 | 17/09/2024 | 24/09/2024 | 31/10/2024 | 31/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving |  | 2024-09-09 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | odinaka omanukwue | IA/RA Power Generation Optimization( Solar and Paas) | I-4078736 | USD | 2555000 | USD | 2555000 |  |  | 30/11/2024 | Real Estate | 30 | On track | L3 | OP23 Above the Plan not in LE | 23/08/2024 | 26/08/2024 | 30/08/2024 | 30/11/2024 | 29/08/2025 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Structural / Recurring saving |  | 2024-07-06 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Simon Edache | Improve Earthing/LPS to eliminate lightning incidents in FOT - 2024 | I-3420912 | USD | 0 |  |  |  |  | 28/03/2024 | Production Services | -217 | On track | L2 | OP23 In Plan | 15/02/2024 | 15/03/2024 | 28/03/2024 | 15/08/2024 | 30/10/2024 | Spdc Opex Efficiency - Asset cost | Others | #mtce | 29/01/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | John Uduaghan | Improvement of service delivery in PHC RA Guest House | I-3041231 | [6 empty] | 31/10/2024 | Real Estate | 0 | On track | L1 | OP23 Above the Plan not in LE | 2024-11-10 | 31/10/2024 | 29/11/2024 | 31/12/2024 |  | SPDC Opex Efficiency - Above Asset Cost | Cost Avoidance | #infrastructure | 23/11/2023 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | odinaka omanukwue | Improve Metering of IA SCPP Gas Import | I-2313540 | USD | 240000 |  |  |  |  | 30/11/2023 | Real Estate | -336 | On track | L1 | OP22 Above the Plan not in LE; OP23 Above the Plan not in LE | 31/07/2023 | 30/11/2023 | 31/12/2023 | 30/04/2025 | 30/06/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #others | 2023-03-07 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | odinaka omanukwue | Improve UPS System in I.A & R.A or Managing UPS obsolescence in I.A & R.A | I-4638280 | USD | 300000 | USD | 300000 | USD | 300000 | 15/10/2024 | Real Estate | -16 | On track | L3 | OP23 Above the Plan not in LE | 2024-04-10 | 2024-04-10 | 2024-10-10 | 15/10/2024 | 2024-10-12 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving |  | 2024-06-09 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ikemefuna Okereke | Increase PHC RA Occupancy | I-0136905 | USD | 108429.86 | USD | 108429.86 | USD | 30741.81 | 30/11/2024 | Real Estate | 30 | On track | L3 | OP22 Above the Plan in LE; OP23 Above the Plan in LE | 28/02/2021 | 30/04/2023 | 31/05/2024 | 30/11/2024 | 31/12/2024 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Structural / Recurring saving | #infrastructure | 24/12/2020 | Other Income | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | jamilu buhari | Incur zero demurrage at SPDC Terminals. | I-2889155 | USD | 7000000 | USD | 7000000 |  |  | 31/12/2025 | West Asset | 426 | On track | L3 | OP23 Above the Plan not in LE | 16/02/2024 | 29/02/2024 | 31/03/2024 | 31/12/2025 | 31/01/2026 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #ops | 25/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ajiri Ivovi | INSPECT AFREMO A & B STRUCTURES USING ROV BY DECEMBER 2024 | I-3308950 | USD | 700000 |  |  |  |  | 30/04/2024 | Production Services | -184 | On track | L2 | OP23 In Plan; OP23 Above the Plan in LE | 23/02/2024 | 2024-08-03 | 30/04/2024 | 30/06/2024 | 29/11/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #mtce | 2024-09-01 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Gesi Liberty | Installation of Hiber Hilo Technology on Afremo wells | I-0267091 | USD | 808178.34 |  |  |  |  | 31/08/2022 | West Asset | -792 | On track | L2 | OP23 Above the Plan not in LE | 28/02/2022 | 31/05/2022 | 31/08/2022 | 30/09/2022 | 16/12/2022 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #logistics | 22/02/2022 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Anthony Yarhere | Integrated Pipeline Pigging Corrosion Services tender (IPPCCS) | I-3870689 | USD | 428000 |  |  |  |  | 31/07/2024 | CP | -92 | On track | L2 | OP23 Above the Plan in LE | 30/04/2024 | 31/05/2024 | 31/07/2024 | 30/09/2024 | 31/12/2025 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Structural / Recurring saving |  | 30/04/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Anthony Yarhere | Integrated Pipeline repair Services Contract | I-3870665 | USD | 400000 | USD | 400000 |  |  | 31/07/2024 | CP | -92 | On track | L3 | OP23 Above the Plan in LE | 30/04/2024 | 31/05/2024 | 31/05/2024 | 31/07/2024 | 31/12/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving |  | 30/04/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Alexander Samuel | Lease Agreement for Hotels currently used as extended FLBs | I-3041228 | [6 empty] | 31/10/2024 | Real Estate | 0 | On track | L1 | OP23 Above the Plan not in LE | 30/07/2024 | 31/10/2024 | 30/11/2024 | 31/12/2024 | 31/01/2025 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Structural / Recurring saving | #infrastructure | 23/11/2023 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Blessing Lumati | Lifting Inspection & Competency Certification Services | I-0867320 | USD | 2700 | USD | 2700 |  |  | 27/08/2025 | CP | 300 | On track | L4 | OP21 Above the Plan in LE; OP22 In Plan; OP23 In Plan | 30/09/2022 | 28/12/2022 | 30/08/2023 | 28/08/2024 | 27/08/2025 | SPDC Opex Efficiency - Logistics | Cost Avoidance | #mtce | 22/08/2022 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Henry Etukedung | Liquidate 30 RBSL Sites & save circa $300k OPEX by Nov 2024 | I-3041222 | USD | 300000 | USD | 300000 | USD | 202778 | 30/11/2024 | Pipelines | 30 | On track | L3 | OP23 Above the Plan in LE | 29/02/2024 | 29/03/2024 | 30/04/2024 | 30/11/2024 | 31/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #ops | 23/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ehiakhamen Eroms Q | Maintenance of Electronic Control Systems SPDC tender | I-3870656 | USD | 200000 |  |  |  |  | 31/10/2024 | West Asset | 0 | On track | L2 | OP23 Above the Plan in LE | 30/04/2024 | 31/07/2024 | 31/10/2024 | 31/12/2024 | 31/12/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving |  | 29/04/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Moses Osimi | Marine logistics cost improvement | I-3492444 | USD | 3400000 | USD | 4600000 | USD | 4824902.14 | 30/11/2024 | Logistics | 30 | On track | L3 | OP23 Above the Plan in LE | 2024-01-03 | 29/04/2024 | 31/07/2024 | 30/11/2024 | 31/01/2025 | SPDC Opex Efficiency - Logistics | Others | #logistics | 14/02/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Debo Ogunjimi | MEPSS for SPDC - 2024 | I-3003400 | USD | 11627267.28 | USD | 11627267.28 | USD | 10034021.41 | 31/12/2024 | CP | 61 | On track | L4 | OP23 In Plan | 30/11/2023 | 31/03/2024 | 29/04/2024 | 31/05/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #mtce | 20/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ehiakhamen Eroms Q | Metering Maintenance Services SPDC tender | I-3870657 | USD | 125000 | USD | 125000 |  |  | 31/12/2024 | Production Services | 61 | On track | L3 | OP23 Above the Plan in LE | 30/04/2024 | 31/07/2024 | 30/09/2024 | 31/12/2024 | 31/12/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving |  | 29/04/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ehiakhamen Eroms Q | Negotiation of Forcados DCS Upgrade proposal | I-2344793 | [6 empty] | 31/08/2023 | CP | -427 | On hold | L1 | OP23 Above the Plan in LE | 28/07/2023 | 31/08/2023 | 15/09/2023 | 30/09/2023 | 31/12/2023 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving | #mtce | 14/07/2023 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Nimi Onwah | Online Robotic Tank Inspection in FOT to save $500k by Nov 2024 | I-4770535 | USD | 500000 |  |  |  |  | 30/10/2024 | West Asset | -1 | On track | L2 | OP23 Above the Plan not in LE; OP24 In Plan | 30/09/2024 | 15/10/2024 | 30/10/2024 | 15/11/2024 | 31/12/2025 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving |  | 24/09/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Nasiru Gombe | OP 23 Marine Equipment Demand Vs Budget Optimization | I-2889163 | USD | 2400000 | USD | 2400000 | USD | 793258.22 | 30/11/2024 | Logistics | 30 | On track | L3 | OP23 Above the Plan not in LE | 2024-01-03 | 2024-05-03 | 30/06/2024 | 30/11/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Avoidance | #logistics | 25/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | John Uduaghan | OPEX Reduction from Adhoc Catering Services (SPDC) | I-0262276 | USD | 50814.84 | USD | 50814.84 | USD | 153972.01 | 31/08/2023 | Real Estate | -427 | On track | L3 | OP22 Above the Plan in LE; OP23 Above the Plan in LE | 25/03/2022 | 26/07/2022 | 29/07/2022 | 31/08/2023 | 15/12/2023 | SPDC Opex Efficiency - Above Asset Cost | Cost Avoidance | #catering | 28/01/2022 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Iyegoe Igali | OPTIMIZE NOV OP23 OPEX BUDGET BY $2M BY NOV 2024 | I-4078450 | USD | 2000000 | USD | 2000000 | USD | 1164000 | 28/11/2024 | NOV Onshore | 28 | On track | L3 | OP23 Above the Plan in LE | 13/06/2024 | 20/06/2024 | 27/06/2024 | 28/11/2024 | 19/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving |  | 2024-05-06 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ayodeji Aribisala | Optimize OPEX by Commitment Control in East Asset 2024 | I-2926593 | USD | 2000000 |  |  |  |  | 23/10/2024 | East Asset | -8 | On track | L2 | OP23 Above the Plan in LE | 29/05/2024 | 25/09/2024 | 23/10/2024 | 28/11/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #ops | 31/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | odinaka omanukwue | Power Supply Optimization for Ogunu Base in Warri | I-1682938 | [6 empty] | 2023-11-08 | Real Estate | -447 | On track | L2 | OP22 In Plan; OP23 Above the Plan in LE | 21/07/2023 | 31/07/2023 | 2023-11-08 | 30/11/2023 | 19/12/2023 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #others | 2023-10-02 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | odinaka omanukwue | Price agreement for critical spares on TAMAP list to achieve optimized cost | I-1345384 | USD | 29166.69 | USD | 29166.69 | USD | 12839.12 | 31/10/2024 | Real Estate | 0 | On track | L3 | OP22 In Plan; OP23 Above the Plan in LE |  | 31/08/2023 | 30/09/2024 | 31/10/2024 | 18/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving | #others | 2022-01-12 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Debo Ogunjimi | Provision maintenance servs for Siemens Compressors and Accessories SPDC - 2024 | I-3079156 | USD | 600000 | USD | 600000 | USD | 2411732.57 | 31/12/2024 | Production Services | 61 | On track | L4 | OP23 In Plan | 15/03/2024 | 30/03/2024 | 28/04/2024 | 30/05/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #mtce | 28/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | John Uduaghan | Provision of Adhoc Catering Services in Non Standard Shell locations | I-2042024 | USD | 60000 |  |  |  |  | 30/11/2024 | Real Estate | 30 | On track | L1 | OP22 Above the Plan not in LE; OP23 Above the Plan not in LE | 27/06/2023 | 30/11/2024 | 2024-01-12 | 15/12/2024 | 30/12/2024 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Structural / Recurring saving | #catering | 2023-02-05 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Debo Ogunjimi | Prov of Mtc Servs for Solar Turbines SPDC-13% Reduction in Contract Rates - 2024 | I-3079157 | USD | 500000.04 | USD | 500000.04 | USD | 623137.31 | 31/12/2024 | CP | 61 | On track | L4 | OP23 In Plan | 30/11/2023 | 31/03/2024 | 29/05/2024 | 30/06/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #mtce | 28/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Rotimi Jaiyeola | Q1 DIY activities in GBARAN 2024 | I-2926514 | USD | 73000 | USD | 73000 | USD | 25000 | 30/04/2024 | East Asset | -184 | On track | L3 | OP23 In Plan | 19/03/2024 | 27/03/2024 | 17/04/2024 | 30/04/2024 | 30/06/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #ops | 31/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ikechukwu Oweh | Reduce AGO consumption by optimizing FLB Genset operations for NunR by Oct, 2024 | I-2926516 |  |  | USD | 15744 | USD | 31994.88 | 31/12/2024 | East Asset | 61 | On track | L3 | OP23 In Plan | 22/02/2024 | 2024-02-03 | 2024-10-03 | 31/12/2024 | 30/01/2025 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #fuel | 31/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Henry Etukedung | Reduce pipeline MTTR by standardizing cofferdams _ deploy mobile accommodation | I-3041224 | USD | 1000000 | USD | 1000000 | USD | 259000 | 31/10/2024 | Pipelines | 0 | On track | L3 | OP23 Above the Plan in LE | 20/02/2024 | 29/02/2024 | 2024-12-04 | 31/10/2024 | 30/12/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Non Structural / One-off saving | #ops | 23/11/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Jonathan David | RUMUAHIA FACILITIES SOLAR POWER PROJECT | I-1345355 |  |  | USD | 37240 | USD | 15249 | 31/12/2023 | East Asset | -305 | On track | L4 | OP22 In Plan; OP23 In Plan | 31/12/2022 | 31/01/2023 | 30/04/2023 | 30/06/2023 | 31/12/2023 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #fuel | 2022-01-12 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluleke Atanda | SAP Access replacement with SCD -(SEPRA CONTRACT DETAIL)-NG01 | I-2539331 | USD | 262500 | USD | 262500 | USD | 262500 |  | CP |  | Completed | L5 | OP22 Above the Plan in LE; OP23 Above the Plan in LE | 25/08/2023 | 25/08/2023 | 25/08/2023 | 28/12/2023 | 31/12/2023 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving | #IT | 21/08/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluleke Atanda | SAP Access replacement with SCD -(SEPRA CONTRACT DETAIL)-SNBO, SEPA & SNCPFA | I-2619497 | [7 empty] | Corporate |  | Completed | L5 | OP22 Above the Plan in LE; OP23 Above the Plan in LE | 13/09/2023 | 26/09/2023 | 26/09/2023 | 28/09/2023 | 31/12/2023 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving | #IT | 2023-06-09 |  | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ikemefuna Okereke | Share Abuja Office Service charge to save $58k by Nov 2024 | I-3753013 | USD | 58000 | USD | 58000 |  |  | 20/11/2024 | Real Estate | 20 | On track | L3 | OP23 Above the Plan not in LE | 2024-11-09 | 19/09/2024 | 31/10/2024 | 20/11/2024 | 30/12/2024 | SPDC Opex Efficiency - Above Asset Cost | Cost Saving - Structural / Recurring saving |  | 16/04/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluleke Atanda | SODCAN BOT ACV RECOVERY 2 | I-3675841 | USD | 17207.99 | USD | 17207.99 | USD | 17207.99 |  | CP |  | Completed | L5 | OP23 Above the Plan in LE | 17/05/2024 | 30/05/2024 | 30/06/2024 | 30/12/2024 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving |  | 21/03/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Mukhtar Sani | Soku 2024 Savings via DIY and OPEX Optimisation | I-2926388 | USD | 206000 | USD | 206000 | USD | 2335944.57 | 31/07/2024 | East Asset | -92 | On track | L3 | OP23 In Plan | 27/02/2024 | 2024-12-03 | 27/03/2024 | 31/07/2024 | 25/09/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving | #mtce | 30/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Ikechukwu Oweh | Solar Project for NunR & DBUC in 2024 | I-2926522 | USD | 14756 |  |  |  |  | 30/08/2024 | East Asset | -62 | On track | L2 | OP23 In Plan | 2024-02-01 | 2024-02-02 | 30/08/2024 | 30/09/2024 | 31/10/2024 | SPDC Opex Efficiency - Asset Cost | Cost Saving - Structural / Recurring saving | #fuel | 31/10/2023 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Alexander Samuel | SPDC Hotels and Travels demand reduction_2024 | I-3492462 | USD | 13000000 | USD | 9000000 | USD | 5000000 | 30/11/2024 | Real Estate | 30 | On track | L3 | OP23 Above the Plan not in LE | 21/02/2024 | 2024-05-04 | 20/04/2024 | 30/11/2024 | 31/12/2024 | SPDC Opex Efficiency - Above Asset Cost | Others | #travel | 14/02/2024 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Onuoha-Isiodu Joy | SPDC Material Re-Use (O) - 2024 | I-2964181 | USD | 2000000.04 | USD | 2000000.04 | USD | 2680991.49 | 2024-12-12 | Production Services | 42 | On track | L3 | OP23 Above the Plan in LE | 23/01/2024 | 2024-01-02 | 31/10/2024 | 2024-12-12 | 31/12/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #materials | 2023-09-11 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Oluleke Atanda | Tender Tracker (Contrack | I-4078239 | USD | 75000 | USD | 75000 | USD | 75000 | 17/11/2024 | CP | 17 | On track | L4 | OP23 Above the Plan in LE | 25/06/2024 | 30/06/2024 | 2024-08-07 | 20/08/2024 | 17/11/2024 | Spdc Opex Efficiency - Asset cost | Cost Avoidance |  | 2024-03-06 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hyginus njoku | Tunu Node COST Avoidance on GTG N+1 restoration FOR Q1 2024 (March 20th ,2024) | I-3713567 | USD | 50000 | USD | 50000 | USD | 50000 | 23/03/2024 | West Asset | -222 | On track | L3 | OP23 In Plan | 2024-09-03 | 2024-11-03 | 19/03/2024 | 23/03/2024 | 30/04/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving |  | 2024-01-04 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | hyginus njoku | TUNU NODE COST SAVING FOR Q1 2024 (25th Feb, to 4th March, 2024) | I-3600897 | USD | 57960 | USD | 57960 | USD | 57960 | 2024-06-03 | West Asset | -239 | On track | L3 | OP23 In Plan | 25/02/2024 | 27/02/2024 | 2024-04-03 | 2024-06-03 | 31/03/2024 | Spdc Opex Efficiency - Asset cost | Cost Saving - Non Structural / One-off saving |  | 2024-08-03 | Opex | 2024-10-31
Lasbery Ogofia | CJ Akwaeze | Efe Otofia | Wells OPEX Cost Optimization Opportunities 2024 | I-3713309 | USD | 1500000 | USD | 1500000 | USD | 1100000 | 30/11/2024 | Wells | 30 | On track | L3 | OP23 Above the Plan not in LE | 28/03/2024 | 2024-12-04 | 30/04/2024 | 30/11/2024 | 31/01/2025 | Spdc Opex Efficiency - Asset cost | Cost Saving - Structural / Recurring saving | #others | 27/03/2024 | Opex | 2024-10-31