## Slide 1: Optimization of ETSOM Global Charges to save $1M ($440K by Dec 2023 & $560K by 2024)
Fit4 ID
I-0899428
Workstream | Opex
Location(s) | SPDC
Current L-Gate | L1 | Initiative Lead | Ubong EDEM
L1 Date | 01 Sep 2022 | Initiative Sponsor | Femi ADEYEMI
L2 Date | 31 March 2023 |  | 
Problem Statement
It currently costs SCiN circa $13M in ETSOM Global Charges which covers GI accounts and associated services for both staff and contractors, with GI for staff accounting for $3.8M of the total cost, while GID for contractors and shared associated services costs account for $2.9M and $6.3M respectively. Post reshape, it has become increasingly difficult to secure JV partners approval to service these charges as number of staff is expected to have reduced with likelihood of a Category 3B cost recovery risk. There is opportunity, therefore, to optimize the number of GI accounts and associated services cost to reflect reduced staff numbers post reshape by using cheaper alternatives to GI accounts and save circa $1M.
Initiative Description
This initiative seeks to optimize ETSOM Global Charges by migrating some eligible personnel GI accounts to a cheaper alternative platform. Key areas of focus are: Upgrade, identify and resolve any performance issues on the alternative platform Migrate about 400 GI-D account users to the alternative platform in 2023 and 600 in 2024 Optimize consumption items/cost buckets for possible additional savings
Estimate Impact
High level assumptions – $440K target savings in 2023 & $560K in 2024.
Key Stakeholders
Project Sponsor: Femi Adeyemi Steering Committee: Femi Adeyemi, Oghale Akpobome, Olamide Oladipupo, Adeolu Okanlawon Implementation Lead: Ubong EDEM, Eka Ituen, Onyeugwuakazi Michael Project Team: Ubong EDEM, Eka Ituen, Enyinnaya Ikedichi, Femi Ejiwunmi, Kings Ituen, Uche Nwichi, Bobby Ekpo, Emuobosa Fabolude
Decisions needed to mature
Go/No decision post pilot implementation Approval for migration of nominated accounts by respective GMs

## Slide 2: Status Update
Action No. | Action Item | Owner | Status | Current Progress | Next Steps
1 | Configure the initial Lab hardware | Ejiwunmi | Done | 13 test laptops setup for the pilot testing | 
2 | Develop a configuration design for the SCIN-Connect PC | Ejiwunmi/Johnson | Ongoing | Configuration design is being documented | 
3 | Identify tester community | ICE | Done | Pilot users identified | 
4 | Develop application test scripts | ICE/Bobby | Ongoing | Test scripts developed for 37 out of 65 applications. Other scripts are being developed on case-by-case basis in consultation with the application users. Also, further reductions expected from rationalization project. | 
5 | Business engagement and communication to testers | Edem/Mike | Done | Draft communication reviewed and ready for use | 
6 | Onboard testers | Ejiwunmi | Not Started |  | 
7 | Carry out apps testing | Testers | Not Started |  | 
8 | Resolve issues from the testing | Edem/Mike | Not Started |  | 
9 | Improve performance - local Citrix server* | Nwichi | Ongoing | Global team providing support to improve time it takes to open applications. Local citrix implementation not currently considered. Rollout of New TPA environment in Nigeria scheduled for 05/09/23. | 
10 | Improve performance - network connectivity | Ituen | Done | Internet breakout upgrade improved UX Tests carried out on network security (SSL and user authentication) implementation by the group failed for users on LAN. Risk acceptance for a one-year step-out for Nigeria signed off by SOM | 
11 | Support Improvement and documentation | Ejiwunmi | Ongoing | Weekly cadence with support team creating support documentations | 
12 | Review the testing outcome; Go/No-Go Decision | Eka/Mike/LT | Not Started |  | 
13 | Analyse Aternity data to identify users to migrate | Edem/Mike | Ongoing |  | 
14 | Batch users for migration | Edem/Mike | Not Started |  | 
15 | Develop a communication strategy | Edem/Mike | Ongoing |  | 
16 | Execute the comms plan | TBA | Not Started |  | 
17 | Print the SCIN-Connect sticker |  | Not Started |  | 
18 | GM validation of migration list | IDTM | Not Started |  | 
19 | Migrate batch 1 - N users | Edem/Ejiwunmi/Mike | Not Started |  | 

## Slide 3: Time Adjustments
Change impact to OfficeGST login/resolution
Rollout of New TPA environment in Nigeria by the Global team scheduled for 05/09/23.
Change in PM
Activity | Initial timeline | Revised Timeline
Pilot Testing | 15/05 -15/06/23 | 11 - 25/09/23
Resolve issues from testing | 20/05 -15/07/23 | 11/09 - 09/10/23
Review entire feedback/test experience/(Go/No go decision) | 01-07/07/23 | 09 -16/10/23
Batch 1 Migration starts (With a “GO” decision) | 15/07/23 | 23/10/23

## Slide 4: Proposed Implementation Plan
2023 | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec | 
Hardware Provisioning and Platform testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Support Organization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Improve and Rebrand |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Migrations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Major Milestone
Decision
Setup test hardware platform
Develop test scripts for existing applications
Identify and Onboard Testers
Run Pilot testing
Review support organisation and optimise
Optimise Request & onboarding process
Resolve issues from testing
Develop User guides and support documentations
Troubleshoot & fix Platform Performance issues
Procure branding items
Execute Comms Plan
Develop Comms Plan
Analyze user usage data
Migrate identified personnel in other functions
Hardware Strategy Agreed
Users to Migrate agreed by lines
Migration begins
Batch users into phases

## Slide 5: Previous Implementation Plan
2023 | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec | 
Hardware Provisioning and Platform testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Support Organization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Improve and Rebrand |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Migrations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Major Milestone
Decision
Setup test hardware platform
Develop test scripts for existing applications
Identify and Onboard Testers
Run Pilot testing
Review support organisation and optimise
Optimise Request & onboarding process
Resolve issues from testing
Develop User guides and support documentations
Troubleshoot & fix Platform Performance issues
Procure branding items
Execute Comms Plan
Develop Comms Plan
Analyze user usage data
Migrate identified personnel in other functions
Pilot Users migrated for test
Hardware Strategy Agreed
Users to Migrate agreed by lines
Migration begins
Batch users into phases