## Slide 1
  Background
  Due to movement of personnel within the organization, Technical gaps have been observed in the frontline.
  This initiative aims to put a structure in place to identify and close out gaps as well as facilitate technical competence assurance for frontline personnel.
  Objectives
  To develop a more competent workforce and to boost their morale at the frontlines
  Develop more technically competent frontline personnel.
  Provide opportunities for multi-skilling, upskilling, ownership and responsibility
  Build a sense of empowerment and pride in the assets
  (Potential) Solutions
  Technical Coaching Sessions
  On the Job training at sites
  Workshops
  Benefits
  More competent personnel manning facilities
  Improved facility uptime and availability
  Better risk appreciation in work execution at the frontline (improved safety).
  Improve ownership and accountability
Technician Competence Improvement Initiative
Key Task/Milestone | When
Gap identification | March 2023
Secure commitment with Technical Authorities | March 2023
Categorise Gaps (Coaching in specialist/general areas) | April 2023
Strategize on inhouse and external focus areas | April 2023
Secure nomination from PU’s | April 2023
Work with different functions (META,MRTA, engineering etc)for coaches. | May 2023
Commence coaching workshops for different (PACO, Mech, disciplines | May 2023
Review Progress | August 2023
  Resource/Team
  Soba Osuji Bells- Production Capability Manager
  Otoakhia, Iroboudu
  John Nna-Okpabi
  Onibonoje Olayiwola
  Mike Dawodu
  Chibuzo Onumadu
  Awe Afolabi
  Oluseye Phillips
  Nsikak Ekpoh
  Diana Osaigbovo
  Functional SME’s