## Slide 1: Project Title: Replace corroded F/l section to restore Saghr3S prod by April 2021
Business Case/Objectives:
Saghara Flowstation has been mothballed and wells flowing to the station routed to Otumara flowstation. One of the Wells affected is Saghara 3S that was last produced March 2013 and has a potential of 629 bbls. This volume is void of the expected flush production expected to be more than the known well potential.
There is an opportunity for Escravos/Otumara PU to meet her OP20 production target by flowing Saghr3S via any of the available lines - Test or bulk header (tested & certified integral) to Otumara flowstation to realize the LIP of the well.
Asset Engineering is required to carry out flowline sectional replacement to enable asset team lock the Well potential of 629 bbls
Potential Benefits & Measurement:
Volume Benefit: Increase production availability of Otumara by 629bopd and meet the PU’s OP20 production target.
Safety & Integrity: Asset Engineering to mobilize to site and carry out sectional replacement
Production gains:
Additional production of 629bopd
Implementation Cost: $200K
FCF approx. $1.08m
Critical Success Factors:
Rectify SCSSV issue to clear Well failure Model rating Action Code 9 and make well available for operation team to open.
  Project Sponsor: Oyedele Oyebode.
  Team Members: Imoh Isang, Ewarah Erhumu Ikoho Anthony, & Akasa Dekawei
  Implementation/Project Lead: Anoruse Thomas
Action | Responsible Team | Timeline
Liaise with Asset Engineering to scope F/L sectional | Anoruse | March 1, 2021
Secure FTO/CTS | Adedeji Tolulope | March 15, 2021
Secure Budget approval | Sagbe Seprebo | March 8, 2021
Carry out sectional replacement of Saghr3S flowline | Sagbe Seprebo/Uche Egunatum | April 25, 2021
Open up Saghr3S | Imoh Isang/Ewarah Erhumu | April 30, 2021