## December 2023
Row Labels | Plan ($, M) | Forecast ($, M) | Actual ($, M)
Deepwater Projects | 5.5664 | 6.4143 | 8.2737
Wells | 4.2312 | 19.1124 | 16.496
Bonga Production | 298.1817 | 397.6826 | 375.7959
Erha Production | 26.3926 | 38.4958 | 61.6729
Abex | 7.2634 | 15.682 | 14.001
Opex Efficiency | 4.1723 | 3.2675 | 3.4677
Grand Total | 345.8077 | 480.6545 | 479.7072

## 2023 Dec Performance
Workstream Name | Work Stream 2 | Workstream Sponsor: Full Name | Workstream Lead: Full Name | Owner: Full Name | Idn | Initiative Name | Planned Date | Actual L-Gate | Overall status | Yearly Planned value | Yearly Forecast value | Yearly Actual value | Plan | Forecast | Actual | Plan Relevance | Formula Data Filter 1 | Formula Data Filter 2 | HashTag # | Created Date | Date Downloaded
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Paul Anyankpele | I-1742172 | BMIRP: FSV utilization optimization | NULL | L5 | Completed | 84000 | 84000 | 84150 | 0.084 | 0.084 | 0.08415 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-2889044 | IPF reclassification project - Efficient Execution | NULL | L5 | Completed | 170864 | 140675.97 | 140675.97 | 0.17086 | 0.14068 | 0.14068 | OP22 Above the Plan in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-1344935 | FD-1: HFL procurement optimization | NULL | L5 | Completed | 41250 | 24000 | 24390 | 0.04125 | 0.024 | 0.02439 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-1344934 | FD-1: SCM/choke refurb optimization | NULL | L5 | Completed | 82500 | 82500 | 99000 | 0.0825 | 0.0825 | 0.099 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-2505483 | FD-1 Optimize B57XT tree refurbishment (Workshop hours and 3rd party scope) | NULL | L5 | Completed | 185000 | 185000 | 288750 | 0.185 | 0.185 | 0.28875 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1640372 | As built Update of engineering documents_ Optimize use | NULL | L5 | Completed | 4125 | 0 | 0 | 0.004125 | 0 | 0 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | 2023-01-02 | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-2101583 | FD1: Optimization of PM cost for tree Refurbishment | NULL | L5 | Completed | 41000 | 41000 | 53625 | 0.041 | 0.041 | 0.053625 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-2101581 | FD-1: Contingency Cost Reduction | NULL | L5 | Completed | 363825 | 363825 | 363825 | 0.36383 | 0.36383 | 0.36383 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-2739439 | Additional BMIRP Savings (FSV cost, Owners Cost, Travels & Customs duties) | NULL | L5 | Completed | 300000 | 453750 | 453750 | 0.3 | 0.45375 | 0.45375 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Nonye Eforuoku | I-2191415 | Early Payment Discount Initiative_EPCm Contract _IESL | NULL | L0 | On track | 41250 | 0 | 0 | 0.04125 | 0 | 0 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | 2023-07-06 | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Olaniyi Ilesanmi | I-2659278 | BMLE Portfolio PSCS Upgrade Optimization | NULL | L5 | Completed | 272250 | 253415.77 | 253415.77 | 0.27225 | 0.25342 | 0.25342 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | 2023-12-09 | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Opeyemi Ogunlade | I-1344936 | Bonga Alarm Management - manhours reduction | NULL | L5 | Completed | 4743.75 | 4743.75 | 4743.75 | 0.0047437 | 0.0047437 | 0.0047437 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-1344933 | FD-1: tree refurb spares procurement optimization | NULL | L5 | Completed | 206250 | 206250 | 779625 | 0.20625 | 0.20625 | 0.77963 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-1344931 | FD-1: jumper spools and kit procurement optimization | NULL | L5 | Completed | 206250 | 103125 | 103125 | 0.20625 | 0.10312 | 0.10312 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Samson Oguejiofo Osolu | I-1344932 | BMIRP: HFL / EFL procurement optimization | NULL | L5 | Completed | 82500 | 82500 | 207141 | 0.0825 | 0.0825 | 0.20714 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-1344929 | FD-1: TH/THS optimization | NULL | L5 | Completed | 412500 | 412500 | 552750 | 0.4125 | 0.4125 | 0.55275 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310358 | Hose change out (20 lines) - optimized execution | 2023-08-30 | L3 | On hold | 16763 | 10000 | 0 | 0.016763 | 0.01 | 0 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310353 | Crane Upgrade - optimized logistics & offshore execution | NULL | L5 | Completed | 82500 | 492108.39 | 492108.39 | 0.0825 | 0.49211 | 0.49211 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310373 | 25 FIT-203 Crude run-down meter - alternative materials and resourcing approach | NULL | L5 | Completed | 413 | 413 | 8250 | 0.000413 | 0.000413 | 0.00825 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310377 | Redesign of Solar supplied Simplex Liquid Fuel Filter FS-934 & HP Liquid Fuel fi | NULL | L5 | Completed | 41131 | 709092.04 | 709092.04 | 0.041131 | 0.70909 | 0.70909 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310375 | SPM booster pump voith coupling - optimized execution | NULL | L5 | Completed | 413 | 2100 | 0 | 0.000413 | 0.0021 | 0 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Avoidance | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310364 | Instal of 2nd isolation barrier on Bonga scrubber bridle drain - alternativ mats | NULL | L5 | Completed | 1093 | 1093 | 17845.11 | 0.001093 | 0.001093 | 0.017845 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310359 | Conversion of temporary to permanent equipment - optimized execution | NULL | L5 | Completed | 7838 | 3500 | 18562.5 | 0.007838 | 0.0035 | 0.018562 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310363 | Online corrosion monitoring probe on F lines WF - alternative mats & resourcing | NULL | L5 | Completed | 1134 | 1134 | 10738.01 | 0.001134 | 0.001134 | 0.010738 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310352 | Minox replacement - interface engineering estimate reduction | NULL | L5 | Completed | 41250 | 33000 | 39187.5 | 0.04125 | 0.033 | 0.039188 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310350 | Mooring Chain Replacement (remove connecting arm scope) | NULL | L5 | Completed | 1567500 | 1000000 | 1864500 | 1.5675 | 1 | 1.8645 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310360 | Accommodation sewage down comer 2" pipework & headers - optimized mats & exec | 2023-08-31 | L3 | On hold | 1894 | 0 | 0 | 0.001894 | 0 | 0 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-2407868 | BMIRP: Slot Doubler Duties and Taxes | NULL | L5 | Completed | 200000 | 200000 | 200000 | 0.2 | 0.2 | 0.2 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Omolola Ayeni | I-2407863 | BMIRP: Contingency Drop | NULL | L5 | Completed | 170000 | 170000 | 170000 | 0.17 | 0.17 | 0.17 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310357 | Replacement of ODME - optimized execution targeting 3% savings | NULL | L5 | Completed | 4788 | 49500 | 62737.54 | 0.004788 | 0.0495 | 0.062738 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310351 | STOMP: efficient execution on procurement, installation & comm | NULL | L5 | Completed | 177217 | 177217 | 765940.31 | 0.17722 | 0.17722 | 0.76594 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310370 | Replacement of check valves with pup pieces - alternative materials and resourci | NULL | L5 | Completed | 1134 | 1134 | 22687.5 | 0.001134 | 0.001134 | 0.022687 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310395 | CDR structural - drop objects batch (2) 63 no.s - optimized execution | NULL | L5 | Completed | 1407 | 12375 | 12375 | 0.001407 | 0.012375 | 0.012375 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310366 | Back pressure control valve/blow down of FGS - optimized execution | NULL | L5 | Completed | 4208 | 4208 | 4125 | 0.004208 | 0.004208 | 0.004125 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310392 | CDR waterflood batch 6-10 - optimized execution | NULL | L5 | Completed | 23625 | 23625 | 23625 | 0.023625 | 0.023625 | 0.023625 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310403 | Bonga IT equipment optimization | NULL | L5 | Completed | 3094 | 39600 | 39600 | 0.003094 | 0.0396 | 0.0396 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310401 | PM Cost Optimization | NULL | L5 | Completed | 73314 | 386893.85 | 386887.04 | 0.073314 | 0.38689 | 0.38689 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Musa Aliyu | I-1310397 | CDR structural - drop objects 74 no.s - optimized execution | NULL | L5 | Completed | 3869 | 16500 | 16500 | 0.003869 | 0.0165 | 0.0165 | OP22 Above the Plan not in LE | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Deepwater Projects | Deepwater Projects | Aiboni Elohor J | Otubanjo Babafemi O | Osita Anako | I-2101697 | Alternative Delivery Strategy for Bonga OML 118 OBN Seismic EIA Study | 2023-09-30 | L3 | On track | 643500 | 643500 | 0 | 0.6435 | 0.6435 | 0 | OP22 In Plan | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Ejiro Emifoniye | I-1309844 | 2023 Drilling Campaign In-plan Savings | 2023-05-31 | L4 | On track | 1619062.08 | 1619062.08 | 1619062.08 | 1.6191 | 1.6191 | 1.6191 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Ejiro Emifoniye | I-1309845 | 2023 Drilling Campaign Above-plan Savings | 2023-05-25 | L3 | On track | 1619062.08 | 17493305 | 14876954.99 | 1.6191 | 17.4933 | 14.877 | OP22 Above the Plan not in LE | Wells | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Boham Kalada D | I-1578557 | Deployment of the Jetting tool technology for well stimulation | 2023-04-30 | L2 | On track | 174460 | 0 | 0 | 0.17446 | 0 | 0 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | Wells | NULL | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Boham Kalada D | I-1578556 | Reduced service cost for the provision of Coiled Tubing services | 2023-04-30 | L2 | On track | 348920 | 0 | 0 | 0.34892 | 0 | 0 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | Wells | NULL | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Boham Kalada D | I-1578555 | Reduction in service cost for the Provision of Frac and Pac services | 2023-04-30 | L2 | On track | 174460 | 0 | 0 | 0.17446 | 0 | 0 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | Wells | NULL | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Boham Kalada D | I-1609676 | Cost reduction for Cementing Services, Float Equipment and Casing Accessories | 2023-06-30 | L2 | On track | 167750 | 0 | 0 | 0.16775 | 0 | 0 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | Wells | NULL | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Boham Kalada D | I-1671017 | Reduced service rates for the supply of OCTG for SNEPCO drilling operations | 2023-03-31 | L2 | On track | 51000 | 0 | 0 | 0.051 | 0 | 0 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | Wells | 2023-07-02 | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Boham Kalada D | I-1671018 | Reduced service rates for the supply of Wellhead equipment for SNEPCO operations | 2023-04-30 | L2 | On track | 51000 | 0 | 0 | 0.051 | 0 | 0 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | Wells | 2023-07-02 | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Boham Kalada D | I-1671014 | GE PCSNL savings on Wellhead supplies | 2023-06-30 | L2 | On track | 12750 | 0 | 0 | 0.01275 | 0 | 0 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | Wells | 2023-07-02 | 2023-12-20
SNEPCo Capex Efficiency - Wells | Wells | Aiboni Elohor J | Ismail Hamzat | Boham Kalada D | I-1670973 | Savings from OCTG supply when compared to SPDC price | 2023-06-30 | L2 | On track | 12750 | 0 | 0 | 0.01275 | 0 | 0 | OP22 In Plan | Wells | Cost Saving - Non Structural / One-off saving | Wells | 2023-07-02 | 2023-12-20
SNEPCo Commercial | SNEPCo Commercial | Aiboni Elohor J | Uche Ogbue | Enam Ngwobia | I-1640148 | OML 118 Education Tax Stabilization | NULL | L5 | Completed | 2020051.46 | 2020051.46 | 3366257.89 | 2.0201 | 2.0201 | 3.3663 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Samson Onoh | I-0169183 | POR: Solar Turbines Mgt. (GTs & FGCs) - Proposed Self Cleaning Air Inlet Filter | NULL | L0 | On track | 13750 | 0 | 0 | 0.01375 | 0 | 0 | OP22 Above the Plan not in LE | NULL | NULL | NULL | 2021-12-04 | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1274313 | Above Plan - B37 Support from B72 Injector well (+4.5kbopd) | 2024-01-31 | L4 | On track | 19845000 | 16981550 | 14603190 | 19.845 | 16.9815 | 14.6032 | OP22 Above the Plan not in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chukky Ochonogor | I-1274310 | Above Plan - Acceleration of FD 1 Project OSD by 5 months (+2.4kbopd ) | NULL | L5 | Completed | 10584192.78 | 13310930 | 15103930 | 10.5842 | 13.3109 | 15.1039 | OP22 Above the Plan not in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chukky Ochonogor | I-1274311 | Above Plan - 702w10 Acceleration to Aug 2023 (+1.5kbopd) | NULL | L5 | Completed | 8379003.6 | 10771654.79 | 13536884.79 | 8.379 | 10.7717 | 13.5369 | OP22 Above the Plan not in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-0205941 | Integrated Visualization Manager (IVM) Deployment | 2024-01-31 | L4 | On track | 2116800 | 1343690 | 894090 | 2.1168 | 1.3437 | 0.89409 | OP22 In Plan | Production Assets | Production Increase | NULL | 2021-03-10 | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1771770 | Bonga Flowline Digital Twin for slug and production optimisation | 2024-01-31 | L4 | On track | 4410000 | 2622403 | 748780 | 4.41 | 2.6224 | 0.74878 | OP22 Above the Plan not in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | francis alegbe | I-1771766 | Bonga Extra Cargo | NULL | L5 | Completed | 80000000 | 193800000 | 193800000 | 80 | 193.8 | 193.8 | OP22 Above the Plan not in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Ofonmbuk Ubong | I-2440322 | OP22 SNEPCo Marine Vessels Optimization | 2024-02-29 | L4 | On track | 846923.1 | 942912.54 | 942912.54 | 0.84692 | 0.94291 | 0.94291 | OP22 Above the Plan in LE | Production Assets | Cost Saving - Non Structural / One-off saving | NULL | 2023-04-08 | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1609792 | Optimization of 2023 MER | 2024-01-31 | L4 | On track | 308700 | 458740 | 2211030 | 0.3087 | 0.45874 | 2.211 | OP22 Above the Plan not in LE; OP23 Above the Plan not in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1274308 | Above Plan - B72 Acceleration to 2022 with a 1.1kbopd new oil addition (B71) | 2024-01-31 | L4 | On track | 36178848 | 36244904 | 35098800 | 36.1788 | 36.2449 | 35.0988 | OP22 Above the Plan not in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1274668 | Production Metering Re-instatement and Optimization (0.5kbopd) | 2024-01-31 | L3 | On track | 1626000 | 1626000 | 0 | 1.626 | 1.626 | 0 | OP22 In Plan; OP23 In Plan | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1274665 | PSO-Changes within the existing Wells & Facilities envelopes | 2024-01-31 | L3 | On track | 46305000.5 | 43100473.6 | 48521880 | 46.305 | 43.1005 | 48.5219 | OP22 In Plan; OP23 In Plan | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1274306 | In-Plan Delivery of 12.8 kbopd new oil in 2023 | 2024-01-31 | L4 | On track | 56492100 | 55433931 | 48389180 | 56.4921 | 55.4339 | 48.3892 | OP22 In Plan | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1274686 | Strategy Refresh part 2 implementation (2 kbopd) | NULL | L5 | Completed | 8820000 | 8820000 | 0 | 8.82 | 8.82 | 0 | OP22 In Plan | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-2375886 | Carrying out Leak-off Test without Injection Pump Shutdown | NULL | L5 | Completed | 1087410 | 1087410 | 229560 | 1.0874 | 1.0874 | 0.22956 | OP22 In Plan; OP23 In Plan | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-3003349 | OP23: LOT Frequency Optimization | 2024-02-29 | L0 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 Above the Plan in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-1447945 | Wells B43 Sealtite Restoration | 2024-01-31 | L4 | On track | 13230000 | 3200000 | 1715670 | 13.23 | 3.2 | 1.7157 | OP22 Above the Plan not in LE | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Bonga Production | Bonga Production | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-0206841 | Production Enhancement ? Emulsion Viscosity Reducers | 2024-01-31 | L3 | On track | 7938000 | 7938000 | 0 | 7.938 | 7.938 | 0 | OP22 In Plan | Production Assets | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0039702 | Restoration of Erha-33 Well | 2023-03-31 | L1 | On track | 2070740 | 3623795 | 3751530 | 2.0707 | 3.6238 | 3.7515 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE; OP23 Above the Plan not in LE; OP20 In Plan | NOV Offshore | Production Increase | #16841 | 2020-02-08 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0039705 | Restoration of Erha-25 well | 2023-12-15 | L4 | On track | 637150 | 5508575 | 8688990 | 0.63715 | 5.5086 | 8.689 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE; OP20 In Plan | NOV Offshore | Production Increase | #17014 | 2020-02-08 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0039760 | Restoration of Erha-50 well | 2023-12-15 | L4 | On track | 572600.1 | 270866.7 | 86410 | 0.5726 | 0.27087 | 0.08641 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE; OP20 In Plan | NOV Offshore | Production Increase | #18654 | 2020-02-08 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0210953 | Water injection pump (WIP#9) maintenance & repair | 2023-10-31 | L3 | On track | 800000 | 400000 | 0 | 0.8 | 0.4 | 0 | OP21 In Plan; OP22 In Plan | NOV Offshore | Production Increase | NULL | 2021-02-12 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0210956 | Well Intervention: ER-17 | 2022-10-31 | L1 | On track | 695450 | 347725 | 0 | 0.69545 | 0.34773 | 0 | OP22 Above the Plan not in LE; OP23 Above the Plan not in LE | NOV Offshore | Production Increase | NULL | 2021-02-12 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0578604 | Restoration of Erha-38 | 2022-08-26 | L1 | On track | 637150 | 318575 | 0 | 0.63715 | 0.31857 | 0 | OP22 Above the Plan in LE; OP23 Above the Plan not in LE | NOV Offshore | Production Increase | NULL | NULL | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0578603 | Restoration of Erha-11 | 2023-09-29 | L3 | On hold | 1448160 | 700000 | 0 | 1.4482 | 0.7 | 0 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0274664 | Erha-51 well restoration | 2023-12-15 | L4 | On track | 318580 | 526290 | 312330 | 0.31858 | 0.52629 | 0.31233 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-1711336 | 2023 Erha TAM duration optimization | NULL | L5 | Completed | 150000 | 150000 | 1715000 | 0.15 | 0.15 | 1.715 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0210957 | Well Intervention: ER-20 | NULL | L5 | Completed | 222789.99 | 270000 | 187270 | 0.22279 | 0.27 | 0.18727 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE | NOV Offshore | Production Increase | NULL | 2021-02-12 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-1379333 | Water Injection Pump #7 maintenance & repair (In-plan) | 2023-06-30 | L3 | On track | 80000.1 | 80000.1 | 0 | 0.08 | 0.08 | 0 | OP22 In Plan | NOV Offshore | Production Increase | NULL | 2022-05-12 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-1379334 | Wells/Facility production optimization to enable well restoration | NULL | L5 | Completed | 4560000 | 9300000 | 15860810 | 4.56 | 9.3 | 15.8608 | OP22 Above the Plan not in LE | NOV Offshore | Production Increase | NULL | 2022-05-12 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-1379337 | Erha DSA gains (2023 recovery) | NULL | L5 | Completed | 14000000 | 14000000 | 26694805.94 | 14 | 14 | 26.6948 | OP22 Above the Plan not in LE | NOV Offshore | Others | NULL | 2022-05-12 | 2023-12-20
SNEPCo Delivery - Erha Production | Erha Production | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-2042374 | Restoration of Erha-29 well | 2023-10-27 | L4 | On track | 200000 | 3000000 | 4375740 | 0.2 | 3 | 4.3757 | OP22 Above the Plan not in LE | NULL | NULL | NULL | 2023-03-05 | 2023-12-20
SNEPCo Opex Efficiency - Abex | Abex | Aiboni Elohor J | Ismail Hamzat | Ejiro Emifoniye | I-1711266 | 2023 Abandonment Campaign Above-plan Savings | 2023-12-28 | L3 | On track | 4013109 | 12431665 | 11055814 | 4.0131 | 12.4317 | 11.0558 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Abex | Abex | Aiboni Elohor J | Ismail Hamzat | Ejiro Emifoniye | I-1711259 | 2023 Abandonment Campaign In-plan Savings | 2023-12-28 | L3 | On track | 3250294 | 3250294 | 2945164 | 3.2503 | 3.2503 | 2.9452 | OP22 In Plan | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Above Asset Costs | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Adeolu Adeniyi | I-0210145 | Optimization of ERP and Non-ERP Services - SNEPCO | 2023-04-30 | L3 | On track | 14850 | 14850 | 2541.49 | 0.01485 | 0.01485 | 0.0025415 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE | IT | Cost Saving - Structural / Recurring saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Above Asset Costs | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Oge Obianuka | I-2313595 | SNEPCo HR Opex Savings | NULL | L5 | Completed | 213428.02 | 213428.02 | 213428.02 | 0.21343 | 0.21343 | 0.21343 | OP22 Above the Plan not in LE | HR | Cost Saving - Non Structural / One-off saving | NULL | 2023-04-07 | 2023-12-20
SNEPCo Opex Efficiency - Above Asset Costs | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Ikemefuna Okereke | I-0051965 | Refund of payment made to LASG to SNID | 2024-08-31 | L2 | On track | 721000 | 0 | 0 | 0.721 | 0 | 0 | OP22 Above the Plan in LE; OP20 In Plan | Real Estate | Cost Saving - Non Structural / One-off saving | NULL | 2020-07-09 | 2023-12-20
SNEPCo Opex Efficiency - Above Asset Costs | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Okoroafor Uchenna E | I-2221871 | FORTE OIL - Money recovery | 2023-11-22 | L3 | On track | 8028.9 | 8028.9 | 0 | 0.0080289 | 0.0080289 | 0 | OP22 In Plan | Production Assets | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Above Asset Costs | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Jobson Gwatana | I-0899885 | SNEPCO ITF Cost Recovery | 2022-09-30 | L2 | On track | 52647.98 | 0 | 0 | 0.052648 | 0 | 0 | OP21 Above the Plan not in LE; OP22 Above the Plan in LE | HR | Cost Saving - Non Structural / One-off saving | NULL | 2022-02-09 | 2023-12-20
SNEPCo Opex Efficiency - Above Asset Costs | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Olamide Oladipupo | I-0259738 | Optimization of GIT Global Charges (SNEPCO) | 2022-05-27 | L1 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE | IT | Cost Saving - Structural / Recurring saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Above Asset Costs | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Bob-Manuel Isoboye N | I-1449253 | 2023 Optimization of CBCM Consumption - Snepco | NULL | L0 | On track | 6325 | 0 | 0 | 0.006325 | 0 | 0 | OP22 In Plan | IT | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Franklin Okafor | I-1866194 | DUSTLESS BLASTING TECHNOLOGY FOR IMPROVED FABRIC MAINTENANCE ACTIVITIES | 2024-02-29 | L3 | On track | 13612.5 | 13612.5 | 0 | 0.013612 | 0.013612 | 0 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Olakemi Aluko | I-0211219 | MEPSS for SNEPCo? Ops and maintenance support | 2024-01-31 | L3 | On track | 165000 | 110000 | 0 | 0.165 | 0.11 | 0 | OP22 Above the Plan in LE; OP23 Above the Plan in LE | Production Assets | Cost Saving - Structural / Recurring saving | PLM | 2021-06-12 | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Agala Belema F | I-1274684 | Deliver flare stretch of 1.0mmscfd against OP22 target of 3.4mmscfd | NULL | L5 | Completed | 240897.25 | 240897.25 | 150562.5 | 0.2409 | 0.2409 | 0.15056 | OP22 Above the Plan not in LE | NULL | NULL | Energy transition; GHG reduction | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Akinyemi Oluwaseun A | I-1274693 | Localization of the 13% global alliance discount on all Solar EFA rates | NULL | L5 | Completed | 65787.86 | 65787.86 | 65787.86 | 0.065788 | 0.065788 | 0.065788 | OP22 In Plan | Production Assets | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Chiejina Leo C | I-2375887 | Methanol Delivery Cost Reduction Bundling with Chevron (OPTS-ICE) | NULL | L5 | Completed | 222732 | 222732 | 222732.35 | 0.22273 | 0.22273 | 0.22273 | OP22 In Plan | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Jude Igurube | I-0057838 | Reduce / Eliminate Demurrage by Optimizing Key Offtake Activities | 2024-01-31 | L4 | On track | 0 | 0 | 816394.7 | 0 | 0 | 0.81639 | OP22 Above the Plan in LE | Production Assets | Others | #AIP | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Akinyemi Oluwaseun A | I-2313783 | Localization of 13% global alliance discount on all Siemens EFA rates | 2024-01-31 | L4 | On track | 0.24 | 0.24 | 19387.5 | 2.4e-07 | 2.4e-07 | 0.019387 | OP22 In Plan | NULL | NULL | NULL | 2023-06-07 | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Akinyemi Oluwaseun A | I-1609791 | Sales of disused FGC Solar turbine parts to HHOG | 2024-01-31 | L4 | On track | 1419.72 | 1419.72 | 1419.72 | 0.0014197 | 0.0014197 | 0.0014197 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Kelechi Onukagha | I-1983544 | Direct Fuel Delivery to SNEPCO Offshore Vessels (STS & stocking)) | 2024-01-31 | L4 | On track | 1407450 | 1407450 | 1078269.35 | 1.4075 | 1.4075 | 1.0783 | OP22 In Plan | Logistics | Cost Saving - Structural / Recurring saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Udoba Nnamdi | I-1983561 | SUPPLY OF VARIOUS OEM- (FCA) (STINDUSTRIES, QUINTAS & OFFSPRING - SNEPCO | NULL | L5 | Completed | 3799.95 | 3799.95 | 3799.95 | 0.0037999 | 0.0037999 | 0.0037999 | OP22 Above the Plan in LE | CP | Cost Avoidance | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Akinyemi Oluwaseun A | I-0274396 | Service exchange of Gearbox for GT- Power Turbine | NULL | L5 | Completed | 9608.09 | 19216.18 | 9608.09 | 0.0096081 | 0.019216 | 0.0096081 | OP22 Above the Plan in LE | Production Assets | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Franklin Okafor | I-2926830 | Corrosion Advanced Risk Modelling (CARMA) | 2024-01-31 | L0 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan; OP23 In Plan | NULL | NULL | NULL | 2023-02-11 | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Franklin Okafor | I-2926702 | Air Deluge Testing (Dry Flo) | 2024-01-31 | L0 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan; OP23 In Plan | NULL | NULL | NULL | 2023-01-11 | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Odebeatu Chike U | I-2739282 | AoF: DATA & SYSTEMS: CONNECTIVITY AND MOBILE CAPABILITY (Connected Worker) | NULL | L0 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan; OP23 In Plan | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Odebeatu Chike U | I-2739280 | AoF: DATA & SYSTEMS: DATA CENTRIC & INSGHTS DRIVEN ORGANIZATION (Data Analytics) | NULL | L0 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan; OP23 In Plan | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Odebeatu Chike U | I-2739279 | AoF: DATA & SYSTEMS: VIRTUALIZED ASSET (Bonga Digital Twin ) . | NULL | L0 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan; OP23 In Plan | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Kelechi Onukagha | I-2101308 | Fuel Monitoring System on SNEPCO Marine Vessels - 2023 | 2023-06-30 | L1 | On hold | 0 | 0 | 0 | 0 | 0 | 0 | OP22 Above the Plan not in LE | Logistics | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Akinyemi Oluwaseun A | I-2375026 | Buy back of CCC's series 3+ anti surge controllers | NULL | L5 | Completed | 8250 | 8250 | 0 | 0.00825 | 0.00825 | 0 | OP22 Above the Plan not in LE | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Bonga Opex | Opex Efficiency | Aiboni Elohor J | Jonathan Amakiri R | Agala Belema F | I-0683696 | Use of 1 power turbine for FPSO start up post trip to save diesel | NULL | L5 | Completed | 41247.25 | 41247.25 | 68750 | 0.041247 | 0.041247 | 0.06875 | OP21 Above the Plan not in LE; OP22 Above the Plan in LE | Production Assets | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Onuoha-Isiodu Joy | I-1238967 | SNEPCO Material Re-use - 2023 | NULL | L5 | Completed | 68749.92 | 68749.92 | 27662.77 | 0.06875 | 0.06875 | 0.027663 | OP22 Above the Plan in LE | NULL | Cost Saving - Structural / Recurring saving | NULL | 2022-08-11 | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Oluleke Atanda | I-2539354 | SAP Access replacement with SCD -(SEPRA CONTRACT DETAIL)-NG02 | NULL | L5 | Completed | 2332.34 | 2332.34 | 2332.34 | 0.0023323 | 0.0023323 | 0.0023323 | OP22 In Plan; OP23 Above the Plan in LE | CP | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Felicia Enechi | I-1449268 | 2023 -Sale of SNEPCo Surplus Materials | 2023-09-30 | L3 | On track | 24750 | 2000 | 1417.01 | 0.02475 | 0.002 | 0.001417 | OP22 Above the Plan in LE | CP | Cost Saving - Structural / Recurring saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Felicia Enechi | I-1449270 | 2023-Sales of SNEPCo Scrap Materials | 2023-11-30 | L3 | On track | 12375 | 12375 | 16640.52 | 0.012375 | 0.012375 | 0.016641 | OP22 Above the Plan in LE | NULL | Cost Saving - Structural / Recurring saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Oluwakemi Patrick-Oko | I-1449588 | GCC Procurement Simplification-SNEPCO | 2023-11-29 | L1 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan | NULL | NULL | SC Ops | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Oluwakemi Patrick-Oko | I-1449585 | Project Marble 2023 : Improve procurement strategy from Delivered Duty-SNEPCO | 2023-11-30 | L1 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan | CP | Cost Saving - Structural / Recurring saving | SC Ops | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Oluwakemi Patrick-Oko | I-1449583 | Procurement Negotiated Savings on Material Purchases-SNEPCO | NULL | L1 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan | CP | Cost Saving - Structural / Recurring saving | SC Ops | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Akpokodje Peter | I-2344772 | Optimization (reduction) of 2023 Q3 FYLE for SNEPCo Supply Base | NULL | L5 | Completed | 80239.23 | 80239.23 | 80239.23 | 0.080239 | 0.080239 | 0.080239 | OP22 Above the Plan in LE | CP | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Okoroafor Uchenna E | I-0184484 | Capture the Deal/Reimbursable Misuse - SeaGold | 2022-09-30 | L1 | On hold | 0 | 0 | 0 | 0 | 0 | 0 | OP21 Above the Plan in LE; OP22 Above the Plan not in LE | CP | Cost Saving - Non Structural / One-off saving | Excellence | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Tola Rotimi | I-1804037 | SNEPCo Savings from Contract Compliance Review (CCR) | 2023-07-31 | L4 | On track | 556.88 | 556.88 | 556.88 | 0.00055688 | 0.00055688 | 0.00055688 | OP22 In Plan | CP | Cost Saving - Non Structural / One-off saving | Excellence | 2023-10-03 | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Oluwakemi Patrick-Oko | I-2926337 | SNEPCO Insurance 2023: Savings from negotiated rates | 2023-12-21 | L2 | On track | 276847.07 | 0 | 0 | 0.27685 | 0 | 0 | OP22 In Plan | CP | Cost Saving - Structural / Recurring saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Oluwakemi Patrick-Oko | I-3003351 | Cost avoidance on VFD car park lease renewal | NULL | L2 | On track | 685.56 | 0 | 0 | 0.00068556 | 0 | 0 | OP22 In Plan | CP | Cost Avoidance | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Oluwakemi Patrick-Oko | I-3003350 | Cost Avoidance on Facility Lease-Rebecca court | 2023-11-28 | L1 | On track | 7550.98 | 0 | 0 | 0.007551 | 0 | 0 | OP22 In Plan | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Oluwakemi Patrick-Oko | I-3003352 | Cost avoidance from negotiated rates for supply of flooring for Project Eagle | NULL | L2 | On track | 29148 | 0 | 0 | 0.029148 | 0 | 0 | OP22 In Plan | CP | Cost Avoidance | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - CP | Opex Efficiency | Okpoechi Chioma N | Oduwole Tunde T | Okoroafor Uchenna E | I-0164901 | Reimbursable Misuse - Gramen | 2022-09-30 | L1 | On hold | 0 | 0 | 0 | 0 | 0 | 0 | OP21 Above the Plan in LE; OP22 Above the Plan not in LE | CP | Cost Saving - Non Structural / One-off saving | Excellence | NULL | 2023-12-20
SNEPCo Opex Efficiency - Erha Opex | Opex Efficiency | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0608168 | Erha cargo pumps overhaul | 2023-11-24 | L4 | On track | 28000 | 150000 | 75000 | 0.028 | 0.15 | 0.075 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE | NOV Offshore | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Erha Opex | Opex Efficiency | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-0154673 | Restoration of multimedia filters and replacement of skid instrumentation | 2023-10-27 | L3 | On hold | 171498.81 | 171498.81 | 0 | 0.1715 | 0.1715 | 0 | OP21 Above the Plan not in LE; OP22 Above the Plan not in LE | NOV Offshore | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Erha Opex | Opex Efficiency | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-1239082 | 2023 Erha Employee Cost Optimization | NULL | L5 | Completed | 85744.41 | 85744.41 | 147000 | 0.085744 | 0.085744 | 0.147 | OP22 In Plan | NOV Offshore | Cost Saving - Non Structural / One-off saving | NULL | 2022-09-11 | 2023-12-20
SNEPCo Opex Efficiency - Erha Opex | Opex Efficiency | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-1379344 | Process cooling medium pumps overhaul optimization (in-plan) | 2023-08-31 | L3 | On hold | 24494.4 | 24494.4 | 0 | 0.024494 | 0.024494 | 0 | OP22 In Plan | NOV Offshore | Cost Saving - Non Structural / One-off saving | NULL | 2022-05-12 | 2023-12-20
SNEPCo Opex Efficiency - Erha Opex | Opex Efficiency | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-1379342 | Subsea control module refurbishment optimization (in-plan) | 2023-11-30 | L4 | On track | 24494.4 | 160000 | 142010 | 0.024494 | 0.16 | 0.14201 | OP22 In Plan | NOV Offshore | Cost Saving - Non Structural / One-off saving | NULL | 2022-05-12 | 2023-12-20
SNEPCo Opex Efficiency - Erha Opex | Opex Efficiency | Aiboni Elohor J | Asaolu Ibiyemi F | Elliot Ibie | I-1379343 | HPU pump replacement optimization (in-plan) | NULL | L5 | Completed | 24494.4 | 24494.4 | 61250 | 0.024494 | 0.024494 | 0.06125 | OP22 In Plan | NOV Offshore | Cost Saving - Non Structural / One-off saving | NULL | 2022-05-12 | 2023-12-20
SNEPCo Opex Efficiency - Feasex | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Olaniyi Ilesanmi | I-0211012 | BMLE ? 4D Modelling | 2022-10-17 | L2 | On track | 0 | 0 | 0 | 0 | 0 | 0 | OP22 In Plan | Deep Water Projects | Cost Saving - Non Structural / One-off saving | NULL | 2021-03-12 | 2023-12-20
SNEPCo Opex Efficiency - Feasex | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Olaniyi Ilesanmi | I-2191110 | IT Infrastructure Synergy and Savings | NULL | L5 | Completed | 9762.5 | 9762.5 | 9762.5 | 0.0097625 | 0.0097625 | 0.0097625 | OP22 In Plan | NULL | NULL | NULL | 2023-05-06 | 2023-12-20
SNEPCo Opex Efficiency - Feasex | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Olaniyi Ilesanmi | I-2191106 | Interface Management Tool Change | NULL | L5 | Completed | 8250 | 8250 | 8250 | 0.00825 | 0.00825 | 0.00825 | OP22 In Plan | NULL | NULL | NULL | 2023-05-06 | 2023-12-20
SNEPCo Opex Efficiency - Feasex | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Olaniyi Ilesanmi | I-1449263 | BN Bid Evaluation Delivery Model Optimization | NULL | L3 | On track | 96250 | 96250 | 242854.5 | 0.09625 | 0.09625 | 0.24285 | OP22 In Plan | NULL | NULL | NULL | NULL | 2023-12-20
SNEPCo Opex Efficiency - Feasex | Opex Efficiency | Aiboni Elohor J | Oduwole Tunde T | Lateef Muritala | I-2573071 | Bosi Development Planning cost reduction | NULL | L5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | OP22 Above the Plan not in LE | Development | Cost Saving - Non Structural / One-off saving | NULL | NULL | 2023-12-20