## Sheet1
SN | Description | Duration (days) | Action Party | Target date | FEB | [19 empty] | MARCH | [30 empty] | APRIL
[5 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | Line/ AM approval | 5 | Bob-Manuel, I | 13/2/2018 | bar: FEB 9 to FEB 13
2 | Submission for CC approval | 5 | Akpala, Ude | 13/2/2018 | bar: FEB 9 to FEB 13
3 | Engage NIMASA to provide clarity on issuance Statement of Compliance | 5 | Orji, Emenike | 13/2/2018 | bar: FEB 9 to FEB 13
4 | Raise required ABC documentation/ approvals | 14 | Orji, Emenike | 27/2/2018 | bar: FEB 14 to FEB 27
4.1 | Confirmed GI screening and IDD cleared |  | Orji, Emenike | 21/2/2018
4.2 | Pre-engage Legal Counsel |  | Bob-Manuel, I | 22/2/2018
4.3 | Complete GI engagement process |  | Orji, Emenike | 27/2/2018
5 | Hold awareness sessions on ISPS code with relevant stake holders at site (both crews) | 1 ea | Orji, Emenike | TBA | bar: FEB 28; MARCH 7
6 | 50% upfront payment | 5 | Akpala, Ude | 2018-05-03 | bar: FEB 28 to MARCH 5
7 | ISPS certification exercise | 40 | RSO/ BNY PFSO/ NIMASA | 2018-09-04 | bar: MARCH 6 to APRIL 14
7.1 | On the Scene Survey | 3
7.2 | Preparation of draft PFSA report | 8
7.3 | Submission and review of PFSA by NIMASA | 7
7.4 | Feedback, finalization and adoption of PFSA report | 3
7.5 | Preparation and submission of draft PFSP to NIMASA | 6
7.6 | Submission and review of PFSP by NIMASA | 6
7.7 | Feedback, finalization and adoption of PFSP report | 2
7.8 | Production and submission of final copies of PFSA and PFSP for endorsement | 2
7.9 | Processing and issuing of Approval letter for Port Facility | 3
8 | Verification Inspection Exercise (VIE) | 7 | RSO/ NIMASA | 16/4/2018 | bar: APRIL 15 to APRIL 21
9 | Issuance of Statement of compliance (SoC) | 7 | RSO/ NIMASA | 23/4/2018 | bar: APRIL 22 to APRIL 28
10 | 50% balance payment | 7 | Akpala, Ude | 23/4/2018 | bar: APRIL 22 to APRIL 28
Completed
Ongoing