## Work Schedule BOGT
BOGT ELECTRICAL SYSTEM EXECUTION PLAN
| ACTIVITY DESCRIPTION | N0 OF PROTECTION RELAYS. | N0 OF FEEDERS |  | EXECUTION PARTY: MTCE EXECUTION COMM. TEAM. | [43 empty] | REMARKS / ACTIONS
|  |  |  | PERCENTAGE(%) COMPLETION |  | SEPTEMBER |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUAY |  |  |  | FEBUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPT |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DEC |  |  |  | REMARKS / ACTIONS
[6 empty] | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
1 | FEEDER AS-BUILT DRAWING VERIFICATION
| SS-200 SUBSTATION 11KV |  |  | 100% | MTCE EXECUTION COMM. TEAM. | [43 empty] | COMPLETED (All drawings reviewed and verified) | bar: SEPTEMBER WK 2 to SEPTEMBER WK 3
| SS-300 SUBSTATION 6.6 KV & 11KV |  |  | 100% | [44 empty] | COMPLETED ( (All drawings reviewed and verified) | [20 empty] | COMPLETED (All drawings reviewed and verified) | bar: SEPTEMBER WK 3 to SEPTEMBER WK 4
| PSS-1 SUBSTATION 11KV |  |  | 100% | [44 empty] | COMPLETED ( (All drawings reviewed and verified) | [20 empty] | COMPLETED ( (All drawings reviewed and verified) | bar: OCTOBER WK 1 to OCTOBER WK 2
| SS-100 SUBSTATION 11KV |  |  |  |  | OCTOBER WK 4: TIME OFF | ONGOING | [20 empty] | COMPLETED ( (All drawings reviewed and verified)
| PSS-2 SUBSTATION 33KV & 6.6KV | [68 empty] | ONGOING | bar: NOVEMBER WK 2 to NOVEMBER WK 3
2 | PROTECTION RELAY INJECTION TEST AND SWGR PREVENTIVE MAINTENANCE.
| SS-200 SUBSTATION 11KV | 25 | 20 |  | MTCE EXECUTION COMM. TEAM. | NOVEMBER WK 4: TIME OFF
| SS-300 SUBSTATION 6.6KV & 11KV | 54 | 44 |  |  | FEBUARY WK 3: SEA EAGLE INTERVENTION; APRIL WK 1: SS300
| PSS-1 SUBSTATION 11KV | 37 | 20 |  |  | MAY WK 1: PSS1
| SS-100 SUBSTATION 11kV | 21 | 18 |  |  | JUNE WK 1: SS100
| PSS-2 SUBSTATION 33KV & 6.6KV | 57 | 37 |  |  | JULY WK 1: PSS2 |  | TIME OFF
| TOTAL | 194 | 139
3 | DRAWING RED LINE MARKUP / ISSUE & CONCERN EXECUTION. | [47 empty] | To be finalized with Asset holder team.
To be finalized with Asset holder team.
5 | RESOLVE BOOSTER PUMP REMOTE OPERATION ISSUE IN SS-100.
6 | GCP - 210 CONTROL PANEL HMI REPLAEMENT AND FUNCTION CHECKS.
7 | RESOLVE CLINK SYCHRONIZATION ERROR.
8 | RESOLVE PSS-1 UPS RECTIFIER BC-00F07 COMMON AND CURRENT ALARM FAULT
CLOSED
ONGOING
TIME OFF
PLAN
ACTIVITY LEGEND