## Work Plan BOGT Black Start
BOGT BLACK START AVAILABILITY IMPROVEMENT
| ACTIVITY DESCRIPTION |  | FEBUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE
|  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
1 | Repair and commission Black Start generator GD110 - PSS-2
| Procure required spares | MTCE EXECUTION COMM. TEAM./C & P | bar: FEBUARY WK 1 to FEBUARY WK 3
Consult OEM - Mantrac, Enercon | bar: FEBUARY WK 1 to MARCH WK 2
| Follow through readiness of Electrical specialist maintenance contract | [21 empty] | Ongoing | bar: FEBUARY WK 1 to MARCH WK 3
Raise and Issue one-off PO (Mantrac) | bar: MARCH WK 1 to MARCH WK 2
Mobilise Mantrac field engineer and clear unit alarms | bar: MARCH WK 3 to APRIL WK 1
Mobilise Enercon field engineer | bar: APRIL WK 2
Repair and commision unit | bar: APRIL WK 3 to MAY WK 1
2 | Replacement of GD-210 (CCB) Control panel display screen
| Replace screen with old unit of GD110 as temporary measure | C&P | [20 empty] | Temporary measure | bar: FEBUARY WK 1
| Procure new HMI for GD210 | [21 empty] | PO 4510386084/30 EDD in past - 30.11.2017 | bar: FEBUARY WK 1 to MARCH WK 1
Replace screen with newly procured unit | bar: MARCH WK 1 to MARCH WK 2
3 | Repair and commission Emergency Diesel generator GD220 - FGP
| Troubleshooting and OEM correspondence | OEM/C&P | bar: FEBUARY WK 4
| Procurement of required spares for repair/upgrade | [21 empty] | PO 4510386084/30 EDD in past - 30.11.2017 | bar: FEBUARY WK 1 to MAY WK 3
| Follow through readiness of Electrical specialist maintenance contract | [21 empty] | Ongoing | bar: FEBUARY WK 1 to MARCH WK 3
Repair and commision units | bar: MAY WK 4 to JUNE WK 3
4 | Procurement of Insurance spares for all BOGT EDG
| Develop and optimise critical spares listing for diesel engines/alternators | OEM/C&P | bar: FEBUARY WK 2 to MARCH WK 1
Request quotes and carry out SAP coding | bar: FEBUARY WK 3 to MARCH WK 1
Create PR/POs | bar: MARCH WK 1 to MARCH WK 2
Take deliveries | bar: MARCH WK 3 to JUNE WK 4
5 | Procurmeent of Insurance spares for EDG Enercon Control Panels
| Develop and optimise critical spares listing for Enercon control panels | OEM/C&P | bar: FEBUARY WK 1 to FEBUARY WK 4
Request quotes and carry out SAP coding | bar: MARCH WK 1
Create PR/POs | bar: MARCH WK 2 to MARCH WK 3
Take deliveries | bar: MARCH WK 4 to JUNE WK 4
9 | Competence development
| Compile training needs and identify means | L&D | bar: FEBUARY WK 3 to MARCH WK 1
Training of personnel on the diesel engine and controls systems
CLOSED
ONGOING
NOT STARTED