## Sheet1
TANKPAC INSPECTION PLAN/UPDATE
Tank 2 |  | Jan'18 | [17 empty] | Feb'18 | [20 empty] | Mar'18
Inspections |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Feb. 22nd to Mar. 21st | Mar. 22nd
Acoustic Emmission | Target | bar: Jan'18 31 to Feb'18 1
Implimentation | bar: Jan'18 31 to Feb'18 1
Annular Plate LRUT | Target | bar: Feb'18 7 to Feb'18 8
Implimentation
Shell Plate Thickness Survey | Target | bar: Feb'18 15 to Feb'18 16
Implimentation
Shell Nozzles Thickness Survey | Target | bar: Jan'18 14 to Jan'18 30
Implimentation | bar: Jan'18 14 to Jan'18 30
Roof Plates Thickness Survey | Target | bar: Jan'18 14 to Jan'18 30
Implimentation | bar: Jan'18 14 to Jan'18 30
Data Review Report | Target
Implimentation
Report Submission to DPR | Target
Implimentation
Tank 18 |  | Jan'18 14: Jan'18; Feb'18 1: Feb'18
Inspections |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Feb. 22nd to Mar. 21st | Mar. 22nd
Acoustic Emmission | Target | bar: Feb'18 2 to Feb'18 3
Implimentation | bar: Feb'18 2 to Feb'18 4
Annular Plate LRUT | Target | bar: Feb'18 9 to Feb'18 10
Implimentation
Shell Plate Thickness Survey | Target | bar: Feb'18 17 to Feb'18 18
Implimentation
Shell Nozzles Thickness Survey | Target | bar: Jan'18 14 to Jan'18 30
Implimentation | bar: Jan'18 14 to Jan'18 30
Roof Plates Thickness Survey | Target | bar: Jan'18 14 to Jan'18 30
Implimentation | bar: Jan'18 14 to Jan'18 30
Data Review Report | Target
Implimentation
Report Submission to DPR | Target
Implimentation
Tank 21 |  | Jan'18 14: Jan'18; Feb'18 1: Feb'18
Inspections |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Feb. 22nd to Mar. 21st | Mar. 22nd
Acoustic Emmission | Target | bar: Feb'18 4 to Feb'18 5
Implimentation
Annular Plate LRUT | Target | bar: Feb'18 11 to Feb'18 12; Feb'18 19 to Feb'18 20
Implimentation
Shell Plate Thickness Survey | Target
Implimentation
Shell Nozzles Thickness Survey | Target | bar: Jan'18 14 to Jan'18 30
Implimentation | bar: Jan'18 14 to Jan'18 30
Roof Plates Thickness Survey | Target | bar: Jan'18 14 to Jan'18 30
Implimentation | bar: Jan'18 14 to Jan'18 30
Data Review Report | Target
Implimentation
Report Submission to DPR | Target
Implimentation
Tank 22 |  | Jan'18 14: Jan'18; Feb'18 1: Feb'18
Inspections |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Feb. 22nd to Mar. 21st | Mar. 22nd
Acoustic Emmission | Target | bar: Feb'18 6 to Feb'18 7
Implimentation
Annular Plate LRUT | Target | bar: Feb'18 13 to Feb'18 14
Implimentation | bar: Jan'18 31
Shell Plate Thickness Survey | Target | bar: Feb'18 20 to Feb'18 21
Implimentation
Shell Nozzles Thickness Survey | Target | bar: Jan'18 14 to Jan'18 30
Implimentation | bar: Jan'18 14 to Jan'18 30
Roof Plates Thickness Survey | Target | bar: Jan'18 14 to Jan'18 30
Implimentation | bar: Jan'18 14 to Jan'18 30
Data Review Report | Target
Implimentation
Report Submission to DPR | Target
Implimentation