## Slide 1
The Gbaran FLB, CPF, Flow stations and remote locations perimeter and process area lighting has significant amount of non-functional light bulbs and recent 2023 inspection indicates the following critical light bulbs in these areas are not functional: FLB and CPF about -43% , Flow stations -80% and remote locations -50%. These sub-optimal illumination status presents a huge gap to optimal security management and portends a credible threat to the safeguarding of both personnel and asset in the areas.
This initiative is aimed at identifying the causal issues behind this sub-optimal availability status, in addition to developing a credible plan to restore top quartile perimeter and process area lighting availability and sustain the desired availability performance overtime.
Business Case
1
2
Verify illumination status of all lamps in area (Validate 2023 inspection outcome)
Identify causal factors behind significant failure rate.
Develop roadmap to restore 100% functionality.
Drive execution of required intervention
Introduce measures to sustain performance.
Add the illumination status in UTL for tracking.
Project Scope
3
Improve FLB, CPF, Flow station & Remote locations illumination systems availability (50%  +/- 95%)
Prevent security incidents and support Goal Zero aspiration.
Increase probability of mitigating potential unauthorized access to subject areas
Potential Benefit/Impact
L1: 28th Feb 2024
L2:30th Apr 2024
L4: 30th Sept 2024
L3: 30th Jun 2024
L5: 30th Nov 2024
Project Sponsor: Adeleke Oluseyi.
Project Lead: Emetubelem Muolee.
Team members: Kpoudosu David, Richard Ba-bari, Hilary Opukiri, Ajie Elemchukwu, Joel Justus, Destiny Otunumeruke, Monday John.
Implementation
Availability of funding for materials (replacement lamps, etc) and services
Availability of execution team. (NGRE; Mtce Exec; C &P).
Timely delivery of required spares & execution resources
Critical Success Factors
4
5
MTO ID: 1-3600666
Score: N/A
Replace spent lamps to improve illumination to 95% and prevent security incidents in Gbu/kolc facilities by September 2024.