## Slide 1: Commission Well Test Systems at Tunu Node To Accelerate Ramp-Up of Production and Support Start-up of AG Facilities By September 2019
Valuation of impact overview
Risks, challenges and interdependencies
  Risks
  Challenges
  Interdepen-dencies
  Threat to Production Allowable or sanctions by DPR
  Non-Financial impact
  Production impact
  GHG Objectives
  Achieve CO2 abatement of circa 300KTCO2/yr…
  Full Commissioning of the Well Test System will result in the following production gains:
  Production volumes of 5kbopd from bean ups. Sale of gas (circa 30 MMscfd) in the DOMGAS market.
  Contractual/financial exposure for the SSAGS Project.
Description of the initiative
  Situation
  Initiative description
  Tunu, Opukushi, Benisede and Ogbotobo
  Scope
  Expedite Vendor (SAIPEM) availability to enable adequate resources for the full commissioning activities.
    Complete the commissioning/verification of the well testing system and logics at the Tunu Node flow station.
    Implement well test plan and bean up the wells with potential
  In Tunu Node, Lack of Well Testing Is Hampering Bean-Up Opportunities Which Impacts Ramp-Up of Production.
    Tunu Node, having been shut-in for Pipeline Outage, was re-opened on the smallest beans.
    While facilities were shut-in, the SSAGS brownfield upgrades were completed.
    However, the commissioning/fine-tuning/configuration of the new well-test metering system and logic has not been completed. Therefore, well-test is not happening. Corporate metering team has now been involved for support.
    Testing of the opened-up wells need to be done to enable bean-up/ramp-up that does not damage the reservoir.
    Current gas production is inadequate for startup of the AG facilities
  Ongoing Efforts Have Resulted In Acceptable Liquid Metering for Tunu Flowstation. Hence Limited Well Testing Has Commenced.
    Bean-Up has commenced in Tunu field based on tested liquid rates only.
    Bean-up has also started in the other fields in the node based on observing BS&W results. About 3Kbopd has already been gained in the past two days.
Key stakeholders
  Workstream lead: Godwin
  Initiative lead: Emmanuel
  Business focal point: Mesh Maichibi
  Business: Simon
  Finance lead: Isaac Audu-Usman
  Other key stakeholders : Chris Ubuane
INITIATIVE CHARTER – WRFM
Have materials been secured?
Are there people contracted to perform the service?
Is the area accessible for the job?
Is there a clear business case for funding?
Is the initiative in plan?
Source: Production Clinic Workshop West Asset, Team analysis