## DFTP Overall -OP22
DFTP OP-22 MILESTONES | [5 empty] | LEADING INDICATORS
S/No | Project Name | Milestones /Portfolio Details | Team Target | OP-22/P50 | Remarks/Premise | C & P | ENGRG | QA/QC | OR&A | HSE | LOGISTICS | INTERFACE | SP | PS | Assumption
TERMINALS
1 | BOGT Tank Rehab | Complete Rehabilitation of Tanks 20 | 2023-06-24 | 2023-08-21 | 1. Secure Approval from GM to RTS by end Jan'23 2. Re-Mob personnel to site - end Feb'23 3. Complete Hydrotest by Apr'23 4. Complete Calibration by Jun'23 |  |  |  |  | Re-Mob personnel to site - end Feb'22 Close-out specific action from investigations. | Re-Mob personnel to site - end Feb'23 | 1. Pay Statutory Calibaration fee by May'23 2. Inform DPR to participate in Calibration exercise by Jun'23 | Sustain CTS from Feb '23 - Jun'23 | 1. Update Schedule & PMS by mid Feb'23
2 | BOGT Facilities | Complete Installation of Produced water Meter | 2023-07-28 | 2023-08-28 | 1. Pay NMDPRA vFAT fees by Feb'23 2. Complete outstanding Contracting by Mar'23 3. Meter Delivery by Apr'23 4. Mechanical completion by May'23 5. Commissioning and integration Jul'23 | 1.Complete Time extention on Contract by Feb'23. | [5 empty] | 1. Pay NMDPRA vFAT fees by Feb'23 |  | 1. Provide CE for ACV Increase by Mar'23 | 2. Issue P.O by Mar'23
3 | FOT Tank Rehab | Progress T101 rehab to 50% | 2023-10-23 | 2023-12-23 | 1. Issue P.O by Jan'23. 2. Mobilize by Feb'23. 3. Complete Condition Survey by Mar'23 4. Complete Demolition works (Floor plates etc) by May'23 5. Deliver LLI (plates) by May'23 6. Complete Tank Floor Installation by Aug'23. 7. Complete 50% Roof installation by Oct'23 |  |  |  |  | 1. Contractor is red banded- Gaps to be closed by Feb'23 |  |  | Obtain CTS by May' 23 Sustain CTS thru Dec '23 | 1. Issue P.O by Jan'23.
4 | FOT Tank Rehab | Complete Robotic Cleaning of Tanks 207 | 2023-09-28 | 2023-11-28 | 1. Mob Robotic equip & key personnel to site -Jan'23 2. Set up Robotic equipment Mar'23. 3. Complete De-oiling by Mar'23 4. Clean & treat Sludge by robotic cleaning by Jul'23. 5. Transfer of waste to approved NMDPRA dumpsite by Aug '23 6. Final tank washing for man entry & inspection by Sep '23 7. 4 MONTHS execution duration end-to-end | 1. Obtain CC approval by Feb'23. | [6 empty] | Secure CTS by Feb' 23 Sustain CTS thru Jul '23 | 1. Issue CE by Feb'23
5 | FOT Facility | Complete Auto Sampler Installation | 2023-07-29 | 2023-09-30 | 1. Complete Contracting and secure budget offset by Mar'23 2. Complete systen flusing and installation of advance tie-in by Mar'23. 3. Conclude FAT by end Mar'23 4. Deliver Auto Sampler to site by May'23 5. Complete installation, commission and integration by Jul'23. 6. Demobilize from site by Jul'23 | 1. Obtain MCB Approval by Mar'23. 2. Conclude Negotiations by Mar"23.
6 | FSPM 2 | Complete FSPM 2 Installation (ACOE) | 2023-04-30 | 2023-05-30 | 1. Complete Mooring activity installation by Feb'23. 2. Complete DP Vessel mob by Feb'23 3. Complete cross over tools, floating hose & spectacle blind installation by Mar'23. 4. Complete Commissioning in Apr'23 | [7 empty] | Secure CTS by Mar' 23 & sustain CTS by March '23 | 1. Complete CE for standby claims by Feb'23. 2. Finalize schedule with contractors input by Feb'23
7 | SPM | Complete 30% Fabrication of New SPM Buoys | 2023-11-29 | 2023-12-30 | 1. Award Contract by May'23 2. Issue P.O by May'23. 3. Conclude ELDL by May'23 4. Place order for 2 new buoys by May'23 5. Commence fabrication of new buoys by Aug'23 6. Complete fabrication 1 no. SPM Buoy body by Dec'23 | [7 empty] | Obtain and secure CTS by June '23 | 1.Conclude CE by Mar'23
8 | SPM | Complete Repair of Buoy 12481 | 2023-03-30 | 2023-04-29 | 1. Issue PO for repair of Buoy by Feb'23 2. Mob for Equip & personnel to Fab yard by Feb'23 3. Complete Bouy 12481 repair and Function testing by Mar'23. | [7 empty] | Issue PO for repair of Buoy by Feb'23
9 | SSEP | Deliver LLIs to Site - BOGT, FOT, Bonga, EA | 2023-07-31 | 2023-08-31 | 1. Issued P.O in Sep '22. 2. Deliver LLI in Jul '23
10 | SSEP | Mechanical completion of BOGT 3 - Towers and PIDS SSEP | 2023-09-30 | 2023-10-31 | 1. Contractor already mobilized to site. 2. Complete construction of foundations in Jun '23. 3. Complete tower erection in Jul '23. 4. Complete fencing in Aug '23
11 | SSEP | Mech Completion FOT SSEP - P2 (Perimeter Video Surveillance System - CCTV) | 2023-10-31 | 2023-11-30 | 1. Complete Installation of Camera poles and earthing in May '23. 2. Complete fibre optic and power cabling in Jul '23. 3. Complete installation of cameras in Sep '23.
12 | SSEP | Mech Completion FOT SSEP - P2 (Access Control System) -Radar Action | 2023-12-31 | 2023-12-31 | 1. Commence installation works in Jun '23. 2. Complete installation works in Nov '23
DOMGAS
1 | Otumara CEIP | Complete Poles Installation for Otumara CPF to Deghele Section(13km) | 2023-03-21 | 2023-04-21 | 1. Erection of Concrete poles erection ; 239 of 260 = 92% . 2. Contractor RTS by Feb'23 3. Complete Balance pole erection by Mar'23 |  |  | Review Contractor proceedure for Repairs by Feb'23 |  |  |  |  | Sustain CTS thru Feb' 22
2 | Otumara CEIP | Award of Section 2 Contract | 2023-10-30 | 2023-11-30 | 1. Pre-Engage NUIMs to align on ITT package by Mar-23 2. IDD Clear the Vendor by Mar-23 3. Issue ITT by Mar-23 4. Receive Bids by Mar-23 5. Evaluate the bids with NUIMS by Apr-23 '6. Award Recommendation (Part B) by May-23 7. Transmit to NUIMs and Secure NUIMs approval by Jul-23 8. Operationalize Contract by Aug-23 9. Sign off Agreement by Aug-23
3 | SSAGS CEIP | Re-mob 1st Transmission Line Contractor for site construction. | 2023-04-29 | 2023-05-29 | 1. Secure CRB & NUIMS approval by Jan'23 2. Conclude 1st VP Negotiation in Feb'23. (Actual: 31-Jan'23) 3. Mob Contractor to site by Mar'23. | Conclude 1st VP Negotiation in Feb'23. |  |  |  | Conclude Premob by Mar'23 | Mob Contractor to site by Mar'23. | Secure CRB & NUIMS approval by Jan'23 | -Revalidate CTS by Feb' 23 -Sustain CTS thru Mar '22 | Load E-LDL values & provide budget for 2023 by Feb'23
4 | SSAGS CEIP | Achieve 50% Foundation works at Benesede | 2023-08-30 | 2023-11-28 | 1. Premised on VP Resolution by Mar'23. 2. Raise ELDL by Mar'23 3. RTS by Apr'23. 4. 380 foundations in Total : 160 foundations @ 2 Fdns/day based on offsite fab. | Premised on VP Resolution by Mar'23. |  |  |  | Conclude Premob by Mar'24 | Mob Contractor to site by Apr'23. |  | -Revalidate CTS by Feb' 23 -Sustain CTS thru Nov '22
5 | SSAGS CEIP | Award 1st TDN Contract | 2023-05-28 | 2023-07-30 | 1. Secure NUIMS Approval by Feb'23. 2 Conclude PMO commercials by end Mar'23. 3. Award by May'23. | Conclude PMO commercials by end Mar'23. | [5 empty] | Secure NUIMS Approval by Feb'23. | Obtain SI&S, ABC Memo approval Mar' 22
6 | SSAGS 3A | Obtain EIA Approval | 2023-09-30 | 2023-11-20 | 1. EIA - In-house review of draft Report – completed 2. EIA - Printing and Submission of draft EIA report to DPR/FMEnv – Submitted 3. EIA - Public display in LGA/Receipt of comments provisional approval from - Panel Review and re-submit report – May'23 4. EIA - Final Approvals / Environmental Impact Assessment – Sep'23
7 | SSAGS 3B | Mob Survey Contractor | 2023-04-21 | 2023-05-21 | 1. Conclude Prelim Route Map & SoW by Jan'23. 2. Issue PO by Feb'23. 3. Obtain CTS by Feb'23 4. Complete Pre-Mob by Feb'23 5. Mob Houseboat to site by Mar'23 (Marine team) 6. Mob to Site by Mar'23. | [7 empty] | -Obtain CTS by Feb' 23 - Sustain CTS thu June '22 | Issue PO by Feb'23.
8 | SSAGS 3B | Complete FEED | 2023-09-30 | 2023-11-30 | 1. Site visit & CTR Concluded in Nov'22. 2. Kickoff in Jan'23 3. Complete Survey by Jun'23 4. Complete PEF Review by Feb'23. 5. Complete Process Saety Reviews by Apr'23 6. Complete Model Review by Apr'23 7. Complete BDEP by Jun'23 8. Benchmark with SSAGS 3A. (9 Months) |  | 1. Complete PEF Review by Feb'23. 2. Complete Process Saety Reviews by Apr'23 3. Complete Model Review by Apr'23 4. Complete BDEP by Jun'23 | [5 empty] | -Secure CTS by Feb' 23 -Sustain CTS thru Mar' 22 | 1. Conclude and Align Progress with FEED Team by Jan'23
9 | SSAGS | Tunu AGC 2 Exhaust Collector Repair | 2023-05-15 | 2023-05-30 | 1. Issue PO by Feb'23 2. Sourcing for Lifting tools & Accessories from Solar/other SPDC locs by Mar'23. 3. Mobilize LIFTING TOOLS & Equipment from Warri to TUNU by Mar'23 4. Mobilize Contractor/OEM(Solar) to Site late Apr'23. 5. Decouple engine from Skid & remove Exhaust Collector by Apr23 6. Repair exhaust collector - Welding by Apr'23. 7. Install repaired exhaust collector & couple Engine /Skid by May'23. 8. Demob A frame/Trolley Hoist & install Enclosure door on Compressor unit by May'23. 9. Pre-Start up Checks by May'23 10. Commission AGC Exhaust collector by May'23 | [8 empty] | Issue PO by Feb'23
10 | SSAGS | Procure, Install & Commission HVAC systems at Tunu Central Control Room | 2023-05-15 | 2023-05-30 | 1. Issue PO by Feb'23. 2. Secure CTS by Feb'23 3. Procure & Deliver to site HVAC spares by Mar'23 4. Mobilize Contractor to Site Mar'23 5. Complete work Execution Activities by Apr'23 6. Re- Commission re-vamped HVAC System by May'23 |  |  |  | 1. Functionality assurance by May'23 | Work Method statement & JHA Feb'23 | Support Vendor Mobilization by Feb'23 |  | 1.Secure CTS by Feb' 23 2.Sustain CTS thru Apr' 22 | Issue PO by Feb'23
FYIP
1 | SBFS | SBFS Booster Compressor - RFSU | 2023-02-28 | 2023-02-28 | 1. low Pressure surge gas volume (LPSGV) challenge to be resolved by Jan'23. 2. Re-mobilized Contractor to site by Jan'23. (Feb'23) 3. Fabrication & installation Spools by Feb'23. 4. Secure Shut down for LPSGV Modificaton by Feb'23 5. NEAC FSR's re-mobilized by Feb '23. (SPDC to commission) 6. Restart Booster compressor by Feb'23 LEC 4Apr'23 |  | 1. Complete MoC for LP Makeup gas line by Jan'23 | [6 empty] | Secure break-in for shutdown via CRET by Feb'23
2 | Yorkri Flow Station | YOKRI FS - RFSU | 2023-03-28 | 2023-03-28 | 1. MC for Critical subsystem completed (54/63) 2. TA's review of Draft UT report by Jan'23 3. Issue PO to INTECH by Jan'23. 4. Issue PO for 8'' IP by Jan'23. 5. Complete 8'' IP works (Gas lift line) by early Feb '23. LEC: Mar'23 6. Complete N2He leak test by Feb'23. LEC: Mar'23 7. Sign SOF by Apr'23. 8. Complete Phased RFSU by Mar'23. LEC: Apr'23 due to sectional replacement 16'' Pipeline. MoC required |  |  |  | 1. Complete outstanding TIV actions by Mar'23. 2. Complete 16-inch pipeline by Mar'23. 3. Close-out PSUA H-H items by Mar'23. 4. Close-out all SUOP Recommendations Mar'23 |  |  |  |  | 1. Issue PO to INTECH by Jan'23. 2. Issue PO for 8'' IP by Jan'23.
3 | Yorkri Flow Station | Achieve Yokri Flares down | 2023-05-28 | 2023-06-27 | 1. Resolve contract vehicle and Issue PO to Howden- Feb' 31 LEC 10th Apr 2. VISA and Travel Permit for Howden-Mid Feb'23 - LEC 24th Apr 3. Mobilize vendor for Screw Compressor PC&C- end Feb'23- LEC 1st May 4. Complete Piping, Mechanical, Electrical , Instrumentation pre Com-May’23 5. Complete Commissioning the Screw Gas Compressor-May'23 |  |  |  | 1. Complete Competency development hands-on training for Screw compr by Jun'23. |  | Re-mobilized Contractor to site by Jan'23. |  | -Secure CTS by Feb '23 -Sustain CTS thru April' 21
4 | Pipeline Leak Repair | 12" SBFS-NEFS AG PL leak repair -RFSU | 2023-02-28 | 2023-03-28 | 1. Complete Derogation Implementation Action ( Marker buoys positioning etc) by Jan'23. 2. Replace defective buoys by Jan'23 3. Complete PSUA sign-off (PUM) by Feb'23 before introducing H2C. LEC: Mar'23 |  |  | TA's review of Draft UT report by Jan'23 | 1. Sign SOF by mid Mar'23. before introducing Hydrocarbon. |  |  |  | Obtain and sustain CTS by Feb '21 | 1. Issue PO to INTECH by Jan'23. 2. Issue PO for 8'' IP by Jan'23. 3. Issue Cost Estimate for N2He leak test by Jan'23
5 | North Bank CPF | NB CPF - Commission & Start-up New AG compressor | 2023-02-27 | 2023-02-27 | 1. New AG compressor Vendor/OEM FSR's re-mobilized by Feb'23 2. New AG compressor completion works by Feb'23. 3 Start up AG Compressor by Feb'23 |  | 1. Complete engagement to the OEM on Seal Gas OPS by Feb'23 2. Provide Commissioning Support for SU of AG Compressor by Feb'23 | [5 empty] | -Secure CTS by Feb' 23 -Sustain CTS thru Apr '21
6 | 33kv Subsea Cable | 33KV Subsea Cable Link-1 - RFSU | 2023-03-30 | 2023-04-29 | 1. Onshore Scope: Complete excavation , cable lay & backfilling of FOT by Feb'23. 2. Onshore Scope: Complete excavation , cable lay & backfilling of Obotobo by Feb'23. 3. Offshore Scope: Complete mattress inst. By Jan'23. 4. Complete Cable lay by Feb'23.(Actual-10th Feb'23) 5. Termination & Commissioning by Mar'23 LEC: Mar'23 | [7 empty] | Sustain CTS by Feb '21
7 | FOT Fuel Line | FOT Fuel Gas Sustainability - RFSU | 2023-06-30 | 2023-08-29 | 1. Complete Premob offsh pipelay barge & supporting vessels by Jan'23. 2. Complete Installion Engineering by Jan'23. Achieved - Feb'23 3. Secure Marine Warranty survey by Jan'23. Achieved - Feb'23 4. Mob to Site Pipelay by Jan'23. Achieved - Feb'23 5. Complete offshore pipelay (20 jnt/day) by Mar'23. LEC: May'23 6. Deliver End Fac LLI by Mar '23. LEC: Apr'23 7. Mob for End Facility by Feb'23. LEC: Apr'23 8. Complete End Facility (FOT)by Apr'23. LEC: Jun'23 9.Complete End Facility (CPF) by May'23. LEC: Jul'23 10. Complete Integration of End facilities/pipelines etc by Jun'23. LEC: Jul'23 11. Secure TIV /SOF/ commisioning by Jun'23. LEC: Jul'23 |  | 1. Provide construction support by Jun'23 |  | 1.Complete CMMS by Apr'23. LEC: Jun'23 2 Complete TIV May'23 .LEC: Jun'23 3. Complete PSUA by Jun'23.LEC: Jul'23 4. Secure SOF by Jun'23. LEC: Jul'23 |  |  |  |  | 1. Review and align contractor schedule by Feb'23
8 | Pipeline Dent Repair | 12"/24'' Complete Dent Repair | 2023-06-30 | 2023-09-28 | 1. All POs for IP tools issued to DSV by Jan'23. 2. Secure CE for Dent Repair by Jan'23. 3. Mob for 12'' repair premised on compltn of FOT Offshore pipelay completing retrofit of Rabidaf007 by May'23 4. Delivery of Clamps for 24'' by Apr'23. LEC: May'23 5. Complete 12'' repair by May '23. LEC:Aug '23 6. Complete 24'' Repair by Jun'23. LEC: Aug'23 |  |  | QMS Audit of Fenog by Feb'22 |  | Sign HSE Certificate By Jan'23. LEC: May'23 HSE-MS of Fenog by Feb'22. LEC: May'23 | Complete Marine Assurance by Jan'23. LEC: May'23 |  | -Sustain CTS thru Mar '21. LEC: May'23 | 1. Obtain TA Approval for RFQ on Dent repair by Feb'23. Achieved Mar'23
D-2-F
1 | Drill to Fill | Ready to Award (RTA) | 2023-06-30 | 2023-06-30 | 1. Complete Advert & upload Bid list in NIPEX by Jan'23. 2. Prepare in house company Estimate & Obtain Sign-off by Jan'23. 3. Issue Tech/Commercial ITT (Double envelope) to Bidders by Feb'23 4. Conclude Joint Desktop Tech Bid evaluation (CMT/NUIMS) by Apr'23 5 Conduct site visit & issue tech bids for evaluation by May'23 6. Conclude Joint Comm bid openning & Evaluation (CMT/NUIMS) by May'23 7. Issue part A & part B tech/Comm bid to partners for approval by May'23. 8. Receive approval for Award from NUIMS/ NCDMB by Jun'23
Formulas:
OP-22/P50 = [Team Target]+0

## Sheet1
MINOR MILESTONES
FYIP
S/No | Milestones | Dates | Premise
1 | Complete 12 & 24 Inch IP Works | 2023-04-30 | 1. Deliver IP Tool by end Feb'23. 2. Complete Mob of JUB (LB Grand) to site by Feb'23. 3. Secure CTS by Feb'23 4. Complete IP Works by Mar'23 5. Otain Prelims & Final report by Apr'23.
2
3
4
5
6
DOMGAS
1
2
3
4
5
6
7
TERMINALS
1
2
3
4
5
6
7
8

## DFTP Overall -OP22 (2)
DFTP OP-22 MILESTONES
S/No | Project Name | Milestones /Portfolio Details | Team Target | OP-22/P50 | LEC/ACTUAL
TERMINALS
1 | BOGT Tank Rehab | Complete Rehabilitation of Tanks 20 | 2023-06-24 | 2023-08-21
2 | BOGT Facilities | Complete Installation of Produced water Meter | 2023-07-28 | 2023-08-28
3 | FOT Tank Rehab | Progress T101 rehab to 50% | 2023-10-23 | 2023-12-23
4 | FOT Tank Rehab | Complete Robotic Cleaning of Tanks 207 | 2023-09-28 | 2023-11-28
5 | FOT Facility | Complete Auto Sampler Installation | 2023-07-29 | 2023-09-30
6 | FSPM 2 | Complete FSPM 2 Installation (ACOE) | 2023-04-30 | 2023-05-30
7 | SPM | Complete 30% Fabrication of New SPM Buoys | 2023-11-29 | 2023-12-30
8 | SPM | Complete Repair of Buoy 12481 | 2023-03-30 | 2023-04-29
9 | SSEP | Deliver LLIs to Site - BOGT, FOT, Bonga, EA | 2023-07-31 | 2023-08-31
10 | SSEP | Mechanical completion of BOGT 3 - Towers and PIDS SSEP | 2023-09-30 | 2023-10-31
11 | SSEP | Mech Completion FOT SSEP - P2 (Perimeter Video Surveillance System - CCTV) | 2023-10-31 | 2023-11-30
12 | SSEP | Mech Completion FOT SSEP - P2 (Access Control System) -Radar Action | 2023-12-31 | 2023-12-31
DOMGAS
1 | Otumara CEIP | Complete Poles Installation for Otumara CPF to Deghele Section(13km) | 2023-03-21 | 2023-04-21
2 | Otumara CEIP | Award of Section 2 Contract | 2023-10-30 | 2023-11-30
3 | SSAGS CEIP | Re-mob 1st Transmission Line Contractor for site construction. | 2023-04-29 | 2023-05-29
4 | SSAGS CEIP | Achieve 50% Foundation works at Benesede | 2023-08-30 | 2023-11-28
5 | SSAGS CEIP | Award 1st TDN Contract | 2023-05-28 | 2023-07-30
6 | SSAGS 3A | Obtain EIA Approval | 2023-09-30 | 2023-11-20
7 | SSAGS 3B | Mob Survey Contractor | 2023-04-21 | 2023-05-21
8 | SSAGS 3B | Complete FEED | 2023-09-30 | 2023-11-30
9 | SSAGS | Tunu AGC 2 Exhaust Collector Repair | 2023-05-15 | 2023-05-30
10 | SSAGS | Procure, Install & Commission HVAC systems at Tunu Central Control Room | 2023-05-15 | 2023-05-30
FYIP
1 | SBFS | SBFS Booster Compressor - RFSU | 2023-02-28 | 2023-02-28
2 | Yorkri Flow Station | YOKRI FS - RFSU | 2023-03-28 | 2023-03-28
3 | Yorkri Flow Station | Achieve Yokri Flares down | 2023-05-28 | 2023-06-27
4 | Pipeline Leak Repair | 12" SBFS-NEFS AG PL leak repair -RFSU | 2023-02-28 | 2023-03-28
5 | North Bank CPF | NB CPF - Commission & Start-up New AG compressor | 2023-02-27 | 2023-02-27 | 2023-02-27
6 | 33kv Subsea Cable | 33KV Subsea Cable Link-1 - RFSU | 2023-03-30 | 2023-04-29
7 | FOT Fuel Line | FOT Fuel Gas Sustainability - RFSU | 2023-06-30 | 2023-08-29
8 | Pipeline Dent Repair | 12"/24'' Complete Dent Repair | 2023-06-30 | 2023-09-28
D-2-F
1 | Drill to Fill | Ready to Award (RTA) | 2023-06-30 | 2023-06-30
Formulas:
OP-22/P50 = [Team Target]+0
LEC/ACTUAL = [OP-22/P50]+0