## SSAGS 3B
SSAGS STEP 3B
July 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | BulkLine | Flowlines & Hook-up | Drilling & Compl | Dredging | Constrn Camp | Rig Movw & Well Clean-up | Location Specific Cost, Security | ANGA-003 Well Prep. | Statutory costs | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 17.2 | 21.4 | 60.2 | 17.3 | 6.8 | 18.8 | 9.45 | 2.9 | 8.71 | 162.76 | P50 Months | Start | 2018-09-01 | 2020-06-24 | 2022-06-15 | 2024-07-16 | 2018-09-01 | 2023-08-07
| IPA | 2.2 | 17.2 | 21.4 | 60.2 | [6 empty] | 98.8 |  | End | 2020-06-24 | 2022-06-15 | 2024-07-16 | 2027-03-27 | 2027-03-27
| Non-IPA |  |  |  |  | 17.3 | 6.8 | 18.8 |  |  |  | 42.9 |  | Duration | 22 | 24 | 25 | 32 | 103 | 11
| Nigeria Special | [7 empty] | 9.45 | 2.9 | 8.71 | 21.06
| Benchmarking Status | TQ | 2Q | 3Q | 2Q | 2Q | 2Q | 2Q |  |  |  | TQ |  | Benchmarking Status |  | 4Q | 4Q | 3Q | 3Q
BCC BUILD UP ($ MLN) | IPA | 1.4 | 15.1 | 15.6 | 45.8 | [6 empty] | 76.5 | BCS | IPA
| Non-IPA |  |  |  |  | 12.4 | 4.5 |  |  |  |  | 16.9 |  | Non-IPA
| Nigeria Special | [10 empty] | 0 |  | Nigeria Special
| Total |  | 15.1 | 15.6 | 45.8 | 12.4 | 4.5 | 0 | 0 | 0 | 0 | 93.4 |  | IPA |  | 16 | 16 | 19 | 51
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 162.76 | 162.76 |  | Remaining Duration |  |  |  | 43 | 43
| Use 14km bulkline identified from FYIP stock, out of required 18 km | [9 empty] | -2 |  |  | Leverage on opportunistic SD window (IAP) for early Browfield tie-works |  |  |  | -3
| Post-tender negotiation (optimise contract) | [9 empty] | -1 |  |  | Accelerate rig availability |  |  |  | -2
| KUDH Well design optimization using High perf. WBM | [9 empty] | -2.1 |  |  | Use of suplus linepipes stock from FYIP |  |  |  | -6
| Use high perf. WBM in place of POBM/re-use inventory stock | [9 empty] | -2.3 |  |  | Adoption of re-engineered WBM |  |  |  | -0.5
| Single trip completions | [9 empty] | -1.2 |  |  | Learnings from 3A - Use of pre-FEED information from Step 3A (inhouse experience). |  |  |  | -2
| Use of grey stock Xmas tree | [9 empty] | -0.5 |  |  | Use of OABP contracts – Back up to clustering |  |  |  | -3
| Rigless well testing | [9 empty] | -1 |  |  | Mobilisation of Survey Contractor to Site |  |  |  | -1 | -1
| Use of EFA for linepipes procurement (China mills) | [9 empty] | -0.1 |  |  | FEED Completion |  |  |  | -2
| Use of same contractors from prior projects e.g.SSAGS 2 & 3A | [9 empty] | -0.21
| Total | [9 empty] | 152.35 | 162.76 |  | Total |  |  |  | 23.5 | 42
Gap to Potential Report
Linepipes already identified and QA/QC carried out
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## HAGasPhase1A (hidden)
HA Phase 1 Development Project
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | PP + LQ | WHP | PPL Gas | PPL Oil | PPL water | FSO | WELLS | Total | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME | Current date
P50 EDM LE ($ mln) | Total |  | 803.3716 | 126.8113 | 62.4187 | 97.528 | 48.5509 | 303.7276 | 222.2731 | 1664.6811 | P50 Months | Start | 2017-04-19 | 2017-11-28 | 2020-03-27 | 2024-01-31 | 2017-04-19 | 2023-08-07
| IPA | 2.2 | 642.6973 | 100.1809 | 25.5917 | 35.1101 | 31.5581 | 261.2057 | 217.8277 | 1314.1714 |  | End | 2017-11-28 | 2020-03-27 | 2024-01-31 | 2028-07-27 | 2028-07-27
| Non-IPA | [8 empty] | 0 |  | Duration | 7 | 28 | 46 | 54 | 135 | 6
| Nigeria Special |  | 160.6743 | 26.6304 | 36.827 | 62.4179 | 16.9928 | 42.5219 | 4.4455 | 350.5097
| Benchmarking Status | TQ | 4Q | 4Q | BiC | 4Q | 2Q | 2Q | 4Q | 3Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | 1.4 | 365.7865 | 62.602 | 33.6049 | 14.0193 | 20.4788 | 37.7878 | 80.8705 | 615.1498 | BCS | IPA
| Non-IPA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Non-IPA
| Nigeria Special |  | 88.7728 | 16.8577 | 49.3191 | 24.7348 | 10.8542 | 5.981 | 18.6002 | 215.1197 |  | Nigeria Special
| Total |  | 454.5593 | 79.4597 | 82.9239 | 38.7541 | 31.333 | 43.7687 | 99.4708 | 830.2695 |  | IPA |  | 17.7 | 20.7 | 46 | 84.4
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [9 empty] | Schedule | Duration Log
| Description | [7 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [7 empty] | 1664.6811 | 1664.6811 |  | Remaining Duration |  |  |  | 60 | 60
| Fab yard productivity, Helidek, and Boat catcher Optimization | [7 empty] | -33 |  |  | FEED Rollover |  |  |  | -2
| Equipment and pipeline size optimization | [7 empty] | -5.88 |  |  | Fabrication improvement |  |  |  | -4
| Commercial and CP optimization | [7 empty] | -79 |  |  | HLV availability |  |  |  | -2
| Offshore installation related optimization | [7 empty] | -37.26 |  |  | Construction Efficiency |  |  |  | -4
| Mooring change from spread to SYMP | [7 empty] | -22.2
| Total | [7 empty] | 1487.3411 | 1664.6811 |  | Total |  |  |  | 48 | 60
Gap to Potential Report
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]