## Slide 1: Produced water sump pump P-1404A/B Optimization study and implementation
BOGT MECHANICAL TEAM

## Slide 2
Unit 14 Sump Pump P-1401A/B Optimisation Study And Implementation
  Production Unit: Central East Hub - Bonny
  Project Owner: lroloye Bob-manuel/Essienton Victor
  Process Custodian: Opel Joel
  Process Focal Point: Bela-zabe Dumtuaka
  Process Stakeholders: Ikechi Amaewhule, Brossa Isaac, Osita Nnajiofor, Terfa Iortsuun, Ireti Omotoso, Roddy Simon
PROCESS OWNERSHIP
OPPORTUNITY STATEMENT
Opportunity Framing
Fluid Laboratory analysis and simulations
MOC/TA Approvals
Material sourcing and procurement
Execution by DIY
Commissioning
SCOPE
BUSINESS CASE
GOAL
POTENTIAL ROADBLOCKS/ ISSUES
Gross Cost
Material Cost (NGN165,000)
Machinist cost (NGN100,000)
Technician cost (NGN 50,000)
Soft Benefits:
- Safer unit for operators’ daily routine
- Improved wrench time
- Stress Reduction
COST/BENEFITS
The BOGT produced water sump pump P-1404A/B has not worked since inception (2008). Pump continued to suffer extremely high frequency of failures after commissioning. All efforts by OEM and other support teams to proffer a solution failed to date.
Gas release and crude overflow have occurred severally due to P-1404A/B non functionality. Also the BDH quality remains a concern.
New initiative by OEM to produce a customized pump was to cost over 1.5m without 100% guarantee that it will solve the problem.
The asset saw a huge opportunity to conduct an optimization study and implementation of study report to ensure value for money and improvement on safety.
Successful resolution of this problem using inhouse resources will:
Eliminate continuous gas release due to use of surface pumps
Eliminate risk of vessel overflow due to non-functional Pump and improve BDH
Result in significant cost savings with improved pump availability and reliability.
Cost savings of $1.5M, Safety, efficiency, service, and improved workplace ambience
Precision machining and fabrication issues
Performance testing challenges.
100%
0%
01/09/19
20/10/19
PROCESS STATUS
70%
100%
Health
% Compl
Completion Date
Start Date
Overall Health Status (Current)
Study/ Materials Procurement
Cutting, Machining and fabrication
Part assembly and pump building
Installation and Commissioning
21/09/19
20/10/19
Continuous
Gross Hard Benefits*:
Cost saving ($1.5m)
Eliminate Continuous gas release/crude overflow
30/09/19
30/03/19
21/09/19