## STOG Opportunities Execution Pl
Execution Plan for STOG Opportunities Maturation Project Team
[7 empty] | 2017-02-01 |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-02 |  |  |  | 2017-06-03 |  |  |  | 2017-07-04
S/N | ACTIVITY | ACTION PARTY | START DATE | END DATE | STATUS | REMARK | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
1 | Share out list of Immediate / ST wells to PUM's | Devt | 2018-02-20 | 2018-02-20 | Completed | *Divide list into Asset Engineering and CWI. *Cross check Isu well.
2 | Receive pictures of Immediate/ ST wells from PUM's | PUM's | 2018-02-21 | 2018-02-25 | Completed | *Pictures of Locations, Wellheads, Flowlines including a report of the ROW i.e Encroachment etc. | 0
3 | Low hanging fruits | Asset Engr & CWI | 2018-02-21 | 2018-03-02 | Completed | *Bean up's on gas lift lines etc. 6 out of 6 wells beaned up.
4 | Review information from PUM's - Scope verification | Asset Engr & CWI | 2018-02-26 | 2018-02-26 | Completed | *Possible renewal of proposal where scope changes
| Feed back from Geomatics | Asset Engr | 2018-02-26 | 2018-03-01 | Completed | Encroachment status for Flowlines etc.
| Review Fims report to assess the integrity of the fLowlines | Asset Engr | 2018-02-27 | 2018-02-28 | Completed | Mostly amber/yellow
5 | Site visit | Asset Engr & CWI | 2018-03-05 | 2018-03-09 | Completed | *Include pictures where applicable Rescheduled to 5th - 9th March in view of no security escorts. Obigbo & Nkali pending.
| Pressure Testing / Costing (Quick Wins) | Asset Engr | 2018-03-05 | 2018-03-16 | Completed | 6 wells already completed and confirmed ok.
6 | Cost Estimation and Material availability | Asset Engr & CWI | 2018-03-19 | 2018-03-23 | Completed
8 | Cost/Scope Challenge | ALL | 2018-03-27 | 2018-03-27 | Completed
11 | Budget Proposal to AM | Ufuoma/BT | 2018-03-29 | 2018-03-29 | Completed
9 | Sequencing (FTO,Logistics etc) | ALL | 2018-03-30 | 2018-03-30 | Completed
10 | Finalize Execution plan + Cost Estimate report for Budget | ALL | 2018-03-30 | 2018-04-02 | Completed | *Prioritize in terms of do-ability/reduced cost.
12 | Execution (Full pressure test + Restoration + CWI Scope) | ALL | 2018-04-03 | 2018-07-31 | Completed | Early pressure test completed for 6 wells and proposals sent to CWI.
13 | Immediate and ST -Test Date |  | 2018-08-01 | 2018-12-31 | In progress | First oil depends on scope and materilas availbility for completion - End to End. Agbada 54 (200bopd), Min 002 (250bopd), Imor 57 (500bopd). Remaining 13 candidates awaiting CWI space to unlock total 5000bopd).
LEGEND
Completed
In progress
Not Started
Note on C6: Jamabo, Ibinabo SPDC-UPO/G/PL: Delays due to Security challenges

## Sheet1 (hidden)
S/N | ACTIONS | ACTION PARTY | TCD
1 | Follow up with PUM's for pictures of Immediate/ST wells | BT | 2018-02-27
2 | Include gains from Beaned up wells and Gas lift | Felix | 2018-02-28
3 | Scope for Pressure testing/Costing (Include timelines) | Asset Engr | 2018-02-28
4 | CWI to nominate a representative for Re-scheduled Site visit | Conrad | 2018-03-01
5 | Present options for Pressure Testing/Cost to AM | Ufuoma/BT | 2018-03-01