## AMOR1A
Agbada NAG Filler (AMOR 1A)
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | Bulklines | Drilling & Completion | Construction Camp | Concrete Coating | Loc prep, citadel fencing & cages | Well site fac. & acc | Location Specific Cost, Security | Statutory costs |  | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 33 | 32 | 8 | 1 | 5 | 12 | 8 | 5 | 0 | 104 | P50 Months | Start | 2019-09-01 | 2020-08-30 | 2021-09-30 | 2022-07-31 | 2019-09-01
| IPA | 1.5 | 33 | 32 | [7 empty] | 65 |  | End | 2020-08-30 | 2021-09-30 | 2022-07-31 | 2024-05-31 | 2024-05-31
| Non-IPA |  |  |  | 8 | 1 | [5 empty] | 9 |  | Duration | 12 | 13 | 10 | 22 | 57
| Nigeria Special | [5 empty] | 5 | 12 | 8 | 5 |  | 30
| Benchmarking Status | TQ | BiC | 2Q | 2Q | BiC | [5 empty] | TQ |  | Benchmarking Status |  | 4Q | 3Q | 4Q | 3Q
BCC BUILD UP ($ MLN) | IPA | 1.1 | 34 | 23 | [7 empty] | 57 | BCS | IPA
| Non-IPA |  |  |  | 4.5 | 1 | [5 empty] | 5.5 |  | Non-IPA
| Nigeria Special | [10 empty] | 0 |  | Nigeria Special
| Total |  | 34 | 23 | 4.5 | 1 | 0 | 0 | 0 | 0 | 0 | 62.5 |  | IPA |  | 6 | 6 | 19 | 31
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 104 | 104 |  | Remaining Duration |  |  |  |  | 32
| CS: Wells initiatives | [9 empty] | -1.5 |  |  | EIA acceleration |  |  |  | -6
| TI: Single trip multi-zone gravel pack | [9 empty] | -1.2 |  |  | Use of call-off contract |  |  |  | -8
| TI: Use of high performance water based mud | [9 empty] | -0.5 |  |  | Early tie-in works |  |  |  | -2
| TI: Use of coated tubing vs 13% chrome | [9 empty] | -0.6 |  |  | Construction efficiency |  |  |  | -1
| SCT: Wells rates & contracts | [9 empty] | -0.53 |  |  | Pre-FID procurement of LLIs |  |  |  | -9
| SCT: Separate and accelerate specific works from main EPC contract | [9 empty] | -0.33 |  |  | NTR Management |  |  |  | -4
| SCT: Early discount mechanism introduced as option in contract | [9 empty] | -0.41
| SCT: Use of local EPC type contractors | [9 empty] | -1.18
| EE: Reduction in camp site to 75-man bed | [9 empty] | -3
| Total | [9 empty] | 94.75 | 104 |  | Total |  |  |  |  | 32
Gap to Potential Report
Linepipes already identified and QA/QC carried out
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## SSAGS 3A
SSAGS STEP 3A
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | flowlines + Hookup | Construction Camp | Dredging Cost | Wells Cost | Temp. Const fac | Location Specific Cost, Security | Wells Specials | Statutory costs |  | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 32.4 | 5.2 | 17 | 114 | 3.3 | 8.3 | 5.3 | 10.1 |  | 195.6 | P50 Months | Start | 2017-12-25 | 2019-12-18 | 2021-05-21 | 2023-05-19 | 2017-12-25 | 2023-03-26
| IPA | 2.6 | 32.4 | [8 empty] | 32.4 |  | End | 2019-12-18 | 2021-05-21 | 2023-05-19 | 2026-02-20 | 2026-02-20
| Non-IPA |  |  | 5.2 | 17 | 114 | [5 empty] | 136.2 |  | Duration | 24 | 17 | 24 | 33 | 98 | 2
| Nigeria Special | [5 empty] | 3.3 | 8.3 | 5.3 | 10.1 |  | 27
| Benchmarking Status | 2Q | 3Q | 2Q | 2Q | TQ | [5 empty] | TQ |  | Benchmarking Status |  | BiC | 2Q | 2Q | 2Q
BCC BUILD UP ($ MLN) | IPA | 1.5 | 23 | [8 empty] | 23 | BCS | IPA
| Non-IPA |  |  | 3.1 | 10 | 98 | [5 empty] | 111.1 |  | Non-IPA
| Nigeria Special | [10 empty] | 0 |  | Nigeria Special
| Total |  | 23 | 3.1 | 10 | 98 | [5 empty] | 134.1 |  | IPA |  | 17 | 19 | 25 | 61
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 195.6 | 195.6 |  | Remaining Duration |  |  |  |  | 35
| Define: Standardization: Application of industry standard, EPC scope, unbundling, call-off contracts | [9 empty] | -6 |  |  | Use of call-off contracts |  |  |  | -8
| Define: Use of same contracts as step 2 | [9 empty] | -0.33 |  |  | EIA acceleration (1 season) |  |  |  | -7
| PBOM with high perf WBM single trip completion | [9 empty] | -8 |  |  | Early tie-in |  |  |  | -2
| Negotiate rig day rate, discout from bulk purchase of X-mas tree | [9 empty] | -1 |  |  | Construction efficiency |  |  |  | -1
| Drilling optimization (Time reduction/NPT elimination) | [9 empty] | -3 |  |  | Pre-FID procurement of Llis |  |  |  | -8
| Post tender negotiation | [9 empty] | -2 |  |  | NTR management |  |  |  | -4
| Using local construction contractors vs EPC premium | [9 empty] | -2
| Use of gray stock X-mas tree, rigless well test, High perf WBM | [9 empty] | -7
| Total | [9 empty] | 166.27 | 195.6 |  | Total |  |  |  |  | 35
Gap to Potential Report
Approval secured for a single season sampling
2021-05-21
2019-12-28
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]
Duration Log = [Duration Log, row above]-(17*30)

## SSAGS 3B
SSAGS STEP 3B
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | BulkLine | Flowlines & Hook-up | Drilling & Compl | Dredging | Constrn Camp | Rig Movw & Well Clean-up | Location Specific Cost, Security | ANGA-003 Well Prep. | Statutory costs | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 17.2 | 21.4 | 60.2 | 17.3 | 6.8 | 18.8 | 9.45 | 2.9 | 8.71 | 162.76 | P50 Months | Start | 2018-09-01 | 2020-06-24 | 2022-06-15 | 2024-07-16 | 2018-09-01 | 2023-03-26
| IPA | 2.2 | 17.2 | 21.4 | 60.2 | [6 empty] | 98.8 |  | End | 2020-06-24 | 2022-06-15 | 2024-07-16 | 2027-03-27 | 2027-03-27
| Non-IPA |  |  |  |  | 17.3 | 6.8 | 18.8 |  |  |  | 42.9 |  | Duration | 22 | 24 | 25 | 32 | 103 | 16
| Nigeria Special | [7 empty] | 9.45 | 2.9 | 8.71 | 21.06
| Benchmarking Status | TQ | 2Q | 3Q | 2Q | 2Q | 2Q | 2Q |  |  |  | TQ |  | Benchmarking Status |  | 4Q | 4Q | 3Q | 3Q
BCC BUILD UP ($ MLN) | IPA | 1.4 | 15.1 | 15.6 | 45.8 | [6 empty] | 76.5 | BCS | IPA
| Non-IPA |  |  |  |  | 12.4 | 4.5 |  |  |  |  | 16.9 |  | Non-IPA
| Nigeria Special | [10 empty] | 0 |  | Nigeria Special
| Total |  | 15.1 | 15.6 | 45.8 | 12.4 | 4.5 | 0 | 0 | 0 | 0 | 93.4 |  | IPA |  | 16 | 16 | 19 | 51
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 162.76 | 162.76 |  | Remaining Duration |  |  |  | 48 | 48
| Use 14km bulkline identified from FYIP stock, out of required 18 km | [9 empty] | -2 |  |  | Leverage on opportunistic SD window (IAP) for early Browfield tie-works |  |  |  | -3
| Post-tender negotiation (optimise contract) | [9 empty] | -1 |  |  | Accelerate rig availability |  |  |  | -2
| KUDH Well design optimization using High perf. WBM | [9 empty] | -2.1 |  |  | Use of suplus linepipes stock from FYIP |  |  |  | -6
| Use high perf. WBM in place of POBM/re-use inventory stock | [9 empty] | -2.3 |  |  | Adoption of re-engineered WBM |  |  |  | -0.5
| Single trip completions | [9 empty] | -1.2 |  |  | Learnings from 3A - Use of pre-FEED information from Step 3A (inhouse experience). |  |  |  | -2
| Use of grey stock Xmas tree | [9 empty] | -0.5 |  |  | Use of OABP contracts – Back up to clustering |  |  |  | -3
| Rigless well testing | [9 empty] | -1
| Use of EFA for linepipes procurement (China mills) | [9 empty] | -0.1
| Use of same contractors from prior projects e.g.SSAGS 2 & 3A | [9 empty] | -0.21
| Total | [9 empty] | 152.35 | 162.76 |  | Total |  |  |  | 31.5 | 48
Gap to Potential Report
Linepipes already identified and QA/QC carried out
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## Kolo Creek F-Sand
KOLO CREEK F-SAND
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | Bulkline | Concrete Coating | Construction Camp | Pig Traps | Manifold | Slug Catcher | Tie-in scope | Location Specific Cost, Security | Statutory costs | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 120.5 | 4.5 | 19.4 | 2.8 | 24.8 | 3.2 | 8.13 | 34.78 | 16.93 | 235.04 | P50 Months | Start | 2019-09-01 | 2021-02-28 | 2022-09-30 | 2024-02-28 | 2019-09-01
| IPA |  | 120.5 |  |  |  | 24.8 |  |  |  |  | 145.3 |  | End | 2021-02-28 | 2022-09-30 | 2024-02-28 | 2028-01-17 | 2028-01-17
| Non-IPA |  |  | 4.5 | 19.4 | 2.8 |  | 3.2 |  |  |  | 29.9 |  | Duration | 18 | 19 | 17 | 47 | 101
| Nigeria Special | [7 empty] | 8.13 | 34.78 | 16.93 | 59.84
| Benchmarking Status |  | 2Q | BiC | 2Q | TQ | TQ | TQ |  |  |  | TQ |  | Benchmarking Status |  | 4Q | 3Q | 4Q | 3Q
BCC BUILD UP ($ MLN) | IPA |  | 98.2 |  |  |  | 23.1 |  |  |  |  | 121.3 | BCS | IPA
| Non-IPA |  |  | 4.7 | 17.6 | 2.5 |  | 3.1 |  |  |  | 27.9 |  | Non-IPA
| Nigeria Special | [12 empty] | Nigeria Special
| Total |  | 98.2 | 4.7 | 17.6 | 2.5 | 23.1 | 3.1 |  |  |  | 149.2 |  | IPA |  | 16 | 16 | 19 | 51
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 235.04 | 235.04 |  | Remaining Duration |  |  |  |  | 64
| Structure early contractor involvement + roll over from other projects | [9 empty] | -1 |  |  | Define: Expedited stakeholder alignment & DPR approval of FDP |  |  |  | -2
| Synergies with other ongoing project | [9 empty] | -2 |  |  | Define: Leverage on K2S FEED |  |  |  | -2
| Using smaller contractors | [9 empty] | -9 |  |  | Define: Leverage existing K2S EIA |  |  |  | -3
| Post tender negotiation (structural fix - early payment discout) | [9 empty] | -5 |  |  | Execute: Early tie-ins. |  |  |  | -2
| Use of existing construction camp | [9 empty] | -1 |  |  | Execute: Fabrication of slugcatched overseas |  |  |  | -6
| Use of smaller lay barge | [9 empty] | -2 |  |  | Execute: Use existing competent construction contrator within the organisation |  |  |  | -4
| 60% BL concrete coating | [9 empty] | -2 |  |  | Execute: Pre-FID funding for location prep + procurement of LLIs |  |  |  | -6
| Use only dry season/spread over 2 seasons | [9 empty] | -1
| Total | [9 empty] | 212.04 | 235.04 |  | Total |  |  |  |  | 64
Gap to Potential Report
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## HI Development
HI Development Project
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | PP | WHP | PPL | WELLS | Total | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME | Current date
P50 EDM LE ($ mln) | Total | 6.6719 | 1412.8419 | 292.6325 | 244.4954 | 185 | 2134.9698 | P50 Months | Start | 2006-03-01 | 2010-09-24 | 2019-11-19 | 2023-10-27 | 2006-03-01 | 2023-03-26
| IPA |  | 1291.7618 | 262.5124 | 219.33 | 150.9281 | 1924.5323 |  | End | 2010-09-24 | 2019-11-19 | 2023-10-27 | 2027-07-27 | 2027-07-27
| Non-IPA | [5 empty] | 0 |  | Duration | 55 | 110 | 47 | 45 | 257 | 7
| Nigeria Special |  | 121.0801 | 30.1201 | 25.1654 | 34.0719 | 210.4375
| Benchmarking Status | 2Q | 4Q | 4Q | 4Q | 4Q | 4Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | 4.8 | 621.7086 | 102.3966 | 92.3454 | 80.8705 | 902.1211 | BCS | IPA
| Non-IPA |  | 0 | 0 | 0 | 0 | 0 |  | Non-IPA
| Nigeria Special |  | 57.491 | 11.7488 | 10.5955 | 18.6002 | 98.4355 |  | Nigeria Special
| Total |  | 679.1996 | 114.1454 | 102.9409 | 99.4708 | 995.7567 |  | IPA |  |  |  |  | 0
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [6 empty] | Schedule | Duration Log
| Description |  |  |  |  | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate |  |  |  |  | 2134.9698 | 2134.9698 |  | Remaining Duration |  |  |  | 52 | 52
| WHP Optimization |  |  |  |  | -40.8 |  |  | Minimize carry over work to ALARP |  |  |  | -2
| HU&C |  |  |  |  | -17.6 |  |  | 24/7 work pattern for critical activities and key disciplines |  |  |  | -2
| Depletion Compressors Postponement |  |  |  |  | -45.6 |  |  | Construction Efficency |  |  |  | -1.5
| Modularised LQ |  |  |  |  | -16
| 2x100% Mars 100GTG's to 3x50% Solar Taurus 60 (or Equiv) by rationalizing loads |  |  |  |  | -8
| Pipe Rating 1500 to 900 Pipe Materila SS/Super duplex vs Stainless Steel Cladding on CS |  |  |  |  | -1.36
| Structural analysis for PP, incoorporating above improvements (weight reduction) and confirming design standards |  |  |  |  | -22.4
| Total |  |  |  |  | 1983.2098 | 2134.9698 |  | Total |  |  |  | 46.5 | 52
Gap to Potential Report
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## HA Gas Phase 1A
Project Name
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | PP + LQ | WHP | PPL Gas | PPL Oil | PPL water | FSO | WELLS | Total | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME | Current date
P50 EDM LE ($ mln) | Total |  | 803.3716 | 126.8113 | 62.4187 | 97.528 | 48.5509 | 303.7276 | 222.2731 | 1664.6811 | P50 Months | Start | 2017-04-19 | 2017-11-28 | 2020-03-27 | 2024-01-31 | 2017-04-19 | 2023-03-26
| IPA |  | 642.6973 | 100.1809 | 25.5917 | 35.1101 | 31.5581 | 261.2057 | 217.8277 | 1314.1714 |  | End | 2017-11-28 | 2020-03-27 | 2024-01-31 | 2028-07-27 | 2028-07-27
| Non-IPA | [8 empty] | 0 |  | Duration | 7 | 28 | 46 | 54 | 135 | 10
| Nigeria Special |  | 160.6743 | 26.6304 | 36.827 | 62.4179 | 16.9928 | 42.5219 | 4.4455 | 350.5097
| Benchmarking Status | TQ | 4Q | 4Q | BiC | 4Q | 2Q | 2Q | 4Q | 3Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA |  | 365.7865 | 62.602 | 33.6049 | 14.0193 | 20.4788 | 37.7878 | 80.8705 | 615.1498 | BCS | IPA
| Non-IPA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Non-IPA
| Nigeria Special |  | 88.7728 | 16.8577 | 49.3191 | 24.7348 | 10.8542 | 5.981 | 18.6002 | 215.1197 |  | Nigeria Special
| Total |  | 454.5593 | 79.4597 | 82.9239 | 38.7541 | 31.333 | 43.7687 | 99.4708 | 830.2695 |  | IPA |  | 17.7 | 20.7 | 46 | 84.4
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [9 empty] | Schedule | Duration Log
| Description | [7 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [7 empty] | 1664.6811 | 1664.6811 |  | Remaining Duration |  |  |  | 64 | 64
| Fab yard productivity, Helidek, and Boat catcher Optimization | [7 empty] | -33 |  |  | Pre-FID Funding |  |  |  | -4
| Equipment and pipeline size optimization | [7 empty] | -5.88 |  |  | FEED Rollover |  |  |  | -2
| Commercial and CP optimization | [7 empty] | -79 |  |  | Fabrication improvement |  |  |  | -4
| Offshore installation related optimization | [7 empty] | -37.26 |  |  | HLV availability |  |  |  | -2
| Mooring change from spread to SYMP | [7 empty] | -22.2 |  |  | Construction Efficiency |  |  |  | -4
| Total | [7 empty] | 1487.3411 | 1664.6811 |  | Total |  |  |  | 48 | 64
Gap to Potential Report
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## HAGasPhase1A (hidden)
HA Phase 1 Development Project
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG3
WBS Element |  | UDC ($/boe) | PP + LQ | WHP | PPL Gas | PPL Oil | PPL water | FSO | WELLS | Total | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME | Current date
P50 EDM LE ($ mln) | Total |  | 803.3716 | 126.8113 | 62.4187 | 97.528 | 48.5509 | 303.7276 | 222.2731 | 1664.6811 | P50 Months | Start | 2017-04-19 | 2017-11-28 | 2020-03-27 | 2024-01-31 | 2017-04-19 | 2023-03-26
| IPA | 2.2 | 642.6973 | 100.1809 | 25.5917 | 35.1101 | 31.5581 | 261.2057 | 217.8277 | 1314.1714 |  | End | 2017-11-28 | 2020-03-27 | 2024-01-31 | 2028-07-27 | 2028-07-27
| Non-IPA | [8 empty] | 0 |  | Duration | 7 | 28 | 46 | 54 | 135 | 10
| Nigeria Special |  | 160.6743 | 26.6304 | 36.827 | 62.4179 | 16.9928 | 42.5219 | 4.4455 | 350.5097
| Benchmarking Status | TQ | 4Q | 4Q | BiC | 4Q | 2Q | 2Q | 4Q | 3Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | 1.4 | 365.7865 | 62.602 | 33.6049 | 14.0193 | 20.4788 | 37.7878 | 80.8705 | 615.1498 | BCS | IPA
| Non-IPA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Non-IPA
| Nigeria Special |  | 88.7728 | 16.8577 | 49.3191 | 24.7348 | 10.8542 | 5.981 | 18.6002 | 215.1197 |  | Nigeria Special
| Total |  | 454.5593 | 79.4597 | 82.9239 | 38.7541 | 31.333 | 43.7687 | 99.4708 | 830.2695 |  | IPA |  | 17.7 | 20.7 | 46 | 84.4
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [9 empty] | Schedule | Duration Log
| Description | [7 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [7 empty] | 1664.6811 | 1664.6811 |  | Remaining Duration |  |  |  | 64 | 64
| Fab yard productivity, Helidek, and Boat catcher Optimization | [7 empty] | -33 |  |  | FEED Rollover |  |  |  | -2
| Equipment and pipeline size optimization | [7 empty] | -5.88 |  |  | Fabrication improvement |  |  |  | -4
| Commercial and CP optimization | [7 empty] | -79 |  |  | HLV availability |  |  |  | -2
| Offshore installation related optimization | [7 empty] | -37.26 |  |  | Construction Efficiency |  |  |  | -4
| Mooring change from spread to SYMP | [7 empty] | -22.2
| Total | [7 empty] | 1487.3411 | 1664.6811 |  | Total |  |  |  | 52 | 64
Gap to Potential Report
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## Enwhe
Enwhe Project
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | Pipeline | Remote Facilities | Location Preparation | Reimbursible | PMT | Non-EPC | Wells | Contingency | Total | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 104.845 | 113.5717 | 25.9553 | 16.8669 | 26.1854 | 35.0833 | 118 | 49.0739 | 489.5815 | P50 Months | Start |  |  |  | 2018-08-09 | 2018-08-09
| IPA |  | 104.845 | 113.5717 |  |  | 26.1854 |  | 118 |  | 362.6021 |  | End |  |  |  | 2022-06-22 | 2022-06-22 | 1st gas achieved
| Non-IPA |  |  |  | 25.9553 | 16.8669 |  |  |  | 49.0739 | 91.8961 |  | Duration (months) | 0 | 0 | 0 | 46 | 46
| Nigeria Special | [6 empty] | 35.0833 |  |  | 35.0833
| Benchmarking Status |  | 2Q | 3Q |  |  |  |  | 1Q |  |  |  | Benchmarking Status |  |  |  | 3Q | 3Q
BCC BUILD UP ($ MLN) | IPA |  | 100.5 | 110.1457 |  |  | 26.1854 |  | 102 |  | 338.8311 | BCS | IPA |  |  |  | 27 |  | Industry average (IPA)
| Non-IPA |  |  |  | 25.9553 | 7 |  |  |  | 16.2689 | 49.2241 |  | Non-IPA
| Nigeria Special | [6 empty] | 31.9188 |  |  | 31.9188 |  | Nigeria Special
| Total |  | 100.5 | 110.1457 | 25.9553 | 7 | 26.1854 | 31.9188 | 102 | 16.2689 | 419.974 |  | IPA (months) |  |  |  | 27 | 27
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [10 empty] | Schedule | Duration Log
| Description | [8 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status |  | 2023-03-22 | Today
| Current Estimate | [8 empty] | 489.5815 | 560 |  | Remaining Duration (Enwhe West) |  |  |  | 7 | 7 |  | 2023-09-30 | LE | 6.4 | remaining duration
| Pipeline Package extension of time/preservation VOs | [8 empty] | 20.0271 |  |  | Improve HoTT productivity; Reduced illegal work stoppage |  |  |  | -0.25
| Facilities Package extension of time & other VOs | [8 empty] | 49.7394 |  |  | Early PO placement for LLIs/NCDMB engagement; Close PMT Management of ER Team w.r.t GMOU to forestall community related disruption |  |  |  | -1
| Location preparation | [8 empty] | 0.90769 |  |  | Late Well Spud from February to April LE |  |  |  | 2
| SILS | [8 empty] | 19.4465 |  |  | Maximize weather window to complete construction in one dry season |  |  |  | -1.5
| PMT | [8 empty] | 9.4522
| Wells | [8 empty] | 19.171
| Contingency | [8 empty] | -48.7239
| Total | [8 empty] | 559.6014 | 560 |  | Total |  |  |  | 6.25 | 7
Gap to Potential Report
Note: All costs are in MOD as project is in execute and based on contracts
Formulas:
CYCLE TIME = +[EXECUTE]

## GNC
Gbaran Nodal Compression (GNC)
March 2023
Legend: Color code against Benchmark
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | Compressor Purchase contract | Facilities - EPC contract | SILS | Project Management | SCD | Pre-FID | Contingency | Total | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total | 1 | 32.2679 | 122.8673 | 4.2724 | 22.703 | 3.6722 | 2.8778 | 25.5194 | 214.1801 | P50 Months | Start |  |  |  | 2018-09-17 | 2018-09-17
| IPA | 6 | [7 empty] | 0 |  | End |  |  |  | 2021-09-30 | 2023-07-31 | Train 1
| Non-IPA |  | 32.2679 | 122.8673 | 4.2724 | 22.703 | 3.6722 | 2.8778 | 25.5194 | 214.1801 |  | Duration (months) | 0 | 0 | 0 | 36 | 58
| Nigeria Special | [8 empty] | 0
| Benchmarking Status | BiC | 1Q | 1Q | [7 empty] | Benchmarking Status
BCC BUILD UP ($ MLN) | IPA |  | 32.2679 | 108.6673 | 4.2724 | 17.203 | 3.6722 | 2.8778 | 11 | 179.9606 | BCS | IPA |  |  |  | 25 |  |  | 2020-11-30
| Non-IPA | [8 empty] | 0 |  | Non-IPA
| Nigeria Special | [8 empty] | 0 |  | Nigeria Special
| Total |  | 32.2679 | 108.6673 | 4.2724 | 17.203 | 3.6722 | 2.8778 | 11 | 179.9606 |  | IPA (months) |  |  |  | 25 | 25
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [9 empty] | Schedule | Duration Log
| Description | [7 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status |  | 2023-03-01 | currently
| Current Estimate | [7 empty] | 214.1801 | 325.0185 |  | Remaining Duration (Train 1) |  |  |  | 7.1 | 7 |  | 2023-09-30 | 7.1 | LE
| Compressor purchase VOs | [7 empty] | 4.1265 |  |  | Enhanced HOTT |  |  |  | -0.35
| Facilities EPC VOs | [7 empty] | 63.8217 |  |  | Support Contractor resources on site (Equipment) |  |  |  | -1
| Non-EPC (securrity, insurance, lands, survey, etc) | [7 empty] | 10.6692 |  |  | Increased PMT supervision onsite |  |  |  | -0.3
| Project Management | [7 empty] | 17.121
| Contingency | [7 empty] | 15.1
| Total | [7 empty] | 325.0185 | 325.0185 |  | Total |  |  |  | 5.45 | 7
Gap to Potential Report
Note: All costs are in MOD as project is in execute and based on contracts
Formulas:
CYCLE TIME = +[EXECUTE]

## Uzu
Uzu + CPF Upgrade
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | Pipeline | Remote Facilities | CPF Ugrade (TEG unit) | Location Preparation | PMT | Non-EPC | Wells | Non-Performance Allowance | Contingency | Total | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 28.6759 | 32.8719 | 49.2439 | 6.9458 | 26.61 | 37.372 | 105.835 | 30.442 | 27.0047 | 345.0011 | P50 Months | Start |  |  |  | 2021-07-31 | 2021-07-31 | 2023-03-26
| IPA | 1.84 | 28.6759 | 32.8719 | 49.2439 |  | 26.61 |  | 105.835 |  |  | 243.2367 |  | End |  |  |  | 2024-10-30 | 2024-10-30
| Non-IPA |  |  |  |  | 6.9458 |  |  |  |  | 27.0047 | 33.9504 |  | Duration (months) | 0 | 0 | 0 | 39 | 39 | 19
| Nigeria Special | [6 empty] | 37.372 |  | 30.442 |  | 67.8139
| Benchmarking Status | 2Q | 1Q | 1Q | 3Q |  |  |  | 2Q |  |  |  |  | Benchmarking Status |  |  |  | 4Q | 4Q
BCC BUILD UP ($ MLN) | IPA | 1.68 | 28.6759 | 32.8719 | 49.2439 |  | 26.61 |  | 105.835 |  |  | 243.2367 | BCS | IPA
| Non-IPA |  |  |  |  | 6.9458 |  |  |  |  | 28.3658 | 35.3116 |  | Non-IPA
| Nigeria Special | [6 empty] | 37.372 |  |  |  | 37.372 |  | Nigeria Special
| Total |  | 28.6759 | 32.8719 | 49.2439 | 6.9458 | 26.61 | 37.372 | 105.835 | 0 | 28.3658 | 315.9203 |  | IPA (months) |  |  |  | 18 | 18
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 345.0011 | 345.0011 |  | Remaining Duration |  |  |  | 19 | 19
| Use of Shell turbo tray technology instead of new TEG facility for Gbaran CPF debottlenecking | [9 empty] | -30 |  |  | Improve HoTT productivity |  |  |  | -1
[14 empty] | Early PO placement for LLIs/NCDMB engagement |  |  |  | -1
[14 empty] | Proactive/Early NTR (Community/Security) and stakeholder management, Maximize weather window to complete construction in one dry season |  |  |  | -2
| Total | [9 empty] | 315.0011 | 345.0011 |  | Total |  |  |  | 15 | 19
Gap to Potential Reporting Template
Note: GIP promise of $345Mln & GMT target of $315.9Mln are in MOD for Uzu because project is in execute and costs are firmed (contract prices)
Formulas:
CYCLE TIME = +[EXECUTE]

## GSW
Gbaran Single Well (GSW)
March 2023
Legend: Color code against Benchmark
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | Facilities Pk-1 | Pipelines Pk-2 | Well | PMT | Non-EPC | Contingency | Total | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 26.514 | 10.449 | 70.46 | 4.306 | 1.931 | 6.28 | 119.94 | P50 Months | Start |  |  |  | 2020-01-13 | 2020-01-13
| IPA | [7 empty] | 0 |  | End |  |  |  | 2022-12-31 | 2025-01-31
| Non-IPA |  | 26.514 | 10.449 | 70.46 | 4.306 | 1.931 | 6.28 | 119.94 |  | Duration (months) | 0 | 0 | 0 | 36 | 61
| Nigeria Special | [7 empty] | 0
| Benchmarking Status | [9 empty] | Benchmarking Status
BCC BUILD UP ($ MLN) | IPA | [7 empty] | 0 | BCS | IPA
| Non-IPA |  | 23.5975 | 9.2996 | 66.937 | 3.8323 | 1.7186 | 5.5892 | 110.9742 |  | Non-IPA | [5 empty] | P10 estimate for cist
| Nigeria Special | [7 empty] | 0 |  | Nigeria Special
| Total |  | 23.5975 | 9.2996 | 66.937 | 3.8323 | 1.7186 | 5.5892 | 110.9742 |  | IPA (months)
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [8 empty] | Schedule | Duration Log
| Description | [6 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status |  | 2023-03-01 | Today
| Current Estimate | [6 empty] | 119.94 | 126.3053 |  | Remaining Duration |  |  |  | 23.4 | 23.4 |  | 2025-01-31 | LE
| Facilities Pk-1 (LEE) | [6 empty] | 4.3956 |  |  | Improve HoTT productivity; Reduced illegal work stoppage |  |  |  | -1 |  |  |  | 23.4
| Pipelines Pk-2 (MORPOL) | [6 empty] | -0.28893 |  |  | LLIs clearing - improved timeline |  |  |  | -1
| Location Preparation | [6 empty] | 0.77734 |  |  | Early release and deployment of HPHT RIG Q3 |  |  |  | -3
| Well | [6 empty] | 7.903
| Pre-FID | [6 empty] | -0.12168
| Contingency | [6 empty] | -6.3
| Total | [6 empty] | 126.3053 | 126.3053 |  | Total |  |  |  | 18.4 | 23.4
Gap to Potential Report
Note: All costs are in MOD as project is in execute and based on contracts
Formulas:
CYCLE TIME = +[EXECUTE]

## Epu Phase 2
EPU Phase 2
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | Pipeline | Remote Facilities | Location Preparation | PMT | Non-EPC | Wells | Contingency |  |  | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 63.451 | 52.9289 | 7.5907 | 16.971 | 67.142 | 115.1524 | 33.7961 |  |  | 357.0321 | P50 Months | Start |  |  |  | 2022-12-31 | 0 | 2023-03-26
| IPA | [10 empty] | 0 |  | End |  |  |  | 2026-10-30 | 2026-10-30
| Non-IPA | 2 | 56.0112 | 44.9585 |  | 16.971 | 67.142 | 115.1524 | 33.7961 |  |  | 334.0311 |  | Duration | 0 | 0 | 0 | 46 | 1524 | 43
| Nigeria Special |  | 7.4398 | 7.9705 | 7.5907 | [6 empty] | 23.001
| Benchmarking Status | 2Q | 2Q | 4Q | 2Q |  |  | 2Q | [5 empty] | Benchmarking Status |  |  |  | 4Q | 4Q
BCC BUILD UP ($ MLN) | IPA | [10 empty] | 0 | BCS | IPA
| Non-IPA | 1.9 | 56.0112 | 44.9585 |  | 14.971 | 69.142 | 109 | 22.895 |  |  | 316.9776 |  | Non-IPA
| Nigeria Special |  | 4.4398 | 4.9705 | 7.5907 | [6 empty] | 17.001 |  | Nigeria Special
| Total |  | 60.451 | 49.9289 | 7.5907 | 14.971 | 69.142 | 109 | 22.895 | 0 | 0 | 333.9786 |  | IPA |  |  |  | 31 | 31
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 357.0321 | 357.0321 |  | Remaining Duration |  |  |  | 43 | 43
| aspired to reduce brownfield execution risk for pipeline and secure 100% on IDEC | [9 empty] | -3 |  |  | Ensure restrictions to productivity are reduced to ALARP (early startup, early administration of PTW, etc.) |  |  |  | -1
| aspired to reduce brownfield execution risk for remote facilities and secure 100% on IDEC | [9 empty] | -3 |  |  | Proactive/Early NTR (Community/Security) and stakeholder management |  |  |  | -1
| Schedule acceleration | [9 empty] | -2 |  |  | Maximize weather window to complete construction in one dry season |  |  |  | -1
| Reduced PMT & travel costs by 10% | [9 empty] | -6.1524 |  |  | Ensure reduced illegal work stoppage and leverage on learnings from Enwhe/UZU project |  |  |  | -1
| Manage NTR to reduced construction downtime downtime | [9 empty] | -8.9011 |  |  | Improvement opportunities include Pre-FID funding for land acquisition, location preps & procurement of LLI’s, |  |  |  | -2
| Total | [9 empty] | 333.9786 | 357.0321 |  | Total |  |  |  | 37 | 43
Gap to Potential Report
Formulas:
CYCLE TIME = +[ASSESS]*1
CYCLE TIME = +[EXECUTE]

## ANOH
ASSA NORTH-OHAJI SOUTH PROJECT
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | Site Preparation/Field Logistics Base | Installation & Construction | Process Modules (Enerflex) | Equipment Modules | Engineering | Pipelines | Wells | CEIP | Other Costs (PMT, IM/IT, SCD, CDI, EIA) | External Community Road | Pre-FID spend | Contingency | WBS-9 | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 86 | 263 | 320 | 111 | 26 | 52 | 211 | 9 | 150 | 42 | 142 | 67 |  | 1479 | P50 Months | Start | 2011-06-06 | 2011-09-30 | 2015-03-30 | 2018-12-24 | 2011-06-06 | 2023-03-26
| IPA | 2.8 | [13 empty] | 2.8 |  | End | 2011-09-30 | 2015-03-30 | 2018-12-24 | 2025-12-30 | 2025-12-30
| Non-IPA | [14 empty] | 0 |  | Duration | 4 | 42 | 45 | 84 | 175 | 33
| Nigeria Special | [14 empty] | 0
| Benchmarking Status | [14 empty] | TQ |  | Benchmarking Status |  | BiC
BCC BUILD UP ($ MLN) | IPA | [14 empty] | 0 | BCS | IPA
| Non-IPA | [14 empty] | 0 |  | Non-IPA
| Nigeria Special | [14 empty] | 0 |  | Nigeria Special
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | IPA
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [15 empty] | Schedule | Duration Log
| Description | [13 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [13 empty] | 1479 | 1479 |  | Remaining Duration |  |  |  | 33 | 33
| Contract Negotiations outcomes | [13 empty] | -5 |  |  | NTR/contingency management |  |  |  | -3
| Commissioning support from OEMs | [13 empty] | -0.1 |  |  | Facilities construction acceleration |  |  |  | -2
| Facilities construction efficiency | [13 empty] | -12 |  |  | OEM support during commissioning |  |  |  | -2
| Pipelines construction efficiency | [13 empty] | -4
| Wells delivery efficiency | [13 empty] | -10
| Contingency optimization ( 20% of Contingency) | [13 empty] | -13.4
| Total | [13 empty] | 1434.5 | 1479 |  | Total |  |  |  | 26 | 33
Gap to Potential Report
Approval secured for a single season sampling
2021-05-21
2019-12-28
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]
Benchmarking Status = [Benchmarking Status, row above]-(17*30)

## SSAGS
SSAGS
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | PMT | Wells | CEIP | Residual Works | RPA | Contingency | WBS7 | WBS8 | WBS9 | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 12 | 81 | 52 | 3.2 | 2 | 30 |  |  |  | 180.2 | P50 Months | Start | 2009-08-01 | 2010-04-01 | 2010-12-01 | 2012-04-01 | 2009-08-01 | 2023-03-26
| IPA | [10 empty] | 0 |  | End | 2010-03-24 | 2010-12-01 | 2012-04-16 | 2026-05-30 | 2026-05-30
| Non-IPA | [10 empty] | 0 |  | Duration | 8 | 8 | 17 | 170 | 202 | 38
| Nigeria Special | [10 empty] | 0
| Benchmarking Status | [12 empty] | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | [10 empty] | 0 | BCS | IPA
| Non-IPA | [10 empty] | 0 |  | Non-IPA
| Nigeria Special | [10 empty] | 0 |  | Nigeria Special
| Total | [10 empty] | 0 |  | IPA
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 180.2 | 180.2 |  | Remaining Duration |  |  |  | 38 | 38
[14 empty] | SSAGS CEIP |  |  |  | -2 | 38
| Variations no. 104 & 105 | [9 empty] | -2 |  |  | Residual Works |  |  |  | 3 | 3
| Contingency | [9 empty] | -3 |  |  | RPA |  |  |  | -2 | 17
| Total | [9 empty] | 175.2 | 180.2 |  | Total |  |  |  | 37 | 96
Gap to Potential Reporting Template
Formulas:
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## FYIP
FYIP
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | PMT | CPF | South Bank | Odidi | Yokri FS | Pipelines -24'' | Wells | 5 Wells leak Detection | 16'' Sectional Replacement | 33 KV Subsea Cable L1 | FOT Fuel Sustainability | 12'' Dent Repair & 24'' Clamping | SSU | TOTAL (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 34.1 | 8.2 | 2.4 | 5.2 | 13.8 | 3 | 19.4 | 12 | 4.8 | 1.15 | 11.2 | 21.9 | 99 | 236.15 | P50 Months | Start | 1995-01-30 | 1996-01-28 | 2010-12-15 | 2012-04-30 | 1995-01-30 | 2023-03-26
| IPA | [14 empty] | 0 |  | End | 1996-01-28 | 2010-12-15 | 2012-04-30 | 2024-12-21 | 2024-12-21
| Non-IPA | [14 empty] | 0 |  | Duration | 12 | 179 | 17 | 152 | 359 | 21
| Nigeria Special | [14 empty] | 0
| Benchmarking Status | TQ | 2Q | 3Q | 2Q |  | 2Q |  |  |  | 2Q | 2Q | 2Q | 2Q | 2Q | 2Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | [14 empty] | 0 | BCS | IPA
| Non-IPA | [14 empty] | 0 |  | Non-IPA
| Nigeria Special | [14 empty] | 0 |  | Nigeria Special
| Total | [14 empty] | 0 |  | IPA | 16 | 16 | 16 | 19 | 67
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [15 empty] | Schedule | Duration Log
| Description | [13 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [13 empty] | 236.15 | 236.15 |  | Remaining Duration |  |  |  | 21 | 21
| 16'' Sectional Replacement | [13 empty] | 0 |  |  | 16'' Sectional Replacement |  |  |  | -0.5
| 33 KV Subsea Cable L1 | [13 empty] | 0 |  |  | 33 KV Subsea Cable L1 |  |  |  | 0
| 12'' Dent Repair & 24'' Clamping | [13 empty] | 0 |  |  | 12'' Dent Repair & 24'' Clamping |  |  |  | -0.5
| FOT Fuel Sustainability | [13 empty] | 0 |  |  | FOT Fuel Sustainability |  |  |  | 0
| SSU | [13 empty] | -1.2 |  |  | SSU |  |  |  | -1
| Total | [13 empty] | 234.95 | 236.15 |  | Total |  |  |  | 19 | 21
Gap to Potential Report
Formulas:
SELECT = [ASSESS, row below]
DEFINE = [SELECT, row below]
EXECUTE = [DEFINE, row below]
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## SSEP
TERMINALS
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | WBS1 | SSEP | Tanks | WBS4 | WBS5 | WBS6 | WBS7 | WBS8 | WBS9 | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  |  | 52 | [7 empty] | 52 | P50 Months | Start | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-12-01 | 2018-09-01 | 2023-03-26
| IPA | [10 empty] | 0 |  | End | 2018-09-16 | 2018-10-16 | 2018-11-16 | 2025-03-27 | 2025-03-27
| Non-IPA | [10 empty] | 0 |  | Duration | 0 | 1 | 3 | 76 | 79 | 24
| Nigeria Special | [10 empty] | 0
| Benchmarking Status | TQ | 2Q | 3Q | 2Q | 2Q | 2Q | 2Q | 2Q | 2Q | 2Q | 2Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | [10 empty] | 0 | BCS | IPA
| Non-IPA | [10 empty] | 0 |  | Non-IPA
| Nigeria Special | [10 empty] | 0 |  | Nigeria Special
| Total | [10 empty] | 0 |  | IPA | 16 | 16 | 16 | 19 | 67
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 52 | 52 |  | Remaining Duration |  |  |  | 24 | 24
| SSEP -Latching onto FOT CLP Contractor to complete offshore installation works | [9 empty] | -0.8 |  |  | SSEP |  |  |  | -1
| SSEP Contingency - Provisional, subject to CSRA | [9 empty] | 0
| Total | [9 empty] | 51.2 | 52 |  | Total |  |  |  | 23 | 24
Gap to Potential Report
Formulas:
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## TANK REHAB
TANK REHAB
March 2023
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | BOGT Tank 20 | BOGT Tank 18 | FOT Tank 101 | FOT Tank 207 | FOT Tank 102 | FOT Tank 901 | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 2.5 | 0.2 | 7.2 | 1.2 | 3.5 | 0.25 | 14.85 | P50 Months | Start | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-12-01 | 2018-09-01 | 2023-03-26
| IPA | [7 empty] | 0 |  | End | 2018-09-16 | 2018-10-16 | 2018-11-16 | 2024-12-27 | 2024-12-27
| Non-IPA | [7 empty] | 0 |  | Duration | 0 | 1 | 3 | 73 | 76 | 21
| Nigeria Special | [7 empty] | 0
| Benchmarking Status | TQ | 2Q | 3Q | 2Q | 2Q | 2Q | 2Q | 2Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | [7 empty] | 0 | BCS | IPA
| Non-IPA | [7 empty] | 0 |  | Non-IPA
| Nigeria Special | [7 empty] | 0 |  | Nigeria Special
| Total | [7 empty] | 0 |  | IPA | 16 | 16 | 16 | 19 | 67
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [8 empty] | Schedule | Duration Log
| Description | [6 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [6 empty] | 14.85 | 14.85 |  | Remaining Duration |  |  |  | 21 | 21
| BOGT Tank 20 | [6 empty] | 0 |  |  | BOGT Tanks -Tank 20 |  |  |  | -1
| BOGT Tanks 18 | [6 empty] | 0 |  |  | BOGT Tanks -Tank 18
| FOT Tanks-101 | [6 empty] | -0.2 |  |  | FOT Tanks -Tank 101 |  |  |  | -1
| FOT Tanks-201 (Robotic Cleaning) | [6 empty] | 0 |  |  | FOT Tanks-201 (Robotic Cleaning) |  |  |  | -1
| FOT Tank -102 | [9 empty] | FOT Tank -102
| Total | [6 empty] | 14.65 | 14.85 |  | Total |  |  |  | 18 | 21
Gap to Potential Report
Formulas:
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## CLP
CRUDE LOADING PLATFORM- CLP
Mar 2023
Legend: Color code against Benchmark
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | PMT | MOB & DDEMOB | PROC | INSTALLATION | CONTINGENCY | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 2.1 | 3 | 3 | 33 | 8 | 49.1 | P50 Months | Start | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2021-09-01 | 0 | 2023-03-26
| IPA | [6 empty] | 0 |  | End |  |  | 2021-08-01 | 2023-12-27 | 2023-12-27
| Non-IPA | [6 empty] | 0 |  | Duration | -1426 | -1427 | 33 | 28 | 1490 | 9
| Nigeria Special | [6 empty] | 0
| Benchmarking Status | TQ | 3Q | 2Q | 2Q | 2Q | 2Q | 2Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | [6 empty] | 0 | BCS | IPA
| Non-IPA | [6 empty] | 0 |  | Non-IPA
| Nigeria Special | [6 empty] | 0 |  | Nigeria Special
| Total | [6 empty] | 0 |  | IPA | 16 | 16 | 16 | 19 | 67
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [7 empty] | Schedule | Duration Log
| Description | [5 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [5 empty] | 49.1 | 49.1 |  | Remaining Duration |  |  |  | 9 | 9
| Installation | [5 empty] | -0.1 |  |  | Installation |  |  |  | -0.5
| Contingency -Provisional | [5 empty] | -0.4
| Total | [5 empty] | 48.6 | 49.1 |  | Total |  |  |  | 8.5 | 9
Gap to Potential Report
Formulas:
CYCLE TIME = +[ASSESS, row below]
CYCLE TIME = +[EXECUTE]

## SPM
SPM
March 2023
Legend: Color code against Benchmark
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | PMT | Procurement & Fabrication | Installation | Pre-com/Com & Post comp ops | Contingency | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 11 | 108 | 119 | 21 | 57 | 316 | P50 Months | Start | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2021-01-21 | 2018-09-01 | 2023-03-26
| IPA | [6 empty] | 0 |  | End |  |  | 2020-12-10 | 2026-05-27 | 2026-05-27
| Non-IPA | [6 empty] | 0 |  | Duration | -1426 | -1427 | 25 | 64 | 93 | 38
| Nigeria Special | [6 empty] | 0
| Benchmarking Status | TQ | 3Q | 2Q | 2Q | 2Q | 2Q | 2Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | [6 empty] | 0 | BCS | IPA
| Non-IPA | [6 empty] | 0 |  | Non-IPA
| Nigeria Special | [6 empty] | 0 |  | Nigeria Special
| Total | [6 empty] | 0 |  | IPA | 16 | 16 | 16 | 19 | 67
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [7 empty] | Schedule | Duration Log
| Description | [5 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [5 empty] | 316 | 316 |  | Remaining Duration |  |  |  | 38 | 38
| Proc & Fab | [5 empty] | -1 |  |  | Proc & Fab |  |  |  | -1
| Contingency -Provisional, subject to CSRA | [5 empty] | -2 |  |  | Installation |  |  |  | -1
| Total | [5 empty] | 313 | 316 |  | Total |  |  |  | 36 | 38
Gap to Potential Report
Formulas:
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]

## Otumara CEIP
AGS - OTUMARA CEIP
March 2024
Legend: Color code against Benchmark |  |  | Legend: Color code against Initiative
Best Composite Analysis
Last DG |  | DG4
WBS Element |  | UDC ($/boe) | PMT | Section 1 | Section2 | Section3 | Portacabin | WBS6 | WBS7 | WBS8 | WBS9 | Total (EDM) | WBS Element |  | ASSESS | SELECT | DEFINE | EXECUTE | CYCLE TIME
P50 EDM LE ($ mln) | Total |  | 3.9 | 2.8 | 2.3 | 6 | 2.3 |  |  |  |  | 17.3 | P50 Months | Start | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2021-09-01 | 2018-09-01 | 2023-03-26
| IPA | [10 empty] | 0 |  | End |  |  | 2021-08-01 | 2024-03-27 | 2024-03-27
| Non-IPA | [10 empty] | 0 |  | Duration | -1426 | -1427 | 33 | 31 | 67 | 12
| Nigeria Special | [10 empty] | 0
| Benchmarking Status | TQ | 2Q | 3Q | 2Q | 2Q | 2Q | 2Q | 2Q | 2Q | 2Q | 2Q |  | Benchmarking Status | 3Q | 4Q | 4Q | 3Q | 4Q
BCC BUILD UP ($ MLN) | IPA | [10 empty] | 0 | BCS | IPA
| Non-IPA | [10 empty] | 0 |  | Non-IPA
| Nigeria Special | [10 empty] | 0 |  | Nigeria Special
| Total | [10 empty] | 0 |  | IPA | 16 | 16 | 16 | 19 | 67
Gap to Potential Initiatives and Status
Cost | Estimate Change Log (EDM) | [11 empty] | Schedule | Duration Log
| Description | [9 empty] | Target | LE Status |  | Description |  |  |  | Target | LE Status
| Current Estimate | [9 empty] | 17.3 | 17.3 |  | Remaining Duration |  |  |  | 12 | 12
| OTUMARA CEIP - SECTION 1 | [9 empty] | 0 |  |  | OTUMARA CEIP - SECTION 1 |  |  |  | 0
| OTUMARA CEIP - SECTION 2 | [9 empty] | 0 |  |  | OTUMARA CEIP - SECTION 2 |  |  |  | -1
| OTUMARA CEIP - SECTION 3 | [9 empty] | -0.2 |  |  | OTUMARA CEIP - SECTION 3 |  |  |  | 0
| Total | [9 empty] | 17.1 | 17.3 |  | Total |  |  |  | 11 | 12
Gap to Potential Report
Formulas:
CYCLE TIME = +[ASSESS]
CYCLE TIME = +[EXECUTE]