## Slide 1
Business Case/objectives:
The Yokri flowstation at the Northbank Production unit has 80% of wells on Gaslift for oil production due to decline in reservoir pressure over time. The current Gaslift system at Yokri is a manual system with no automation capabilities, this is a major challenge for Gaslift optimization to maximize oil recovery from the gaslifted wells
Currently, some gaslifted wells are not producing optimally resulting to daily deferment of oil production. There is an opportunity to optimize the Yokri Gaslift system by manually measuring the Gaslift gas for each of the Gaslift wells, to determine the gas rate that maximize oil recovery from the wells. This will be executed by using gas clamp-on meters to measure Gaslift rates for the gas lift wells and use the generated data to determine the optimal gas injection rate into each of the wells.
Objective:
To maximize oil recovery from the gaslifted wells at Yokri flowstation
Asset integrated facility review – Jan 2022
IPSM Model Review – Feb 2022
Procure New Gas clamp-on meter – March 2022
Carry out MRT - April 2022
Analyze data from the MRT – May 2022
Implement actions from analyzed data – June 2022
Input High-level Timeline:
L0-L1 – Jan, 22
L2: Impacts fully identified and FCF calculated- – Feb, 22
L3: When to get approval for implementation – Mar, 22
L4: When to complete all major actions implementation – May, 22
L5: Initiative End – End 2022
Optimize Gaslift system.
Increase oil production.
Increase in daily oil production of about 500bopd.
Generate additional revenue from additional oil production to the Terminal.
  Project Sponsor: Busari Abiodun
  Implementation Lead: Akinro Tunde/Udoh Godwin
  Project Team:
Segun Adomokhai, Obot, Aniekan, Taiwo Agbaje, Barka Chiroma, Umoh Magdalene, Egodo Edward, Liberty Gesi
Potential Benefits & Measurement:
Project Milestones /Actions:
Critical Success Factors:
Project Team/Sponsor:
Project Charter: Optimize Yokri Gaslift system to unlock 500bopd by June 2022
Business Case/Objectives
High-Level Timeline: