## Drop Down (hidden)
Not started
In Progress
Delayed
On-Hold
Completed

## High Level Plan for Steerco (hidden)
ACTIVITY PLAN
| WEEK > |  |  | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29
# | Activity | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | PdM Control valve Deployment | 1 | 18 | bar: 2023-01-02 to 2023-05-01
1.1 | Agree Scope & Kickoff | 1 | 4 | bar: 2023-01-02 to 2023-01-23
1.2 | Data Gathering | 5 | 8 | bar: 2023-01-30 to 2023-02-20
1.3 | Data Loading | 9 | 12 | bar: 2023-02-27 to 2023-03-20
1.4 | No Model Scripts | 13 | 14 | bar: 2023-03-27 to 2023-04-03
1.5 | Bulk Jobs for auto models | 15 | 16 | bar: 2023-04-10 to 2023-04-17
1.6 | Model review and deployment (Hydraulic Valves) | 15 | 18 | bar: 2023-04-10 to 2023-05-01
1.7 | EBS Training | 15 | 15 | bar: 2023-04-10
2 | Model Surveillance | 19 | 22 | bar: 2023-05-08 to 2023-05-29
1 | PdM Critical Equipment Deployment | 1 | 16 | bar: 2023-01-02 to 2023-04-17
1.1 | Agree Scope and kickoff | 1 | 1 | bar: 2023-01-02
1.2 | Data Gathering | 2 | 8 | bar: 2023-01-09 to 2023-02-20
1.3 | Data Loading | 3 | 12 | bar: 2023-01-16 to 2023-03-20
1,4 | Model review and deployment (Hydraulic Valves) | 4 | 16 | bar: 2023-01-23 to 2023-04-17
1.5 | EBS Training | 15 | 15 | bar: 2023-04-10
2 | Model Surveillance | 16 | 22 | bar: 2023-04-17 to 2023-05-29

## Detailed Plan (hidden)
PROJECT: C3 PdM Deployment
Project Lead / Focal: Olakunle Ajayi
Date | 15/11/2022
ACTIVITY PLAN
WEEK > | time axis 2023-02-02 to 2023-12-28
# | Activity | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
1 | PdM Control valve Deployment | 1 | 18 | bar: 2023-02-02 to 2023-06-01
1.1 | Data Gathering | 5 | 8 | bar: 2023-03-02 to 2023-03-23
1.2 | Data Loading | 9 | 12 | bar: 2023-03-30 to 2023-04-20
1.3 | Update Prediction Targets | 13 | 14 | bar: 2023-04-27 to 2023-05-04
1.4 | Run No model scripts | 14 | 14 | bar: 2023-05-04
1.5 | Model review and deployment (50 Valves per week) 200 valves | 15 | 18 | bar: 2023-05-11 to 2023-06-01
1.5.1 | Model review and deployment : 1 to 50 | 15 | 15 | bar: 2023-05-11
1.5.2 | Model review and deployment : 50 to 100 | 16 | 16 | bar: 2023-05-18
1.5.3 | Model review and deployment : 100 to 150 | 17 | 17 | bar: 2023-05-25
1.5.4 | Model review and deployment : 150 to 200 | 18 | 18 | bar: 2023-06-01
1.6 | EBS Training | 15 | 15 | bar: 2023-05-11
2 | PdM Control valve surveillance & monitoring | 19 | 50 | bar: 2023-06-08 to 2023-12-28
1 | PdM Critical Equipment Deployment | 1 | 16 | bar: 2023-02-02 to 2023-05-18
1.1 | Agree Scope (1 equipment per week) 5 Equipments | 1 | 1 | bar: 2023-02-02
1.2 | Model Review and deployment - Equipment 1 | 2 | 4 | bar: 2023-02-09 to 2023-02-23
1.2.1 | Data Gathering | 2 | 2 | bar: 2023-02-09
1.2.2 | Data Loading | 2 | 3 | bar: 2023-02-09 to 2023-02-16
1.2.3 | Model Training, Review and live | 4 | 4 | bar: 2023-02-23
1.3 | Model Review and deployment - Equipment 2 | 5 | 7 | bar: 2023-03-02 to 2023-03-16
1.3.1 | Data Gathering | 5 | 5 | bar: 2023-03-02
1.3.2 | Data Loading | 5 | 6 | bar: 2023-03-02 to 2023-03-09
1.3.3 | Model Training, Review and live | 7 | 7 | bar: 2023-03-16
1.4 | Model Review and deployment - Equipment 3 | 8 | 10 | bar: 2023-03-23 to 2023-04-06
1.4.1 | Data Gathering | 7.9286 | 8.0238 | bar: 2023-03-23
1.4.2 | Data Loading | 8 | 9 | bar: 2023-03-23 to 2023-03-30
1.4.3 | Model Training, Review and live | 10 | 10 | bar: 2023-04-06
1.5 | Model Review and deployment - Equipment 4 | 11 | 13 | bar: 2023-04-13 to 2023-04-27
1.5.1 | Data Gathering | 11 | 11 | bar: 2023-04-13
1.5.2 | Data Loading | 11 | 12 | bar: 2023-04-13 to 2023-04-20
1.5.3 | Model Training, Review and live | 13 | 13 | bar: 2023-04-27
1.6 | Model Review and deployment - Equipment 5 | 14 | 16 | bar: 2023-05-04 to 2023-05-18
1.6.1 | Data Gathering | 14 | 14 | bar: 2023-05-04
1.6.2 | Data Loading | 14 | 15 | bar: 2023-05-04 to 2023-05-11
1.6.3 | Model Training, Review and live | 16 | 16 | bar: 2023-05-18
1.7 | EBS Training | 5 | 5
2 | PdM Critical Equipment surveillance & monitoring | 17 | 50 | bar: 2023-05-25 to 2023-12-28
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | [6 empty] | 35 | [5 empty] | 36 | 37

## CV Phase II Plan (hidden)
Description | Week 1 (Oct 17-21) | Week 2 (Oct 24-28) | Week 3 (Oct 31- Nov4) | Week 4 (Nov7-11) | Week 5 (Nov 14-18) | Week 6 (Nov 21-25) | Week 7 (Nov 28-Dec 02) | Week 8 (Dec 5-Dec-9) | Week 9 (Dec 12-16) | Week 10 (Dec19-23)
Modelling Scope | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
New Live tags | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Surveillance scope | (40 Hyd+75CV ) 90 | 140 | 190 | 240 | 290 | 340 | 390 | 440 | 490 | 540

## Detailed Plan-Old (hidden)
PROJECT: C3 PdM Deployment for Pearl GTL
Project Manager: Vinay Kumar
Date | 31/05/2022
ACTIVITY PLAN
| WEEK > |  |  | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26
# | Activity | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
1 | PdM Control valve Deployment | 1 | 39 | bar: 2022-04-04 to 2022-12-26
1.1 | Agree Scope for Phase-1 (Total Hydraulic Valves - 376) | 1 | 7 | bar: 2022-04-04 to 2022-05-16
1.2 | Data Gathering | 5 | 13 | bar: 2022-05-02 to 2022-06-27
1.3 | Data Loading | 5 | 12 | bar: 2022-05-02 to 2022-06-20
1.4 | Update Prediction Targets | 13 | 14 | bar: 2022-06-27 to 2022-07-04
1.5 | Finalise the modulating hydaulic valves | 14 | 14 | bar: 2022-07-04
1.6 | Model review and deployment (Modulating Hydralic valves - 25 valves) | 15 | 18 | bar: 2022-07-11 to 2022-08-01
1.6.1 | Model review and deployment : 1 to 6 | 15 | 15 | bar: 2022-07-11
1.6.2 | Model review and deployment : 7 to 12 | 16 | 16 | bar: 2022-07-18
1.6.3 | Model review and deployment : 13 to 18 | 17 | 17 | bar: 2022-07-25
1.6.4 | Model review and deployment : 19 to 25 | 18 | 18 | bar: 2022-08-01
1.7 | EBS Training | 7 | 7 | bar: 2022-05-16
1.7 | Model Surveillance | 1 | 39 | bar: 2022-04-04 to 2022-12-26
1.8 | Agree Scope for Phase-2 (Other valves Approx 4000) | 18 | 18 | bar: 2022-08-01
1.9 | Update Prediction Targets
2 | No model possible scripts
3 | Model review and deployment
2 | PdM Critical Equipment Deployment | 1 | 39 | bar: 2022-04-04 to 2022-12-26
2.1 | Agree Scope for Phase-1 (DGS Models) | 5 | 7 | bar: 2022-05-02 to 2022-05-16
2.2 | Data Gathering | 8 | 10 | bar: 2022-05-23 to 2022-06-06
2.3 | Data Loading | 9 | 12 | bar: 2022-05-30 to 2022-06-20
2.4 | Model Review and deployment (DSG Models) | 10 | 21 | bar: 2022-06-06 to 2022-08-22
2.4.1 | Model review and deployment : 1K-3041 | 10 | 11 | bar: 2022-06-06 to 2022-06-13
2.4.2 | Model review and deployment : 2K-3041 | 12 | 13 | bar: 2022-06-20 to 2022-06-27
2.4.3 | Model review and deployment : 1K-3141 | 14 | 15 | bar: 2022-07-04 to 2022-07-11
2.4.4 | Model review and deployment : 2K-3141 | 16 | 17 | bar: 2022-07-18 to 2022-07-25
2.4.5 | Model review and deployment : 1K-3001 & 2K-3001 | 18 | 19 | bar: 2022-08-01 to 2022-08-08
2.5 | EBS Training | 20 | 20 | bar: 2022-08-15
2.5 | Model Surveillance | 15 | 39 | bar: 2022-07-11 to 2022-12-26
2.6 | Agree scope for Phase 2 (Anamoly Detection Models) | 14 | 15 | bar: 2022-07-04 to 2022-07-11
2.7 | Model Review and deployment (Anamoly Detection Models) | 20 | 39 | bar: 2022-08-15 to 2022-12-26
2.6.1 | Data gathering | 20 | 20 | bar: 2022-08-29
2.6.2 | Data Loading | 20 | 20 | bar: 2022-08-29
2.6.3 | Model Deployment : 1K-0781 | 21 | 21 | bar: 2022-09-05
2.6.4 | Data gathering | 22 | 22 | bar: 2022-09-05 to 2022-09-12
2.6.5 | Data Loading | 22 | 22 | bar: 2022-09-05 to 2022-09-12
2.6.6 | Model Deployment :1KT-5181, 1K-5181 I stage,1K-5181 II stage | 23 | 23 | bar: 2022-09-19
2.6.7 | Data gathering | 24 | 24 | bar: 2022-09-12
2.6.8 | Data Loading | 24 | 24 | bar: 2022-09-12
2.6.9 | Model Deployment : 1K-4101 , 1KG-4101 | 25 | 25 | bar: 2022-09-19
2.6.10 | Data gathering | 26 | 26 | bar: 2022-09-12
2.6.11 | Data Loading | 26 | 26 | bar: 2022-09-12
2.6.12 | Model Deployment : 2K-5181 (2K-5181 I stage, 2K-5181 II stage) | 27 | 27 | bar: 2022-09-19
2.6.13 | Data gathering | 28 | 28 | bar: 2022-09-26
2.6.14 | Data Loading | 28 | 28 | bar: 2022-09-26
2.6.15 | Model Deployment : 2K-4001 , 2KG-4001 | 29 | 29 | bar: 2022-10-03
2.6.16 | Data gathering | 30 | 30 | bar: 2022-10-10
2.6.17 | Data Loading | 30 | 30 | bar: 2022-10-10
2.6.18 | Model Deployment : 2P-4001 | 31 | 31 | bar: 2022-10-17
2.6.19 | Data gathering | 31 | 31 | bar: 2022-10-24
2.6.20 | Data Loading | 32 | 32 | bar: 2022-10-24
2.6.21 | Model Deployment : 2KT-2311 | 33 | 33 | bar: 2022-10-31
2.6.22 | Data gathering | 34 | 34 | bar: 2022-11-07
2.6.23 | Data Loading | 34 | 34 | bar: 2022-11-07
2.6.24 | Model Deployment :2K-2312 | 35 | 35 | bar: 2022-11-14
2.6.25 | Data gathering | 36 | 36 | bar: 2022-11-21
2.6.26 | Data Loading | 36 | 36 | bar: 2022-11-21
2.6.27 | Model Deployment : 2KT-2411 | 37 | 37 | bar: 2022-11-28
2.6.28 | Data gathering | 38 | 38 | bar: 2022-12-05
2.6.29 | Data Loading | 38 | 38 | bar: 2022-12-05
2.6.30 | Model Deployment : GTG Power throughput | 39 | 39 | bar: 2022-12-12
2.7 | Model Review and deployment - Anamoly dectction models for K3041, K3141 and K3001 (if required)
2.7.1 | Data gathering
2.7.2 | Data Loading
2.7.3 | Model review and deployment : 1K-3041 & 2K-3041
2.7.4 | Data gathering
2.7.5 | Data Loading
2.7.6 | Model review and deployment : 1K-3141 & 3K-3141
2.7.7 | Data gathering
2.7.8 | Data Loading
2.7.9 | Model review and deployment : 1K-3001 & 2K-3001
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39

## CE LIVE List (hidden)
CE GO-LIVE TRACKER
S.NO. | Asset | Equipment Name | Go Live Date | Remarks
1 | Soku | LP NAG | 2023-05-01
2 | Soku | AGC2 | 2023-05-01
3 | Soku | GTG ( G-8101) | 2023-05-01 | Speed tags required
4 | Soku | GTG ( G-8111) | 2023-05-01 | Speed tags required
5 | Soku | GTG ( G-8121) | 2023-05-01 | Speed tags required
6 | EA | FGC | 2023-05-01 | Speed tags not required, Discharge pressure to be taken SSC
7 | EA | EGC | 2023-05-01 | Speed tags not required, Discharge pressure to be taken SSC
8 | EA | GTG1 | 2023-04-01
9 | EA | GTG2 | 2023-04-01
10 | EA | GTG3 | 2023-04-01
11 | EA | GTG4 | 2023-04-01
12 | EA | GTG5 | 2023-04-01
13 | TUNU | AGC1 | 2023-07-01 | PdA template is uploaded
14 | TUNU | AGC2 | 2023-07-01
15 | TUNU | EGC1 | 2023-07-01
16 | TUNU | EGC2 | 2023-07-01
17 | TUNU | GTG1 | 2023-07-01
18 | TUNU | GTG2 | 2023-07-01
19 | TUNU | GTG3 | 2023-07-01

## PDA Progress
Critical Rotating Equipement PdA |  | Control Valves PdA
Task
Preparation / Kick-off
Pre requiste activities |  | Preparation / Kick-off
Pre requiste activities
Access
Tool access to all stakeholders |  | Access
Tool access to all stakeholders
Gather data
Deliver good quality data, and good failure cases |  | Gather data
Deliver good quality data, and good failure cases
Data Load
Load required data in to C3 for modelling
Data Load
Load required data in to C3 for modelling
Model Training and Review
Model Training and Review
Review anomaly detection
Sign-off from SME that model is identifying anomalies
Review anomaly detection
Sign-off from SME that model is identifying anomalies
Training & product handover
Training to handlover model training and review
Training & Handover
Training to handover model training and review
| Current Week Performance |  |  |  |  | Next Week Target |  |  |  | Challenges
| PDA Models Deployment | Tunu | SOKU | EA | Overall | Tunu | SOKU | EA | Overall | SOKU & EA: Data loading for EA and SOKU is expected to have a delay from the proposed time because of request pending from SSIP.
| Control Valves & Transmitters | 47.8% | 33.8% | 26.85% | 37.02% | 52.8% | 38.8% | 31.85% | 42.02%
| Critical Rotating Equipment | 66% | 65.6% | 72% | 67.87% | 69% | 68.6% | 75% | 70.87%
| Control Valves & Transmitters |  |  |  |  | Tunu: *103 trained models review- to be completed by 29/5/2023, SOKU & EA: *Data loading for EA and SOKU In progress.
Tunu:Provided Tunu P&ID is expected to take surveillance and modelling time consuming as the P&ID is not provided tag wise. SOKU & EA:Data loading for EA and SOKU In progress. Tunu Asset: * 53 Auto live model review completed,
Critical Rotating Equipment
| 1) TUNU: * Data loading on C3.AI completed. 2) SOKU: * LP NAG Compressor Live on C3. *External validation of AG2 Dry Seals 2nos. TCA models completed 3) EA: *EGC & FGC (compressors) Models Training on going. |  |  |  |  | 1) TUNU: *Data Quality tcheck and validation * 2) SOKU: *External Validation of 2 Dry Seals TCA model completed 3) EA: *data loading completed, GTG models deployed, EGC & FGC to be deployed
Last Week
| PDA Models Deployment | Tunu | SOKU | EA | Overall
| Control Valves & Transmitters | 47.8% | 33.8% | 26.85% | 37.02%
| Critical Rotating Equipment | 66% | 65.6% | 72% | 67.87%
Note on E46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Team @ , Please the % completion of YTD performance is auto update. Make all entires in CV & CE Sheet
Note on I51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hello Team, Please make all your entries here. we will review during the weekly calls.

## CV
Control Valve & Transmitters Predictive Analytics (Jan - Dec 2023)
sn | Task | Description | Primary Focal | Supported | Tunu Status | Soku Status | EA Status | Aggregate Status - Plan | Aggregate Status - Actual | Comment | Status Update | Deliverable | Expected Data of Completion- Tunu | Expected Data of Completion- Soku | Expected Data of Completion- EA
1 | Preparation / Kick-off |  |  |  | 100% | 100% | 100% |  | 100%
| Pre requiste activities | Confirm resource availability | PDL / AF |  | 100% | 100% | 100% |  | 100% |  |  | Resource list | Jan - Feb | Jan - Feb | Jan - Feb
|  | Capability Assessment of resource persons | PDL / AF |  | 100% | 100% | 100% |  | 100% |  |  | RACI
|  | Determine Asset Readiness/Resources | PDL / AF |  | 100% | 100% | 100% |  | 100% |  |  | RACI
|  | Define scope | PDL / AF |  | 100% | 100% | 100% |  | 100% |  |  | List of CVs with tag names
|  | Communication, stakeholder alignments | PDL / AF |  | 100% | 100% | 100% |  | 100% |  |  | Meeting minutes
|  | IRM Assesment to load data in C3 | PDL |  | 100% | 100% | 100% |  | 100% |  |  | IRM sign off e-mail
2 | Access |  |  |  | 100% | 100% | 100% |  | 100%
| Tool access to all stakeholders | List of users need access to C3 tool | AF |  | 100% | 100% | 100% |  | 100% | Acess granted |  | user list | 2023-01-15 | 2023-01-15 | 2023-01-15
|  | Provide required access to C3 tool | PDL |  | 100% | 100% | 100% |  | 100% |  |  | SNOW Request | 2023-01-15 | 2023-01-15 | 2023-01-15
|  | Provide acess to PDM TAO for local PI Server and SeeQ | AIDT | AIDT | 100% | 100% | 100% |  | 100% |  |  | Access confirmation | 2023-01-15 | 2023-01-15 | 2023-01-15
3 | Gather data |  |  |  | 75% | 62.5% | 25% |  | 54.17%
| Deliver good quality data, and good failure cases | Provided Tags list for agreed Control valves | APT | AIDT | NA | 100% | 100% |  | 100% | List of tag names for control valve | Tunu CV not in scope | csv files | 2023-01-31 | 2023-04-15 | 2023-04-15
|  | Provided Tags list for agreed Transmitter |  |  | 100% | 100% | 100% |  | 100% | List of tag names for Transmitter for SOKU and EA |  |  | 2023-01-31 | 2023-04-16 | 2023-04-16
|  | Provide P& ID's for all Transmitter |  |  | 100% | 50% | 0% |  | 50% | P&ID for all Transmitters | Sahl(16/5/23):Provided Tunu P&ID is expected to take surveillance and modelling time consuming as the P&ID is not provided tag wise
|  | Provide P& ID's for all control valves | AF | AFO | NA | 50% | 0% |  | 25% | P&ID for all CV |  | P&ID's | 2023-01-31 | 2023-01-31 | 2023-01-31
|  | Provide Datasheets for control valve and transmitter | AF | AFO | 50% | 50% | 0% |  | 33.33% | Datasheets for control valve and transmitter |  | csv files | 2023-02-07 | 2023-02-07 | 2023-02-07
|  | Examine all the information provided (tag list, P&ID's, Limits, etc..) | PINS | APT | 50% | 50% | 0% |  | 33.33% |  |  |  | 2023-02-07 | 2023-02-07 | 2023-02-07
4 | Data Load |  |  |  | 100% | 66.67% | 66.67% |  | 77.78%
| Load required data in to C3 for modelling | Create AF Hierachy | PDE | AIDT | 100% | 100% | 100% |  | 100% |  |  |  | 2023-01-20 | 2023-04-25 | 2023-04-25
|  | Load all tags / data in to C3 | PDE / PDS | AIDT | 100% | 50% | 50% |  | 66.67% |  | Sahl (16/5/2023):Data loading for EA and SOKU is expected to have a delay from the proposed time because of request pending from SSIP. New timeline will be mentioned by the end of the week |  | 2023-01-27 | 2023-05-22 | 2023-05-22
|  | Data Quality / availability Checks | PDE / PDS | AIDT | 100% | 50% | 50% |  | 66.67% |  | Sahl(16/5/23):Tunu Asset:53 Auto live model review completed, 103 models trained which will be reviewed unit wise will be completed by 29/5/2023, 17 models NMP. | Model reviewing requires individual modelling which requires different iterations for single Model, Expected to complete the model reviewing within the specified dates | 2023-02-03 | 2023-05-29 | 2023-05-29
5 | Model Training and Review |  |  |  | 70% | 0% | 0%
|  | Run no model scripts for control valve | PDS | AIDT / ADS | 100% | 0% | 0% |  | 33.33% |  |  | Report | 2023-03-31 | 2023-05-25 | 2023-05-25
|  | Run bulk jobs for auto live models | PDS | AIDT / ADS | 100% | 0% | 0% |  | 33.33% |  |  | Report | 2023-03-31 | 2023-05-29 | 2023-05-29
|  | Working Sessions - Model Trainign, Bulk Jobs, Model Review | PINS / PDS / AF | AIDT / ADS / All | 50% | 0% | 0% |  | 16.67% |  |  | Meeting minutes | 2023-05-30 | 2023-07-03 | 2023-07-03
|  | Perform Model review and training for remaining valves | PINS / AF | AIDT / ADS | 50% | 0% | 0% |  | 16.67% |  |  |  | 2023-06-05 | 2023-07-17 | 2023-07-17
|  | Make models live | PINS / AF | AIDT / ADS | 50% | 0% | 0% |  | 16.67% |  |  |  | 2023-06-30 | 2023-07-29 | 2023-07-29
6 | Review anomaly detection |  |  |  | 0% | 0% | 0% |  | 0%
| Sign-off from SME that model is identifying anomalies | Integrate C3 Alerts in to EBS and setup email alert system | PDL |  | 0% | 0% | 0% |  | 0% |  |  |  | 2023-07-18 | 2023-08-18 | 2023-08-18
|  | Training sessions for Assets focal and Survielance team | Nikki |  | 0% | 0% | 0% |  | 0% |  |  |  | 2023-07-18 | 2023-08-18 | 2023-08-18
|  | Provide list of users need access to EBS | AF |  | 0% | 0% | 0% |  | 0% |  |  |  | 2023-07-18 | 2023-08-18 | 2023-08-18
|  | Provide access to all users | PDL |  | 0% | 0% | 0% |  | 0% |  |  |  | 2023-07-18 | 2023-08-18 | 2023-08-18
|  | Evaluate detected analomalies from EBS | PINS / AF | APTME | 0% | 0% | 0% |  | 0% |  |  |  | 2023-07-18 | 2023-08-18 | 2023-08-18
|  | Perform root cause analysis | PINS / AF | APTME | 0% | 0% | 0% |  | 0% |  |  |  | 2023-07-18 | 2023-08-18 | 2023-08-18
7 | Training & Handover |  |  |  | 0% | 0% | 0% |  | 0%
| Training to handover model training and review | Provide EBS training | Nikki | APTME / All | 0% | 0% | 0% |  | 0% |  |  |  | Aug
|  | Share all recordings and user guides | Nikki | AF | 0% | 0% | 0% |  | 0%
|  | Perform model training and review for some of the valves | ADS / AIDT | PINS | 0% | 0% | 0% |  | 0%
|  | Prepare check list for Product support team (local data scientist/ Local C3 IT team) | PINS / PDS / AF | ADS / AIDT | 0% | 0% | 0% |  | 0%
|  | Prepare and implement Surveilance model for PDM | APTME | AINS | 0% | 0% | 0% |  | 0%
|  |  |  | Overall | 47.8% | 33.8% | 26.85% |  | 37.02%

## CE
CE Predictive Analytics (Jan - Dec 2023)
sn | Task | Description | Team/Role | Supported | Tunu Status | Soku Status | EA Status | Aggregate Status - Plan | Aggregate Status - Actual | Comment | Deliverable | Expected Data of Completion- Tunu | Expected Data of Completion- Soku | Expected Data of Completion- EA
1 | Preparation / Kick-off |  |  |  | 100% | 100% | 100% | 100% | 100%
| Pre requiste activities | Confirm resource availability | PDL / AF |  | 100% | 100% | 100% | 100% | 100% |  | Resource list | Jan - Feb | Jan - Feb | Jan - Feb
|  | Capability Assessment of resource persons | PDL / AF |  | 100% | 100% | 100% | 100% | 100% |  | RACI
|  | Determine Asset Readiness/Resources | AF |  | 100% | 100% | 100% | 100% | 100% |  | RACI
|  | Define scope | PDL / AF |  | 100% | 100% | 100% | 100% | 100% |  | Populated REQ template
|  | Communication, stakeholder alignments | PDL / AF |  | 100% | 100% | 100% | 100% | 100% |  | Meeting minutes
|  | IRM Assesment to load data in C3 | PDL |  | 100% | 100% | 100% | 100% | 100% |  | IRM sign off e-mail
2 | Access |  |  |  | 100% | 100% | 100% |  | 100%
| Tool access to all stakeholders | List of users need access to C3 tool | AF |  | 100% | 100% | 100% | 100% | 100% |  | Knowledge | 2023-01-15 | 2023-01-15 | 2023-01-15
|  | Provide required access to C3 tool | PDL |  | 100% | 100% | 100% | 100% | 100% |  | Knowledge | 2023-01-15 | 2023-01-15 | 2023-01-15
|  | Provide acess to PDM TAO for local PI Server | AIDT |  | 100% | 100% | 100% | 100% | 100% |  | Knowledge | 2023-01-15 | 2023-01-15 | 2023-01-15
3 | Gather data |  |  |  | 100% | 80% | 100% | 100% | 93.33%
| Deliver good quality data, and good failure cases | Provided Tags list for agreed Critical Equipment | AF | AFO/APT/ARET | 100% | 100% | 100% | 100% | 100% | SOKU: Models to started in Oct-2023 for GTGs, Power output to be used as SS tag | Populated REQ template | 2023-01-19 | 2023-01-19 | 2023-01-19
|  | Provide process book displays and P& ID's for all equipments | AF/AIDT | AFO/APT/ARET | 100% | 0% | 100% | 100% | 66.67% | EA: P&ID Outstanding for GTG | Populated REQ template | 2023-01-20 | 2023-01-20 | 2023-01-20
|  | Provide UTL links for operating limits | AF/FO | AFO/APT/ARET | 100% | 100% | 100% | 100% | 100% |  | Populated REQ template | 2023-01-21 | 2023-01-21 | 2023-01-21
|  | provide all shutdown and failure events | AF/AGE | AFO/APT/ARET | 100% | 100% | 100% | 100% | 100% | SOKU: Models to started in Oct-2023 for GTGs, Power output to be used as SS tag TUNU: GTGs data not available | Populated REQ template | 2023-01-22 | 2023-01-22 | 2023-01-22
|  | Examine all the information provided (tag list, P&ID's, Limits, etc..) | PREQ | AFO/APT/ARET | 100% | 100% | 100% | 100% | 100% |  | Populated REQ template | 2023-01-23 | 2023-01-23 | 2023-01-23
4 | Data Load |  |  |  | 83.33% | 80% | 83.33% | 100% | 82.22%
| Load required data in to C3 for modelling | Create AF Hierachy | PDE | AIDT/ADS | 100% | 80% | 100% | 100% | 93.33% | TUNU: data loading completed, quality to be checked while deployment SOKU: NAG & AG2 Models developed internal validation to be done, Models to start in Oct-2023 for GTGs EA: data loading completed, GTG models deployed, EGC & FGC to be deployed | Document | 2023-04-20 | 2023-06-15 | 2023-01-20
|  | Load all tags / data in to C3 | PDE / PDS | AIDT/ADS | 100% | 80% | 100% | 100% | 93.33% |  | data | 2023-04-30 | 2023-06-03 | 2023-01-27
|  | Data Quality / availability Checks | PDE / PDS | AIDT/ADS | 50% | 80% | 50% | 100% | 60% |  | data | 2023-07-01 | 2023-07-01 | 2023-07-13
5 | Model Training and Review |  |  |  | 0% | 33.33% | 50% |  | 27.78%
|  | Working Sessions - Model Training and Model Review | PREQ / PDS / AF | AIDT/ADS | 0% | 50% | 50% | 100% | 33.33% | EA: GTG Completed/ FGC,EGS Outstanding SOKU: NAG & AG2 under progress |  | 2023-06-24 | 2023-06-24 | 2023-06-24
|  | Perform Model review and training for all equipments | PREQ / AF | AIDT/ADS | 0% | 50% | 50% | 100% | 33.33% | EA: GTG Completed/ FGC,EGS Outstanding SOKU: NAG & AG2 under progress | Code | 2023-06-07 | 2023-07-07 | 2023-07-07
|  | Make models live | PREQ / AF | AIDT/ADS | 0% | 0% | 50% | 100% | 16.67% | EA: GTGs live/ FGC,EGS Outstanding | List of anomalies | 2023-07-01 | 2023-07-01 | 2023-07-15
6 | Review anomaly detection |  |  |  | 0% | 0% | 0% |  | 0%
| Sign-off from SME that model is identifying anomalies | Integrate C3 Alerts in to EBS and setup email alert system | PDL | AIDT/ADS | 0% | 0% | 0% | 100% | 0% |  | Document | 2023-07-19 | 2023-07-19 | 2023-07-19
|  | Training sessions for Assets focal and Survielance team | PDL | AIDT/ADS | 0% | 0% | 0% | 100% | 0% |  |  | 2023-07-19 | 2023-07-19 | 2023-07-19
|  | Provide access to all users | PDL | APTME | 0% | 0% | 0% | 100% | 0% |  | Document | 2023-07-19 | 2023-07-19 | 2023-07-19
|  | Evaluate detected analomalies from EBS | PREQ / AF | APTME | 0% | 0% | 0% | 100% | 0% |  |  | April - Dec | April - Dec | April - Dec
|  | Perform root cause analysis | PREQ / AF | APTME | 0% | 0% | 0% | 100% | 0% |  |  | April - Dec | April - Dec | April - Dec
7 | Training & product handover |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0!
| Training to handlover model training and review | Retrian models if required | ADS / AIDT | PREQ |  |  |  | 100% |  |  |  | May - Dec | May - Dec | May - Dec
|  | Continue Surveilance, prepare and implement surveillance model for PDM | APTME | AINS |  |  |  | 100% |  |  |  | June - Dec | June - Dec | June - Dec
|  | Average Performance |  | Overall | 66% | 65.6% | 72% | 100% | 67.87%

## Team Members (hidden)
Role |  | Name | Email ID | Status
AF | Asset Focal | Ajayi, Olakunle J SPDC-UPC/G/USR - SPDC Orjiakor, Charles SPDC-UPC/G/USMP - SOKU Henshaw, Gideon SPDC-UPC/G/USMR - Tunu Uche, Ugochukwu S SPDC-UPC/G/USM - EA | olakunle.ajayi@shell.com C.Orjiakor@shell.com G.Henshaw@shell.com Ugochukwu.Uche@shell.com | In -progress
AREE | Asset Rotating Equipment Engineer - Rotating Equipment Focal | Odunze, Kenechukwu A SPDC-UPC/G/USM Idio, Samuel N SPDC-PTP/O/NE Sanni, Esireyewun SPDC-UPC/G/USMR Digbani, Tamunofiri M SPDC-UPC/G/USMR | Kenechukwu.Odunze@shell.com Samuel.Idio@shell.com E.Sanni@shell.com tamuno.digbani@shell.com | Not started
APT | Asset PACO TA - Control valve Focal | Awe, Afolabi T SPDC-UPC/G/USM | Afolabi.Awe@shell.com | Completed
APTME | Asset Proactive Technical Montioring Eng | Ajayi, Olakunle J SPDC-UPC/G/USR Orjiakor, Charles SPDC-UPC/G/USMP Henshaw, Gideon SPDC-UPC/G/USMR Uche, Ugochukwu S SPDC-UPC/G/USM | olakunle.ajayi@shell.com C.Orjiakor@shell.com G.Henshaw@shell.com Ugochukwu.Uche@shell.com | On Hold
ADE / AIDT | Asset Data Engineer /Asset Information Technology | Ariyo, Oluwatoyin A SNBO-PTIZ/C/ND Egwu, Emmanuel O SPDC-PTIZ/C/N Enyinnaya, Ikedichi C SPDC-PTIZ/C/NA | O.Ariyo@shell.com Emmanuel.Egwu@shell.com ikedichi.enyinnaya@shell.com | Delayed
ADS | Asset Data Scientist | Saka, Adesina M SPDC-PTIZ/C/NS Omoko, Nonso SPDC-PTIZ/C/NS Ajayi, Olakunle J SPDC-UPC/G/USR | adesina.saka@shell.com nonso.omoko@shell.com olakunle.ajayi@shell.com
AREL | Asset Reliability Engineer | Okwuosa, Uju C SPDC-UPC/G/USR Etire Azibanato | Uju.Okwuosa@shell.com Azibanato.Etire@shell.com
APE | Asset Process Engineer
EA AFO |  | Umoh, Ubong Oborokumo, Ebiegberi Reuben, Kitoye M | Ubong.Umoh@shell.com Ebiegberi.Oborokumo@shell.com Kitoye.Reuben@shell.com
TUNU AFO |  | Obi, Emmanuel Amraibure, Ochuko Oni, Andrew Igbinidun, Abigail Timiala, Kharis > | Emmanuel.Obi@shell.com ochuko.amraibure@shell.com andrews.oni@shell.com Abigail.Igbinidun@shell.com Kharis.Timiala@shell.com
SOKU AFO | Asset Field Operations | Nsikak Ekpoh Theresa Abdulmalik Sani Mukhtar Noble Uranta Lukmon Adesina Onyenagbagha Shodipo Ibrahim Olusye Phillips | nsikak.ekpoh@shell.com T.Abdulmalik@shell.com Mukhtar.Sani@shell.com noble.uranta@shell.com Lukmon.Adesina@shell.com a.onyenagbagha@shell.com oladimeji.shodipo@shell.com oluseye.phillips@shell.com
AEE | Asset Electrical Engineer | Onumadu, Chibuzo S SPDC-UPC/G/USM Osaigbovo, Diana R SPDC-UPC/G/USMD | Chibuzo.Onumadu@shell.com Diana.Osaigbovo@shell.com
PINS | Predictive Maintanance TAO Instrumentation Engineer | Sahl, Mohammed SSSCCH-PTS/TMW | Mohammed.Sahl@shell.com
PREQ | Predictive Maintanance TAO Rotating Equipment Engineer | Behera, Soumya R SSSCCH-PTS/TMI | Soumya.Behera@shell.com
PDS | Predictive Maintanance Data Scientist | Sudhakar, Sidarth SSSCCH-PTIY/FHC Mishra, Atul SSSCCH-PTIY/FHC | S.Sudhakar@shell.com Atul.Mishra@shell.com
PDE | Predictive Maintanance Data Engineer | Ranjan, Ashish SBOBNG-PTIY/FHC Farrant, Colin SITI-PTIY/FHC | A.Ranjan2@shell.com Colin.Farrant2@shell.com
PDL | Predictive Maintanance Deployment Lead | Ravi, Gopi SBOBNG-PTIZ/T/M | Gopi.G.Ravi@shell.com
PPLM | Predictive Maintanance Product Line Manager | Blake, Richard J GSNL-PTIZ/T/M | Richard.Blake@shell.com
PPO | Predictive Maintanance Product Owner | Burrell, Susan GSUK-PTS/IG Melendez, Jorge L GSUSI-PTS/IG | Susan.Burrell@shell.com Jorge.Melendez@shell.com
PBDO | Predictive Maintenance BOM/Deployment Owner | Ofori, Kebin M SPDC-UPC/G/US | kebin.ofori@shell.com

## CV LIVE List
CV GO-LIVE TRACKER
S.NO. | Valve Name / Number | Go Live Date | Remarks
Phase II Scope
98 | QSGTL_111FC21010.PIDA.OP | 2022-10-21
99 | QSGTL_112FC10003.PIDA.OP | 2022-10-21
100 | QSGTL_112FC21005.PIDA.OP | 2022-10-21
101 | QSGTL_112FC22005.PIDA.OP | 2022-10-21
102 | QSGTL_112FC22008.PIDA.OP | 2022-10-21
103 | QSGTL_111PC37003.PIDA.OP | 2022-10-21
104 | QSGTL_111FC37003.PIDA.OP | 2022-10-21
105 | QSGTL_111FC35014.PIDA.OP | 2022-10-21
106 | QSGTL_111FC32003.PIDA.OP | 2022-10-21
107 | QSGTL_111PC35008B.PIDA.OP | 2022-10-21
108 | QSGTL_131FC23002.PIDA.OP | 2022-10-21
109 | QSGTL_111FC36006.PIDA.OP | 2022-10-21
110 | QSGTL_111PC33008B.PIDA.OP | 2022-10-21
111 | QSGTL_130FC37001.PIDA.OP | 2022-10-21
112 | QSGTL_111LC36005.PIDA.OP | 2022-10-21
113 | QSGTL_111PC35003.PIDA.OP | 2022-10-28
114 | QSGTL_111PC31008B.PIDA.OP | 2022-10-28
115 | QSGTL_111PC32008B.PIDA.OP | 2022-10-28
116 | QSGTL_111PC34008B.PIDA.OP | 2022-10-28
117 | QSGTL_111FC39003.PIDA.OP | 2022-10-28
118 | QSGTL_111FC32006.PIDA.OP | 2022-10-28
119 | QSGTL_112FC22003.PIDA.OP | 2022-10-28
120 | QSGTL_131PC10153.PIDA.OP | 2022-10-28
121 | QSGTL_111FC22603.PIDA.OP | 2022-10-28
122 | QSGTL_111FC37014.PIDA.OP | 2022-10-28
123 | QSGTL_111FC32014.PIDA.OP | 2022-10-28
124 | QSGTL_111FC21603.PIDA.OP | 2022-10-28
125 | QSGTL_130FC10014B.AUTOMANA.OP | 2022-10-28
126 | QSGTL_111FC21601.PIDA.OP | 2022-10-28
127 | QSGTL_130FC34010.PIDA.OP | 2022-10-28
128 | QSGTL_185TC10003.PIDA.OP | 2022-11-04
129 | QSGTL_130FC38001.PIDA.OP | 2022-11-04
130 | QSGTL_111PC10163.PIDA.OP | 2022-11-04
131 | QSGTL_112FC21002.PIDA.OP | 2022-11-04
132 | QSGTL_130FC35001.PIDA.OP | 2022-11-04
133 | QSGTL_131LC10007.PIDA.OP | 2022-11-04
134 | QSGTL_130FC38006.PIDA.OP | 2022-11-04
135 | QSGTL_131FC21001.PIDA.OP | 2022-11-04
136 | QSGTL_130FC35003.PIDA.OP | 2022-11-04
137 | QSGTL_130FC39001.PIDA.OP | 2022-11-04
138 | QSGTL_130TC10595.PIDA.OP | 2022-11-04
139 | QSGTL_111FC35003.PIDA.OP | 2022-11-04
140 | QSGTL_131LC21003.PIDA.OP | 2022-11-04
141 | QSGTL_184FC10003.PIDA.OP | 2022-11-04
142 | QSGTL_130FC38010.PIDA.OP | 2022-11-04
143 | QSGTL_130FC33001.PIDA.OP | 2022-11-04
144 | QSGTL_131FC10001.PIDA.OP | 2022-11-04
145 | QSGTL_111PC36008B.PIDA.OP | 2022-11-04
146 | QSGTL_184TC10020.PIDA.OP | 2022-11-04
147 | QSGTL_130FC31003.PIDA.OP | 2022-11-04
148 | QSGTL_130FC36010.PIDA.OP | 2022-11-04
149 | QSGTL_131FC22002.PIDA.OP | 2022-11-04
150 | QSGTL_130FC39006.PIDA.OP | 2022-11-04
151 | QSGTL_131FC23010.PIDA.OP | 2022-11-04
152 | QSGTL_130FC31001.PIDA.OP | 2022-11-04
153 | QSGTL_184FC10005.PIDA.OP | 2022-11-04
154 | QSGTL_130FC38009.PIDA.OP | 2022-11-11
155 | QSGTL_111FC42002.PIDA.OP | 2022-11-11
156 | QSGTL_130FC39003.PIDA.OP | 2022-11-11
157 | QSGTL_112FC21003.PIDA.OP | 2022-11-11
158 | QSGTL_130PC10040.PIDA.OP | 2022-11-11
159 | QSGTL_111FC33014.PIDA.OP | 2022-11-11
160 | QSGTL_130FC33010.PIDA.OP | 2022-11-11
161 | QSGTL_131TC10422.PIDA.OP | 2022-11-11
162 | QSGTL_111PC32003.PIDA.OP | 2022-11-11
163 | QSGTL_111FC35006.PIDA.OP | 2022-11-11
164 | QSGTL_111FC33012.PIDA.OP | 2022-11-11
165 | QSGTL_131FC21003.PIDA.OP | 2022-11-11
166 | QSGTL_111FC34003.PIDA.OP | 2022-11-11
167 | QSGTL_130LC10012.PIDA.OP | 2022-11-11
168 | QSGTL_112FC21001.PIDA.OP | 2022-11-11
169 | QSGTL_111FC38014.PIDA.OP | 2022-11-11
170 | QSGTL_111PC38003.PIDA.OP | 2022-11-11
171 | QSGTL_184PC10006B.AUTOMANA.OP | 2022-11-11
172 | QSGTL_184FC10002.PIDA.OP | 2022-11-11