## Tunu recovery
| Well | Production (kbopd) |  | Survey cap | Actuator | comms unit | Flowline repair | hook up arm | WH cage repair | Swab valveBeanboxOthers | Bean box | Master valve | Others | Security ready | LEC | Comments
1 | OPNO005S | 477.4529 | CCU/WH Accessories Theft | Not Available | Not Available | Not Available | Available | Available | Available | Available | Available | Available | Available |  |  | No bean box cover
2 | OPNO028T | 1193.4 |  | Not Available | Not Available | Not Available | Available | Available | Available | Swab valve not available. | Available | N/A | Available |  |  | upper & lower master, wing valve not available,
3 | OPNO021T | 634.2726 |  | Not Available | Not Available | Not Available | Available | Available | Available | Swab valve not available. | Available | N/A | N/A |  |  | Lower master valve available only.
4 | OPUK005S | 738.0129 |  | Available | Not Available | Not Available | Available | Available | Available | Available | Available | Available | Available
5 | OPUK009T | 774.9 |  | Not Available | Available | Not Available | Available | Available | Available | Available | Available | Available | Available
6 | OPUK033S | 728.7919 |  | Not Available | Not Available | Not Available | N/A | Available | Available | Not Available | Not Available | Not Available | Not Available |  |  | Wellhead seriously vandalized
7 | AJAT001L | 1732.3727 | CCU/WH Accessories Theft | Available | Not Available | Not Available | Available | Available | NEED REPAIRS | Available | Available | Available | Available
8 | OPUK012L | 134 | CCU/WH Accessories removed | Not Available | Not Available | Not Available | Available | Available | Available | Not Available | Not Available | Not Available | Not Available |  |  | No actuator housing.Other Well head accessories are with CWI
9 | OPUK012S | 445 | CCU/WH Accessories removed | Not Available | Not Available | Not Available | Available | Available | Available | Not Available | Not Available | Not Available | Not Available |  |  | No actuator housing.Other Well head accessories are with CWI
10 | OPUK024T | 403.4331 | Flowline sabotage & CCU/WH Accessories Theft | Not Available | Not Available | Not Available | Not Available | Available | NEED REPAIRS | Not Available | Available | Available | Available |  | TBA | Cannot acertain the integrity of flowline.
11 | KANB003S | 597.7145 | Flowline sabotage & CCU/WH Accessories Theft | Available | Not Available | Available | Planned in- LEC Oct | Available | Available | Available | Available | Available | Available |  | Oct (more theft of line so scope changed)
12 | KANB005L | 263.397 | Flowline sabotage | Available | Available | Available | Planned in- LEC Oct | Available | Available | Available | Available | Available | Available |  | Oct (more theft of line so scope changed)
13 | KANB006T | 509.5824 |  | Available | Available | Available | Planned in- LEC Oct | Available | Available | Available | Available | Available | Available |  | Oct (more theft of line so scope changed)
14 | KANB009T | 1327.2299 |  | Available | Available | Available | On site. LEC Aug | Available | Available | Available | Available | Available | Available |  | August (9km line. 3 weeks per km)
15 | OPUK039T | 1587.224 |  | Available | Available | Available | Ready to mob. LEC End March | Available | Available | Available | Available | Available | Available |  | End March | Flowline vandalised.
16 | OTUM019T | 939.4067 |  | Available | Available | Available | eldl approved procurement started. LEC Oct | Available | Available | Available | Available | Available | Available |  | October
17 | OPUK 7T |  | Flowline and wellhead vandalised | Available | Not Available | Not Available | Planned in- LEC Oct | Available | Available | Available | Available | Available | Available |  |  | Asset engineering yet to work on the flowline.
18 | OPUK 36T |  | Wellhead vandalised | Not Available | Not Available | Not Available | Available | Available | NEED REPAIRS | Available | Available | Available | Available
19 | OGBO015T | 0 | New well | Available | Available | Available | Planned in | Available | Available | Available |  | Available | Available |  |  | New well
20 | OGBO016T | 0 | New well | Available | Available | Available | Planned in | Available |  | Available |  | Available | Available |  |  | New well
21 | OPOMOYO1S | 2906 | Flowline cut & Stolen CCU/actuator |  |  |  | Planned in- LEC Oct. 8km | Available |  |  |  | Available | Available
22 | OPOMOYO1L | 2797 | Flowline cut | Available | Available | Available | Planned in- LEC Oct- commingled with 1S | Available |  |  | Available | Available | Available
23 | AKONO1S | 1581 | wellhead units vandalized |  |  |  | Available | Available | On site. LEC March
24 | AKONO1L |  | wellhead units vandalized |  |  |  | Available | Available