## Tunu recovery
TTL |  | 20200.1907 |  |  | 12 | 15 | 14 | 12 | 1 | 7 | 10 | 6 | 7 | 6
| Well | Production (kbopd) |  |  | Survey cap | Actuator | Mod. comms unit | Flowline repair | hook up arm | WH cage repair | Swab valveBeanboxOthers | Bean box | Master valve | Others | Security ready | LEC | Comments
1 | OPNO005S | 477.4529 | 3-1/8" x 5k Cameron Gate/Seat | CCU/WH Accessories Theft | Not Available | Warehouse | Not Available | Available | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided |  | No bean box cover
2 | OPNO028T | 1193.4 | 4 1/8" 5K Vecto gray Gate/Bushing |  | Warehouse | Warehouse | Not Available | Available | Available | Available | Not Available, New contract to be loaded. | Not Available | Not Available, New contract to be loaded | Available | Cluster centri-post coverage to be provided |  | upper & lower master, wing valve not available,
3 | OPNO021T | 634.2726 | 4-1/8'' X 5K Cameron FL Gate/Bushing |  | Warehouse | Warehouse | Not Available | Planned in- LEC End June | Available | Available | Not Available, New contract to be loaded | Not Available | Not Available, New contract to be loaded | N/A | Cluster centri-post coverage to be provided |  | Lower master valve available only. Budget required ⁠⁠⁠⁠$277K | In plan
4 | OPUK005S | 738.0129 | 3-1/8" x 5k Cameron Gate/Seat |  | Not Available | Warehouse | Not Available | Available | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided
5 | OPUK009T | 774.9 | 3-1/8"X5K |  | Available | Available | Available | Available | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided |  | Well already flowing
6 | OPUK033S | 728.7919 | 3-1/8'' X 5K Cameron FL Gate/Bushing |  | Not Available | Warehouse | Not Available | N/A | Available | Available | Not Available, New contract to be loaded | Warehouse | Not Available, New contract to be loaded | Not Available | Cluster centri-post coverage to be provided |  | Wellhead seriously vandalized. Confirm flowline length | In plan
7 | AJAT001L | 1732.3727 | 3-1/8"X5K Cameron FL Gate/Bushing | CCU/WH Accessories Theft | Available | Warehouse | Not Available | Available | Available | NEED REPAIRS | Available | Available | Available | Available | Cluster centri-post coverage to be provided |  | Damaged WH cage, hookup arm,Staircase/platform and complete flowline
8 | OPUK012L | 134 | 3-1/8"X5K Cameron FL Gate/Bushing | CCU/WH Accessories removed | Not Available | Warehouse | Not Available | Available | Available | Available | Not Available, New contract to be loaded | Warehouse | Not Available, New contract to be loaded | Not Available | Cluster centri-post coverage to be provided |  | No actuator housing.Other Well head accessories are with CWI.
9 | OPUK012S | 445 | 3-1/8"X5K Cameron FL Gate/Bushing | CCU/WH Accessories removed | Not Available | Warehouse | Not Available | Available | Available | Available | Not Available, New contract to be loaded | Warehouse | Not Available, New contract to be loaded | Not Available | Cluster centri-post coverage to be provided |  | No actuator housing.Other Well head accessories are with CWI
10 | OPUK024T | 403.4331 | 4-1/8'' X 5K Cameron FL Gate/Bushing | Flowline sabotage & CCU/WH Accessories Theft | Warehouse | Warehouse | Not Available | Planned in- LEC End Nov | Available | NEED REPAIRS | Not Available, New contract to be loaded | Not Available | Available | Available | Cluster centri-post coverage to be provided | TBA | Cannot acertain the integrity of flowline. Budget required $1.43M | In plan
11 | KANB003S | 597.7145 | 3-1/8"X5K | Flowline sabotage & CCU/WH Accessories Theft | Available | Warehouse | Available | Planned in- LEC Oct | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided | Oct (more theft of line so scope changed) | Sepy to confirm the well. KAN003L is in plan
12 | KANB005L | 263.397 | 3-1/8" x 5k | Flowline sabotage | Available | Available | Available | Planned in- LEC Oct | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided | Oct (more theft of line so scope changed) |  | In plan
13 | KANB006T | 509.5824 | 3-1/8" x 5k |  | Available | Available | Available | Planned in- LEC Oct | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided | Oct (more theft of line so scope changed) |  | In plan
14 | KANB009T | 1327.2299 | 4-1/16"x5k |  | Available | Available | Available | On site. LEC Aug | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided | August (9km line. 3 weeks per km) | Red-banded | In plan
15 | OPUK039T | 1587.224 | 3-1/8" x 5k Breda Gate/Bushing |  | Available | Available | Available | Ready to mob. LEC End May | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided | End March | Flowline vandalised. | In plan
16 | OTUM019T | 939.4067 | 4-1/16" x 5k |  | Available | Available | Available | eldl approved procurement started. LEC Oct | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided | October |  | In plan
17 | OPUK 7T | 350 | 3-1/8" x 5k Cameron Gate/Seat | Flowline and wellhead vandalised | Available | Warehouse | Not Available | Planned in- LEC Oct | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided |  | Asset engineering yet to work on the flowline. Budget required $966K | In plan
18 | OPUK 36T | 80 | 11'' X 4-1/16'' X 5k Kvaerner | Wellhead vandalised | Warehouse | Warehouse | Not Available | Available | Available | NEED REPAIRS | Available | Available | Available | Available | Cluster centri-post coverage to be provided |  | Repair cage
19 | OGBO015T | 0 | 11” x 3-1/8” x 3-1/8” x 5k Breda gate/bushing | New well | Available | Available | Available | Available | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided |  | New well
20 | OGBO016T | 0 | 11” x 3-1/8” x 3-1/8” x 5k Breda gate/bushing | New well | Available | Available | Available | Available | Available | Available | Available | Available | Available | Available | Cluster centri-post coverage to be provided |  | New well - flowing
21 | OPOMOYO1S | 2906 | 3-1/8"X5K Cameron FL Gate/Bushing | Flowline cut & Stolen CCU/actuator |  | Not Available | Not Available | Planned in- LEC Oct. 8km | Not Available | Not Available | Not Available, New contract to be loaded | Warehouse | Available | Available | Cluster centri-post coverage to be provided |  | Site visit required to confirm latest condition. Proposed to be combined with 1L. $3.5M | In plan
22 | OPOMOYO1L | 2797 | 3-1/8"X5K Cameron FL Gate/Bushing | Flowline cut | Available | Available | Available | Planned in- LEC Oct- commingled with 1S | Available | Not Available | Not Available, New contract to be loaded | Available | Available | Available | Cluster centri-post coverage to be provided |  | Site visit required to confirm latest condition. Proposed to be combined with 1S. Red-banded team has a budget. Seppy to confirm from Sophie Boham | In plan
23 | AKONO1S | 1581 | 3-1/8"X5K Cameron FL Gate/Bushing | wellhead units vandalized | Not Available, New contract to be loaded | Warehouse | Not Available | Available | Available | On site. | Not Available, New contract to be loaded |  | Not Available |  | Cluster centri-post coverage to be provided |  | Site visit required to confirm latest condition
24 | AKONO1L |  | 3-1/8"X5K Cameron FL Gate/Bushing | wellhead units vandalized | Not Available, New contract to be loaded | Warehouse | Not Available | Available | Available | Not Available | Not Available, New contract to be loaded. . |  | Not Available |  | Cluster centri-post coverage to be provided |  | Site visit required to confirm latest condition
24 | KANB008T | 750 |  | Flow line sabotage | [10 empty] | Cluster centri-post coverage to be provided
24 | KANB004S | 400 |  | Flow line sabotage | [10 empty] | Cluster centri-post coverage to be provided
| KANB005S | 300 |  | Downhole safety valve and F/L sabotage | [10 empty] | Cluster centri-post coverage to be provided

## Summary
| Item/Activity | Action/Remarks | When | Parties
| Spares | Secure approval/Waiver to work w/o PO | Today | Chinedu
|  | Confirm delivery dates | 19/04 | Chinedu
| Barge | Ready for mobilization | 28/04 | Chinedu
|  | Pick up ComUnits & deliver at site |  | Chinedu
| ComUnit | Complete 16 Single Units | 28/04 | Esther
| Security | Leverage on alignment with Community while the Centri-post engagement is held with NUIMS
Flowline | OPUK 039 | On track | End May | Sepy
| KAN003S | Sepy to reconfirm the well nomenclature with PUM. Sheet carries KAN003S while KAN003L is in plan | End June | Sepy
| OPNO 021 | Send a note to Juliet for Budget |  | Sepy
| OPUK 7T | Send a note to Juliet for Budget |  | Sepy
| OPUK033S | Confirm flowline length |  | Sepy