## JAN '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | FSIV ELAYNE | SUPPORT VESSEL | 4510462664 | WELLS | AFREMO | 367272.36 | 10908 | 2021-03-04 | 2021-12-31 | 2022-06-01 | 6 | 2203634.16 | 65448
2 | MERCIFUL III | HOUSEBOAT | 4510462476 | OAPB | OTUMARA | 109564.07 | 1018.98 | 17/9/2021 | 2022-01-26 | 13/2/2022 | 18 | 1972153.26 | 18341.64
[12 empty] | 0 | 0
3 | MV PETRAL 1 | TUGBOAT | 4510462478 | OAPB | OTUMARA | 70327.98 | 654.08 | 17/9/2021 | 2022-01-30 | 2022-08-02 | 9 | 632951.82 | 5886.72
[12 empty] | 0 | 0
4 | GOLDSHOLD XVII | CORAL BARGE | 4510462014 | WELLS | OPUKUSHI | 344.25 | 37015.29 | 2022-01-12 | 2022-01-20 | 2022-01-31 | 11 | 3786.75 | 407168.19
[12 empty] | 0 | 0
5 | MARIEN VIII | TUGBOAT | 4510465101 | PIPELINE | ESCRAVOS | 70327.98 | 654.08 | 2022-01-20 | 2022-01-27 | 2022-08-02 | 12 | 843935.76 | 7848.96
[12 empty] | 0 | 0
6 | TEJIRI II | RAMP BARGE | 4510465101 | PIPELINE | ESCRAVOS | 32592.94 | 302.94 | 2022-01-20 | 2022-01-27 | 2022-08-02 | 12 | 391115.28 | 3635.28
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[11 empty] | Total | 6047577.03 | 508328.79

## JAN '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | MV OYENDI II | TUGBOAT | PRODUCTION | N/BNK AND TUNU | 70327.98 | 654.08 | 27/12/2021 | 2022-02-01 | 2022-02-01 | 6 | 421967.88 | 3924.48
2 | DOUBRA II | RAMP BARGE | PRODUCTION | N/BNK AND TUNU | 32592.94 | 302.94 | 27/12/2021 | 2022-02-01 | 2022-02-01 | 6 | 195557.64 | 1817.64
3 | MV FAVOUR 1 | TUGBOAT | PRODUCTION | TUNU | 70327.98 | 654.08 | 20/1/2022 | 24/1/2022 | 24/1/2022 | 5 | 351639.9 | 3270.4
4 | JOETEK VIII | RAMP BARGE | PRODUCTION | TUNU | 32592.94 | 302.94 | 20/1/2022 | 24/1/2022 | 24/1/2022 | 5 | 162964.7 | 1514.7
5 | MV BUDUKA | TUGBOAT | PROJECT | OTUMARA | 70327.98 | 654.08 | 22/1/2022 | 31/1/2022 | 2022-01-02 | 11 | 773607.78 | 7194.88
6 | IYENABO IBIYE IV | RAMP BARGE | PROJECT | OTUMARA | 32592.94 | 302.94 | 22/1/2022 | 31/1/2022 | 2022-01-02 | 11 | 358522.34 | 3332.34
[10 empty] | 44 | 2264260.24 | 21054.44
Note on B4: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP
Note on B5: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP
Note on B6: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP TO SUPPORT TUNU WELL VANDALIZATION
Note on B7: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP TO SUPPORT TUNU WELL VANDALIZATION
Note on B8: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP TO SUPPORT NGC OPS
Note on B9: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP TO SUPPORT NGC OPS

## FEB '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | MV FAVOUR 4 | TUGBOAT | 4510464178 | PRODUCTION | OTUMARA | 70327.98 | 654.08 | 2022-07-02 | 2022-12-02 | 13/1/2022 | 1 | 70327.98 | 654.08
2 | MV FAVOUR 5 | TUGBOAT | 4510464178 | PRODUCTION | OTUMARA | 70327.98 | 654.08 | 2022-07-02 | 2022-12-02 | 13/1/2022 | 1 | 70327.98 | 654.08
[12 empty] | 0 | 0
3 | [11 empty] | 0 | 0
[12 empty] | 0 | 0
4 | [11 empty] | 0 | 0
[12 empty] | 0 | 0
5 | [11 empty] | 0 | 0
[12 empty] | 0 | 0
6 | [11 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[11 empty] | Total | 140655.96 | 1308.16

## FEB '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | TBA | TUGBOAT | PRODUCTION | FORCADOS | 70327.98 | 654.08 | 2022-06-02 | 2022-11-02 | 2022-11-02 | 6 | 421967.88 | 3924.48
2 | TBA | TUGBOAT | PRODUCTION | TUNU | 70327.98 | 654.08 | 2022-06-02 | 2022-11-02 | 2022-11-02 | 6 | 421967.88 | 3924.48
[10 empty] | 12 | 843935.76 | 7848.96
Note on B4: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP
Note on B5: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP

## MAR '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | MV BUDUKA | TUGBOAT | 4510467783 | WELLS | OPUKUSHI | 70327.98 | 654.08 | 24/2/2022 | 2022-08-03 | 2022-09-03 | 1 | 70327.98 | 654.08
2 | MV KESSY II | TUGBOAT | 4510467783 | WELLS | OPUKUSHI | 70327.98 | 654.08 | 25/2/2022 | 2022-08-03 | 2022-10-03 | 2 | 140655.96 | 1308.16
[12 empty] | 0 | 0
3 | MV AKUS | TUGBOAT | 4510466879 | CORROSION | OTUMARA | 70327.98 | 654.08 | 13/12/2021 | 2022-11-03 | 14/3/2022 | 3 | 210983.94 | 1962.24
[12 empty] | 0 | 0
4 | YINS OIL 11 | ENV. BARGE | 4510466879 | CORROSION | OTUMARA | 37015.29 | 344.25 | 13/12/2021 | 2022-11-03 | 14/3/2022 | 3 | 111045.87 | 1032.75
[12 empty] | 0 | 0
5 | MV BUDUKA | TUGBOAT | 4510466197 | PROJECT | NORTH BANK | 70327.98 | 654.08 | 2021-12-03 | 23/3/2022 | 29/3/2022 | 6 | 421967.88 | 3924.48
[12 empty] | 0 | 0
6 | JUBICHRIS | RAMP BARGE | 4510466197 | PROJECT | NORTH BANK | 32592.94 | 302.94 | 2021-12-03 | 23/3/2022 | 29/3/2022 | 6 | 195557.64 | 1817.64
[12 empty] | 0 | 0
7 | TEJIRI II | RAMP BARGE | 4510467783 | WELLS | OPUKUSHI | 70327.98 | 654.08 | 28/2/2021 | 24/3/2022 | 29/3/2022 | 5 | 351639.9 | 3270.4
[12 empty] | 0 | 0
8 | MV FAVOUR 4 | TUGBOAT | 4510466196 | PROJECT | NORTH BANK | 70327.98 | 654.08 | 2021-12-03 | 30/3/2022 | 31/3/2022 | 1 | 70327.98 | 654.08
[12 empty] | 0 | 0
9 | AKUGBENE ISLAND | RAMP BARGE | 4510466196 | PROJECT | NORTH BANK | 32592.94 | 302.94 | 2021-12-03 | 30/3/2022 | 30/3/2022 | 1 | 32592.94 | 302.94
[12 empty] | 0 | 0
10 | MV JOETEK VII | NNRA TUGBOAT | 4510467783 | WELLS | OPUKUSHI | 135587.07 | 1260.72 | 2021-12-03 | 30/3/2022 | 2022-08-04 | 9 | 1220283.63 | 11346.48
[11 empty] | Total | 2825383.72 | 26273.25

## MAR '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | TBA | TUGBOAT | PRODUCTION | FORCADOS | 70327.98 | 654.08 | 22/3/2022 | 26/2/2022 | 26/2/2022 | 5 | 351639.9 | 3270.4
2 | TBA | RAMP BARGE | PRODUCTION | FORCADOS | 32592.94 | 302.94 | 22/3/2022 | 26/2/2022 | 26/2/2022 | 5 | 162964.7 | 1514.7
[10 empty] | 10 | 514604.6 | 4785.1
Note on B4: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP
Note on B5: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP

## APR '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | MV PERELADE 1 | ESV | 4510468038 | PROJECT | FOT ESTUARY | 271442.66 | 2524.5 | 2022-02-03 | 31/3/2022 | 2022-01-04 | 1 | 271442.66 | 2524.5
2 | CLEM 08 | HOUSEBOAT | 4510461273 | PIPELINE | SOKU | 120090.84 | 1116.88 | 16/11/2021 | 2022-03-04 | 2022-09-04 | 6 | 720545.04 | 6701.28
[12 empty] | 0 | 0
3 | MV APUTU 1 | TUGBOAT | 4510465166 | PIPELINE | SOKU | 70327.98 | 654.08 | 18/11/2021 | 2022-03-04 | 14/4/2022 | 11 | 773607.78 | 7194.88
[12 empty] | 0 | 0
4 | MV RUNO | TUGBOAT | 4510465166 | PIPELINE | SOKU | 70327.98 | 654.08 | 29/3/2022 | 2022-03-04 | 2022-06-04 | 3 | 210983.94 | 1962.24
[12 empty] | 0 | 0
5 | WB PERES | WATER BARGE | 4510465026 | WELLS | OPUKUSHI | 35534.25 | 330.48 | 2019-12-06 | 2022-07-04 | 2022-10-04 | 3 | 106602.75 | 991.44
[12 empty] | 0 | 0
6 | MV TIMI II | TUGBOAT | 4510465026 | WELLS | OPUKUSHI | 70327.98 | 654.08 | 2019-12-06 | 2022-07-04 | 2022-11-05 | 34 | 2391151.32 | 22238.72
[12 empty] | 0 | 0
7 | MV EBUERE II | TUGBOAT | 4510465026 | WELLS | OPUKUSHI | 70327.98 | 654.08 | 2019-12-06 | 2022-07-04 | 2022-11-05 | 34 | 2391151.32 | 22238.72
[12 empty] | 0 | 0
8 | MV GODSHOLD XVII | TUGBOAT |  | PRODUCTION | OTUMARA | 70327.98 | 654.08 | 13/4/2022 | 18/4/2022 | 19/4/2022 | 1 | 70327.98 | 654.08
[12 empty] | 0 | 0
9 | OGHENEMINE 1 | TUGBOAT |  | PRODUCTION | OTUMARA | 70327.98 | 654.08 | 13/4/2022 | 18/4/2022 | 19/4/2022 | 1 | 70327.98 | 654.08
[12 empty] | 0 | 0
10 | OGHENEGAREN V | CORAL BARGE | 4510467783 | WELLS | OPUKUSHI | 37015.29 | 344.25 | 24/2/2022 | 2022-05-04 | 24/4/2022 | 19 | 703290.51 | 6540.75
[12 empty] | 0 | 0
11 | OMS 106 | FLAT TOP BARGE | 4510465031 | WELLS | OPUKUSHI | 32592.94 | 302.94 | 2021-10-11 | 20/4/2022 | 2022-11-05 | 21 | 684451.74 | 6361.74
[12 empty] | 0 | 0
10 | [11 empty] | 0 | 0
[11 empty] | Total | 8393883.02 | 78062.43

## APR '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
[10 empty] | 0 | 0 | 0

## MAY '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | MV GLORY I | TUGBOAT | 4510470256 | PIPELINE | ODIMODI | 70327.98 | 654.08 | 22/4/2022 | 2022-06-05 | 2022-07-05 | 1 | 70327.98 | 654.08
2 | MV GLORY II | TUGBOAT | 4510470256 | PIPELINE | ODIMODI | 70327.98 | 654.08 | 22/4/2022 | 2022-06-05 | 2022-07-05 | 1 | 70327.98 | 654.08
[12 empty] | 0 | 0
3 | MV TIMI II |  |  | WELLS | OGBOTOBO | 70327.98 | 654.08 | 18/5/2022 | 21/5/2022 | 31/5/2022 | 10 | 703279.8 | 6540.8
[12 empty] | 0 | 0
4 | MV TIMI III |  |  | WELLS | OGBOTOBO | 70327.98 | 654.08 | 18/5/2022 | 21/5/2022 | 31/5/2022 | 10 | 703279.8 | 6540.8
[12 empty] | 0 | 0
5 | MV KRISTINE II |  |  | WELLS | OGBOTOBO | 70327.98 | 654.08 | 18/5/2022 | 21/5/2022 | 31/5/2022 | 10 | 703279.8 | 6540.8
[12 empty] | 0 | 0
6 | MV BRAKAEMI |  |  | WELLS | OGBOTOBO | 70327.98 | 654.08 | 18/5/2022 | 21/5/2022 | 31/5/2022 | 10 | 703279.8 | 6540.8
[12 empty] | 0 | 0
7 | R.B EBIPADE |  |  | WELLS | OGBOTOBO | 32592.94 | 302.94 | 2022-11-05 | 21/5/2022 | 25/5/2022 | 4 | 130371.76 | 1211.76
[12 empty] | 0 | 0
8 | R.B PERERE |  |  | WELLS | OGBOTOBO | 32592.94 | 302.94 | 2022-11-05 | 21/5/2022 | 25/5/2022 | 4 | 130371.76 | 1211.76
[12 empty] | 0 | 0
9 | AJAKURAMA ISLAND |  |  | WELLS | OGBOTOBO | 32592.94 | 302.94 | 2022-11-05 | 21/5/2022 | 25/5/2022 | 4 | 130371.76 | 1211.76
[12 empty] | 0 | 0
10 | MV MARIEN VIII |  | 4510471258 | WELLS | BENISEDE | 70327.98 | 654.08 | 16/5/2022 | 28/5/2022 | 28/6/2022 | 34 | 2391151.32 | 22238.72
[12 empty] | 0 | 0
11 | OGUNU ISLAND |  | 4510471258 | WELLS | BENISEDE | 32592.94 | 302.94 | 14/5/2022 | 28/5/2022 | 28/6/2022 | 32 | 1042974.08 | 9694.08
[12 empty] | 0 | 0
10 | [11 empty] | 0 | 0
[11 empty] | Total | 6779015.84 | 63039.44

## MAY '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | TBA | TUGBOAT | PRODUCTION | NORTH BANK | 70327.98 | 654.08 | 30/4/2022 | 2022-03-05 | 2022-03-05 | 4 | 281311.92 | 2616.32
2 | TBA | RAMP BARGE | PRODUCTION | NORTH BANK | 32592.94 | 302.94 | 30/4/2022 | 2022-03-05 | 2022-03-05 | 4 | 130371.76 | 1211.76
[10 empty] | 8 | 411683.68 | 3828.08
Note on B4: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP
Note on E4: Igben, Kingsley D SPDC-UPC/G/USLM: MVT OF WATER TANKER TO NORTH BANK THEREBY AVERTING STATION SHUTDOWN BY COMMUNITY AS THREATENED.
Note on B5: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP

## JUN '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | PHILOMENA | CREW BOAT | 4510470770 | WEST ASSET | WEST ASSET | 107559.38 | 3487.5 | 23/5/2022 | 2022-03-06 | 2022-06-06 | 3 | 322678.14 | 10462.5
2 | MV EGO | TUGBOAT | 4510471310 | PIPELINE | ODIMODI | 70327.98 | 654.08 | 2022-05-05 | 2022-09-06 | 2022-04-07 | 25 | 1758199.5 | 16352
3 | AKUGBENE ISLAND | RAMP BARGE | 4510471310 | PIPELINE | ODIMODI | 32592.94 | 302.94 | 2022-05-05 | 2022-09-06 | 2022-04-07 | 25 | 814823.5 | 7573.5
4 | MV FAVOUR 5 | TUGBOAT | 4510471311 | PIPELINE | ODIMODI | 70327.98 | 654.08 | 2022-05-05 | 2022-09-06 | 2022-04-07 | 25 | 1758199.5 | 16352
5 | AMS FAITH | ENV. BARGE | 4510471311 | PIPELINE | ODIMODI | 37015.29 | 344.25 | 2022-05-05 | 2022-09-06 | 2022-04-07 | 25 | 925382.25 | 8606.25
6 | MV URANUS | TUGBOAT | 4510472589 | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2022-07-05 | 2022-12-06 | 15/6/2022 | 3 | 210983.94 | 1962.24
7 | AMS EBIS | ENV. BARGE | 4510472589 | WEST ASSET | TUNU NODE | 37015.29 | 344.25 | 2022-07-05 | 2022-12-06 | 15/6/2022 | 3 | 111045.87 | 1032.75
8 | GODSHOLD XVIII | TUGBOAT | 4510471309 | PIPELINE | ODIMODI | 70327.98 | 654.08 | 2022-06-05 | 2022-09-06 | 2022-03-07 | 24 | 1687871.52 | 15697.92
9 | MARIEN VI | WATER BARGE | 4510471309 | PIPELINE | ODIMODI | 35534.25 | 330.48 | 2022-06-05 | 2022-09-06 | 2022-03-07 | 24 | 852822 | 7931.52
10 | MV MOBILE | TUGBOAT | 4510471950 | WEST ASSET | OTUMARA | 70327.98 | 654.08 | 30/5/2022 | 2022-09-06 | 2022-12-06 | 3 | 210983.94 | 1962.24
11 | MV EBUERE II | TUGBOAT | 4510471951 | WEST ASSET | OTUMARA | 70327.98 | 654.08 | 30/5/2022 | 2022-09-06 | 2022-12-06 | 3 | 210983.94 | 1962.24
12 | YINS OIL II | ENV. BARGE | 4510471951 | WEST ASSET | OTUMARA | 37015.29 | 344.25 | 30/5/2022 | 2022-09-06 | 2022-12-06 | 3 | 111045.87 | 1032.75
13 | SWEET MOTHER | 60 MAN HB | 4510471307 | PIPELINE | NDORO | 109564.07 | 1018.98 | 2022-06-05 | 19/6/2022 | 2022-04-07 | 16 | 1753025.12 | 16303.68
14 | BLECLIF | TUGBOAT | 4510471308 | PIPELINE | NDORO | 70327.98 | 654.08 | 2022-09-05 | 19/6/2022 | 2022-04-07 | 15 | 1054919.7 | 9811.2
15 | MV ROSE | TUGBOAT | 4510471308 | PIPELINE | NDORO | 70327.98 | 654.08 | 18/6/2022 | 19/6/2022 | 24/6/2022 | 5 | 351639.9 | 3270.4
16 | EXCLUSIVE II | 100 MAN HB |  | PIPELINE | ODIMODI | 120090.84 | 1116.88 | 19/4/2022 | 18/6/2022 | 21/6/2022 | 3 | 360272.52 | 3350.64
17 | WANATIMI IV | 100 MAN HB |  | PIPELINE | NDORO | 120090.84 | 1116.88 | 19/4/2022 | 18/6/2022 | 21/6/2022 | 3 | 360272.52 | 3350.64
18 | GLORIOUS IX | 100 MAN HB |  | PIPELINE | ODIMODI | 120090.84 | 1116.88 | 19/4/2022 | 18/6/2022 | 21/6/2022 | 3 | 360272.52 | 3350.64
19 | MV MEMEN I | TUGBOAT |  | PIPELINE | BRASS CREEK | 70327.98 | 654.08 | 19/4/2022 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
20 | MV WANATIMI | TUGBOAT |  | PIPELINE | ODIMODI | 70327.98 | 654.08 | 19/4/2022 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
21 | MV ONOME | TUGBOAT |  | PIPELINE | ODIMODI | 70327.98 | 654.08 | 19/4/2022 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
22 | MV PAPATA II | TUGBOAT | 4510472387 | PIPELINE | ODIMODI | 70327.98 | 654.08 | 2022-06-06 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
23 | MV PAPATA III | TUGBOAT | 4510472387 | PIPELINE | ODIMODI | 70327.98 | 654.08 | 2022-06-06 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
24 | MV PURITY | TUGBOAT | 4510472387 | PIPELINE | NDORO | 70327.98 | 654.08 | 2022-06-06 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
25 | MV OROMENA | TUGBOAT | 4510472388 | PIPELINE | AGHORO | 70327.98 | 654.08 | 2022-06-06 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
26 | MV EDOSE | TUGBOAT | 4510472388 | PIPELINE | NDORO | 70327.98 | 654.08 | 2022-06-06 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
27 | PERELADE 1 | LHT | 4510471910 | WEST ASSET | FORCADOS | 271442.66 | 2524.5 | 26/5/2022 | 22/6/2022 | 24/6/2022 | 2 | 542885.32 | 5049
28 | CLEM 08 | 100 MAN HB |  | PIPELINE | ODIMODI | 120090.84 | 1116.88 | 20/4/2022 | 18/6/2022 | 21/6/2022 | 2 | 240181.68 | 2233.76
29 | MV MARY | TUGBOAT |  | PIPELINE | ODIMODI | 70327.98 | 654.08 | 20/4/2022 | 18/6/2022 | 21/6/2022 | 2 | 140655.96 | 1308.16
30 | CLEM 09 | 100 MAN HB |  | PIPELINE | AGHORO | 120090.84 | 1116.88 | 19/4/2022 | 18/6/2022 | 21/6/2022 | 3 | 360272.52 | 3350.64
31 | DABEL ANGEL VI | TUGBOAT |  | PIPELINE | AGHORO | 70327.98 | 654.08 | 19/4/2022 | 18/6/2022 | 21/6/2022 | 3 | 210983.94 | 1962.24
[11 empty] | Total | 16398273.19 | 159966.83
Note on K56: Igben, Kingsley D SPDC-UPC/G/USLM: CALL OUT WAS DONE ON A NEED TO USE BASIS

## JUN '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | TBA | TUGBOAT | WEST ASSET | FOT/NBANK | 70327.98 | 654.08 | 25/6/2022 | 29/6/2022 | 29/6/2022 | 5 | 351639.9 | 3270.4
2 | TBA | RAMP BARGE | WEST ASSET | FOT/NBANK | 32592.94 | 302.94 | 25/6/2022 | 29/6/2022 | 29/6/2022 | 5 | 162964.7 | 1514.7
[10 empty] | 10 | 514604.6 | 4785.1
Note on C4: Igben, Kingsley D SPDC-UPC/G/USLM: WASTE EVACUATION
Note on C5: Igben, Kingsley D SPDC-UPC/G/USLM: WASTE EVACUATION

## JUL '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | ESIAGU-1 | LANDING CRAFT | 4510474453 | WELLS | DIEBU CREEK | 57249 |  | 2022-01-07 | 2022-09-07 | 15/7/2022 | 6 | 343494 | 0
2 | OGHENEGAREN II | FTB |  | WELLS | OGBOTOBO | 32592.94 | 302.94 | 2022-01-07 | 26/7/2022 | 15/8/2022 | 20 | 651858.8 | 6058.8
3 | OGHENEGAREN VI | FTB |  | WELLS | OGBOTOBO | 32592.94 | 302.94 | 2022-01-07 | 26/7/2022 | 15/8/2022 | 20 | 651858.8 | 6058.8
4 | MV MOBILE | TUGBOAT |  | EAST ASSET | NUN RIVER | 70327.98 | 654.08 | 14/7/2022 | 22/7/2022 | 31/7/2022 | 9 | 632951.82 | 5886.72
5 | OGUNU ISLAND | RAMP BARGE |  | EAST ASSET | NUN RIVER | 32592.94 | 302.94 | 14/7/2022 | 22/7/2022 | 31/7/2022 | 9 | 293336.46 | 2726.46
6 | GRACIOUS GRACE III | TUGBOAT |  | WELLS | OGBOTOBO | 70327.98 | 654.08 | 2022-01-07 | 28/7/2022 | 15/8/2022 | 18 | 1265903.64 | 11773.44
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[11 empty] | Total | 3839403.52 | 32504.22

## JUL '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | TBA | TUGBOAT | WEST ASSET | FOT/NBANK | 70327.98 | 654.08 | 21/7/2022 | 25/7/2022 | 25/7/2022 | 4 | 281311.92 | 2616.32
2 | TBA | RAMP BARGE | WEST ASSET | FOT/NBANK | 32592.94 | 302.94 | 21/7/2022 | 25/7/2022 | 25/7/2022 | 4 | 130371.76 | 1211.76
3 | TBA | TUGBOAT | WEST ASSET | OGBOTOBO | 70327.98 | 654.08 | 24/7/2022 | 29/7/2022 | 29/7/2022 | 5 | 351639.9 | 3270.4
4 | TBA | RAMP BARGE | WEST ASSET | OGBOTOBO | 32592.94 | 302.94 | 21/7/2022 | 25/7/2022 | 25/7/2022 | 5 | 162964.7 | 1514.7
[10 empty] | 18 | 926288.28 | 8613.18
Note on C4: Igben, Kingsley D SPDC-UPC/G/USLM: DELIVERY OF PIPELINE KITS TO FOT USING NDORO PMS COMBO
Note on C5: Igben, Kingsley D SPDC-UPC/G/USLM: DELIVERY OF PIPELINE KITS TO FOT USING NDORO PMS COMBO
Note on C6: Igben, Kingsley D SPDC-UPC/G/USLM: SUPPLY OF A.G.O TO OGBOTOBO USING TUNU PMS COMBO
Note on C7: Igben, Kingsley D SPDC-UPC/G/USLM: DELIVERY OF A.G.O TO OGBOTOBO USING TUNU PMS COMBO

## AUG '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | VALARIE | FT BARGE |  | WELLS | OGBOTOBO | 32592.94 | 302.94 | 2022-01-08 | 2022-02-08 | 15/8/2022 | 13 | 423708.22 | 3938.22
2 | MV AJEMISE | TUGBOAT | 4510474224 | WEST ASSET | NORTH BANK | 70327.98 | 654.08 | 28/7/2022 | 2022-05-08 | 2022-06-08 | 1 | 70327.98 | 654.08
3 | H524 | RAMP BARGE | 4510474224 | WEST ASSET | NORTH BANK | 32592.94 | 302.94 | 28/7/2022 | 2022-05-08 | 2022-06-08 | 1 | 32592.94 | 302.94
4 | MV FAVOUR 4 | TUGBOAT | 4510475457 | EAST ASSET | NUN RIVER | 70327.98 | 654.08 | 14/7/2022 | 2022-05-08 | 31/8/2022 | 26 | 1828527.48 | 17006.08
5 | DIKI ISLAND | RAMP BARGE | 4510475457 | EAST ASSET | NUN RIVER | 32592.94 | 302.94 | 14/7/2022 | 2022-05-08 | 31/8/2022 | 26 | 847416.44 | 7876.44
6 | MV SHANTEL | TUGBOAT |  | WELLS | OGBOTOBO | 70327.98 | 654.08 | 2022-01-08 | 2022-08-08 | 15/8/2022 | 7 | 492295.86 | 4578.56
7 | MV BUDUKA | TUGBOAT |  | WELLS | OGBOTOBO | 70327.98 | 654.08 | 2022-01-08 | 2022-08-08 | 15/8/2022 | 7 | 492295.86 | 4578.56
8 | DV FAVOUR | TUGBOAT | 4510474813 | WEST ASSET | OTUMARA | 70327.98 | 654.08 | 31/7/2022 | 2022-09-08 | 13/8/2022 | 4 | 281311.92 | 2616.32
9 | YINS OIL 11 | ENV. BARGE | 4510474813 | WEST ASSET | OTUMARA | 37015.29 | 344.25 | 31/7/2022 | 2022-09-08 | 13/8/2022 | 4 | 148061.16 | 1377
10 | OGHENEGAREN 1 | CORAL BARGE | 4510475284 | WELLS | OGBOTOBO | 37015.29 | 344.25 | 2022-01-08 | 2022-12-08 | 15/8/2022 | 3 | 111045.87 | 1032.75
11 | ENOHO IV | LANDING CRAFT | 4510473650 | PROJECT | TUNU |  | 57249 | 26/7/2022 | 16/8/2022 | 25/8/2022 | 9 | 0 | 515241
[12 empty] | 0 | 0
12 | MV MOYOWA | TUGBOAT | 4510475484 | OABP | OPUKUSHI | 70327.98 | 654.08 | 13/8/2022 | 17/8/2022 | 19/8/2022 | 2 | 140655.96 | 1308.16
[12 empty] | 0 | 0
13 | MV AKUS | TUGBOAT | 4510475484 | OABP | BENISEDE | 70327.98 | 654.08 | 13/8/2022 | 17/8/2022 | 19/8/2022 | 2 | 140655.96 | 1308.16
14 | LB GRAND | JUB | 4510474329 | OABP | FOT ESTUARY | 770868 | 3780 | 2022-01-08 | 2022-09-08 | 30/8/2022 | 22 | 16959096 | 83160
[11 empty] | Total | 21967991.65 | 644978.27

## AUG '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | TBA TUG | TUGBOAT | WEST ASSET | OGBOTOBO | 70327.98 | 654.08 | 28/8/2022 | 31/8/2022 | 31/8/2022 | 4 | 281311.92 | 2616.32
2 | TBA TUG | RAMP BARGE | WEST ASSET | OGBOTOBO | 32592.94 | 302.94 | 28/8/2022 | 31/8/2022 | 31/8/2022 | 4 | 130371.76 | 1211.76
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[10 empty] | 8 | 411683.68 | 3828.08

## SEPT '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | PRINCESS BISCAR | TUGBOAT | 4510470659 | WELLS | OGBOTOBO | 135587.07 | 1260.72 | 19/8/2022 | 19/9/2022 | 30/9/2022 | 11 | 1491457.77 | 13867.92
2 | ENL VICTORY | RAMP BARGE | 4510470659 | WELLS | OGBOTOBO | 34547.4 | 321.3 | 19/8/2022 | 19/9/2022 | 30/9/2022 | 11 | 380021.4 | 3534.3
[11 empty] | Total | 1871479.17 | 17402.22

## SEPT '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | TBA TUG | TUGBOAT | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2022-01-09 | 2022-06-09 | 2022-06-09 | 6 | 421967.88 | 3924.48
2 | TBA TUG | RAMP BARGE | WEST ASSET | TUNU NODE | 32592.94 | 302.94 | 2022-01-09 | 2022-06-09 | 2022-06-09 | 4 | 130371.76 | 1211.76
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[10 empty] | 10 | 552339.64 | 5136.24

## OCT '22 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | MV MARIEN VIII | TUGBOAT | 4510477501 | AVIATION | FORCADOS | 70327.98 | 654.08 | 27/9/2022 | 2022-03-10 | 2022-06-10 | 3 | 210983.94 | 1962.24
2 | AKUGBENE ISLAND | RAMP BARGE | 4510477501 | AVIATION | FORCADOS | 32592.94 | 302.94 | 27/9/2022 | 2022-03-10 | 2022-06-10 | 3 | 97778.82 | 908.82
3 | MV FAVOUR 2 | TUGBOAT | 4510476066 | MILK RUN | TUNU NODE | 70327.98 | 654.08 | 26/9/2022 | 2022-07-10 | 2022-09-10 | 2 | 140655.96 | 1308.16
4 | DIKI ISLAND | RAMP BARGE | 4510476066 | MILK RUN | TUNU NODE | 32592.94 | 302.94 | 26/9/2022 | 2022-07-10 | 2022-09-10 | 2 | 65185.88 | 605.88
5 | MV SEMEN 1 | TUGBOAT | 4510477381 | BR RIGMOVE | OGBOTOBO | 135587.07 | 1260.72 | 23/9/2022 | 2022-09-10 | 13/10/2022 | 4 | 542348.28 | 5042.88
6 | PRINCESS AWANATE | TUGBOAT | 4510477381 | BR RIGMOVE | OGBOTOBO | 135587.07 | 1260.72 | 23/9/2022 | 2022-09-10 | 13/10/2022 | 4 | 542348.28 | 5042.88
7 | MV BUDUKA | TUGBOAT | 4510474996 | PROJECT | TUNU | 70327.98 | 654.08 | 25/10/2022 | 31/10/2022 | 2022-03-11 | 3 | 210983.94 | 1962.24
8 | JENNELLE | RAMP BARGE | 4510474996 | PROJECT | TUNU | 32592.94 | 302.94 | 25/10/2022 | 31/10/2022 | 2022-03-11 | 3 | 97778.82 | 908.82
[11 empty] | Total | 1908063.92 | 17741.92
17741.92
17402.22
35144.14
Note on C12: Igben, Kingsley D SPDC-UPC/G/USLM: 1500HP CAP
Note on C14: Igben, Kingsley D SPDC-UPC/G/USLM: 1500HP CAP

## OCT '22 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | MV KESSY II | TUGBOAT | WEST ASSET | NORTH BANK | 70327.98 | 654.08 | 21/10/2022 | 24/10/2022 | 24/10/2022 | 4 | 281311.92 | 2616.32
2 | TEJIRI II | RAMP BARGE | WEST ASSET | NORTH BANK | 32592.94 | 302.94 | 21/10/2022 | 24/10/2022 | 24/10/2022 | 4 | 130371.76 | 1211.76
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[10 empty] | 8 | 411683.68 | 3828.08
Note on B4: Igben, Kingsley D SPDC-UPC/G/USLM:RE-CYCLE TO SUPPORT GEN. SET BROKEN DOWN AT NORTH BANK
Note on B5: Igben, Kingsley D SPDC-UPC/G/USLM: RECYCLED TO SUPPORT GEN. SET DELIVERY TO NORTH BANK