## Slide 1
Nun River – Diebu Creek Re-routing - Project Timeline
Integrated schedule NRDC & Pipelines Integrity Restoration Option-1: Service change to happen before defect repairs and Clamp removal
6th Jun ‘22
Achieve RFSU for
NUNR Facility Scope
15th Apr ‘22
Complete KOCR Scope
23rd May ‘22
Achieve RFSU for
DBUC Facility Scope
\
1st July ‘22
Mechanical Completion
DBUC
Now
14th Mar ‘22
14th May ‘22
Mechanical Completion NUNR
13th May ‘22
Complete Service change of 8” NR Line
31st May ‘22
Start Commissioning NR post Service Change of 16” NR –KC line
\
14th Jun ‘22
Start Commissioning DBUC post Service Change of 10” DBUC line
Apr ‘22
May ‘22
Jun ‘22
Jul ‘22
Involve commissioning/ORA team (incorporate into schedule – Achieved
Provide design documentation to commissioning/ORA team – Achieved
Incorporate OR&A/CSU activities into integrated schedule – Achieved
Procure Installation materials 11th April ’22 – PO issued
Get update on IP status from PL team
Kolo Crk :Tie-in @10” critical
Pigging 18” for deliver line critical – (support from pipeline team).
Get NUPRC involved in the permit process
Frequent pull out of resources from Kolo creek impacting progress (stop further pullout)
Diebu Crk
Commence Fab – 08-03-22 - Achieved