## Slide 1: BOGT Power Optimization Project
BOGT AMIS/Electrical Team

## Slide 2
BOGT/Oloma GSF Quarters hook-up to Power
  Production Unit: Central East Hub - Bonny
  Project Owner: Alozie Godfrey/Aminu Sani
  Process Custodian: Akpala Ude, Okoye Stella, Atabor Henry, Udoka Kufre
  Process Focal Point:
  Process Stakeholders: Brossa Isaac, Osita Nnajiofor, Terfa Iortsuun, Ireti Omotoso, Roddy Simon
PROCESS OWNERSHIP
OPPORTUNITY STATEMENT
Opportunity Framing
Power analysis and design
MOC/TA Approvals
Material sourcing and procurement
Execution by DIY
Commissioning
SCOPE
BUSINESS CASE
GOAL
POTENTIAL ROADBLOCKS/ ISSUES
Gross Cost $16 000
500m of 3C x 70mmsq cable; excavation, cable laying and terminations
Soft Benefits:
- Elimination of diesel handling
- Improved wrench time
- Stress Reduction
COST/BENEFITS
The Oloma facility consists of an Associated Gas Compression Plant - 5.95 mmscf/d and a single bank oil flow station with a capacity of 45bpd. The Oloma facility is powered by 2 Gas Engine Generators (G3512) 350KVA/280KW and a Diesel Generator (Olympian 100KVA) for Blackstart.
Currently, power is provided to the GSF accommodation via 2 diesel generating sets rated at 21.6kW each (one used at a time to power full load). The annual expenditure on AGO supply for the generator sets is circa N12m. There are other maintenance costs not documented.
The facility generator sets are sufficiently rated to power the additional load, which has been calculated to be 20kW Peak load. A 30kW spare feeder has also been identified on the AG switchboard.
The power hookup of the Oloma GSF quarters will:
Saving The annual expenditure on AGO supply for the generator sets is circa N12m
Cost of maintenance of the two diesel Generators at the GSF camp. <&10k Annual
GHG emission reduction.
Constant power supply to the GSF camp, thereby improved working condition GSF team
Cost savings, Safety, efficiency, service, and improved workplace ambience
Load inadequacy
Constructability
100%
0%
09/06/19
20/06/19
PROCESS STATUS
50%
100%
Health
% Compl
Completion Date
Start Date
Overall Health Status (Current)
Opportunity Framing
MOC/TA Approvals
Procurement and Installation
Commissioning
21/06/19
19/06/19
Continuous
Gross Hard Benefits*:
Cost Saving: AGO consumption, NGN12m/yr
GHG Emissions reduction
10/06/19
09/06/19
11/06/19