## Slide 1: BOGT Power Optimization Project
BOGT AMIS/Electrical Team

## Slide 2
Oloma Perimeter lighting restoration by DIY
  Production Unit: Central East Hub - Bonny
  Project Owner: Alozie Godfrey/Ojo Akindele
  Process Custodian: Akpala Ude, Okoye Stella, Atabor Henry, Udoka Kufre, Osemu Inegbedion
  Process Focal Point:
  Process Stakeholders: Brossa Isaac, Osita Nnajiofor, Terfa Iortsuun, Ireti Omotoso, Roddy Simon
PROCESS OWNERSHIP
OPPORTUNITY STATEMENT
Troubleshooting
Material sourcing
Execution by DIY
Commissioning
SCOPE
BUSINESS CASE
GOAL
POTENTIAL ROADBLOCKS/ ISSUES
Gross Cost $46,000
Labour
Soft Benefits:
- Improved ambience
- Improved wrench time
- Stress Reduction
COST/BENEFITS
The Oloma facility consists of an Associated Gas Compression Plant - 5.95 mmscf/d and a single bank oil flow station with a capacity of 45bpd. The Oloma facility is powered by 2 Gas Engine Generators (G3512) 350KVA/280KW and a Diesel Generator (Olympian 100KVA) for Blackstart.
The Oloma facility flood lighting fittings were not functional as the cables Linking the poles was damaged and some part of the cable were harvested. The lighting fittings were defective and needed outright replacement and change out.
This Oloma lighting improvement was quoted to cost $250,000 to cover cabling and Ex-rated fittings replacement.
The asset team saw the opportunity of solving the challenge in-house at a reduced cost
The DIY restoration of the Oloma lighting will:
Save the original quoted cost of N250k if vendors are utilised
Improve security
Ensure safe operations
Cost savings, Safety, efficiency, service, and improved workplace ambience
Availability of materials
Availability of manpower
100%
0%
09/06/19
20/06/19
PROCESS STATUS
40%
100%
Health
% Compl
Completion Date
Start Date
Overall Health Status (Current)
Troubleshooting
Material sourcing
Procurement and Installation
Commissioning
21/06/19
19/06/19
Continuous
Gross Hard Benefits*:
Cost Saving $210,000
Security effectiveness
10/06/19
09/06/19
11/06/19