## Slide 1: Development of Integrity management system for the old export
BOGT MECHANICAL TEAM

## Slide 2
Development of Integrity management system for the old export
  Production Unit: Central East Hub - Bonny
  Project Owner: Osita Nnajiofor/Brossa Isaac
  Process Custodian: Victor Essienton/Opel Joel.
  Process Focal Point: Bela-Zabe Dumtuaka.
  Process Stakeholders: Ikechi Amaewhule, Opel Joel, Okaiwele Anthony, Bela-Zabe Dumtuaka, Ukpong Nsibiet, Goodi Emoghware, Ireti Omotoso, Opubo Tamunobarabiye.
PROCESS OWNERSHIP
OPPORTUNITY STATEMENT
Conduct survey and UT wall thickness measurements. – June 2019 /Secure budget cover. – Oct 2019
Execute immediate pipeline restorative works (pipe support, re-coating and seal replacement). – Dec 2019
Implement cathodic protection for pipeline. Sept – Dec ‘19 / Isolate and decommission the line. – Jan 2020
Set up line for yearly sampling, 2yearly WT examination at CMLs. – April 2020
SCOPE
BUSINESS CASE
GOAL
POTENTIAL ROADBLOCKS/ ISSUES
Gross Cost (estimated)
Spares procurement. (NGN 700K)
Eqpt for dismantling old export system (NGN 350K)
Cathodic protection installation (NGN 500K)
Soft Benefits:
Asset Integrity
COST/BENEFITS
An inspection of the old 42” BOGT export line revealed degradation and wall thickness loss due to corrosion. The line which has not been in use for some years is in contact with moist soil which is aggravating surface corrosion, paint flaking and coating deterioration with possible water ingress. This project will execute immediate pipeline restorative works (pipe support, re-coating and seal replacement), implement cathodic protection for pipeline, isolate and decommission the line and set up line for yearly sampling and periodic inspection. On completion this project will assure pipeline integrity and eliminate potential pipeline failure/environmental pollution. Estimated project cost is NGN1.55m
Successful resolution of this problem will:
Ensure asset integrity assurance for the old BOGT export line.
To define and implement a robust integrity assurance system for the old BOGT export line.
Management Commitment.
Successful stakeholder collaboration
Budget cover/Approval
100%
0%
30/10/19
01/04/20
PROCESS STATUS
20%
45%
Health
% Compl
Completion Date
Start Date
Overall Health Status (Current)
Conduct Site Survey/UT Assessment
Execute Pipeline Support Installation
Isolate and decommission line
Set up 2 Years WT exams at CMLs
31 /12/19
31/01/20
Continuous
Gross Hard Benefits*:
Eliminate potential pipeline failure/environmental pollution
30/10/19
30/06/19
30/12/19