## Sheet1 (2)
SN | PPS CODE | HUB | Project_Name | Budget (F$'000) |  |  |  | Basis for cost estimate | State Contract to be used for 2018 SCOPE EXECUTION | Contract Status for 2018 Scope | Team Lead | Pre-GM Challenge | Updates
|  |  |  | Scope |  | 2019
[5 empty] | 2018 Challenged F$x1000 | Proposal F$x1000 | 2019 Challenged F$x1000
27 | C_ISIM_EL1_Z10 | LAND | Electrical facility Upgrade East | Earthing improvement in Isimiri F/S: Provision of materials @ FUSD53K Mob/Demob & Carry out integrity tests to ascertain the status of the existing numbers of earth electrodes and remove all damaged or defunt components @ FUSD37K Provision of engineering support, QA/QC, logistics, etc @ FUSD10k | 100 |  |  | Contract rates & similar scopes. Earthing improvement in Isimiri F/S: Provision of materials @ FUSD53K Mob/Demob & Carry out integrity tests to ascertain the status of the existing numbers of earth electrodes and remove all damaged or defunt components @ FUSD37K Provision of engineering support, QA/QC, logistics, etc @ FUSD10k | NG01022468 | Contract Available with adequate ceiling & time | Omonigho | Align and agree scope and cost with the asset on the Electrical facility upgrade for Land East facilities. | Loaded in IAP.
31 | C_OBEL_EL1_Z10 | LAND | Electrical facility Upgrade East | Earthing improvement in Obele F/S: Provision of materials @ FUSD88K Mob/Demob & Carry out integrity tests to ascertain the status of the existing numbers of earth electrodes and remove all damaged or defunt components @ FUSD51K Provision of engineering support, QA/QC, logistics, etc @ FUSD21k | 160 |  |  | Contract rates & similar scopes. Earthing improvement in Obele F/S: Provision of materials @ FUSD88K Mob/Demob & Carry out integrity tests to ascertain the status of the existing numbers of earth electrodes and remove all damaged or defunt components @ FUSD51K Provision of engineering support, QA/QC, logistics, etc @ FUSD21k | NG01022642 |  | Omonigho | Align and agree scope and cost with the asset on the Electrical facility upgrade for Land East facilities. | Loaded in IAP
36 | C_OGTA_EL1_Z10 | LAND | Electrical facility Upgrade East | Electrical Facility Asset Integrity Review: Mob/demob @ FUSD30K Asset integrity review (including thermographic survey, power system performance checks, earthing system checks, etc) @ FUSD73K Provision of engineering support, QA/QC services, logistics, etc @ FUSD21K | 135 |  |  | Contract rates & similar scopes. Electrical Facility Asset Integrity Review: Mob/demob @ FUSD30K Asset integrity review (including thermographic survey, power system performance checks, earthing system checks, etc) @ FUSD73K Provision of engineering support, QA/QC services, logistics, etc @ FUSD21K | NG01022467 | Contract Available with adequate ceiling & time |  | Align and agree scope and cost with the asset on the Electrical facility upgrade for Land East facilities. | Loaded in IAP. Need to identify budget.
53 | C_SOKU_ES1_Z14 | SWAMP EAST | Control System Upgrade @ Soku Gasplant | Phase 1 (Total cost = FUS$180k): - Upgrade DCS Engineering workstation (HIS0164- Soku Main) and (HIS0364 - Soku FS) to Centum VP R6.04/ Server 2016 with VNET-IP so it coexists with HIS (CS3K R3.06/ win XP). Install Router for VNET VNET-IP comms - Upgrade Soku SIS Engineering Workstation (HIS0264) to Prosafe SLS/ Server 2016 - Upgrade SIS Engineering Workstation (SIO0264 Soku FS) to HIMA ELop II/ Win 10 Phase 2 (Total cost = FUS$365k): - Upgrade 3 Operator workstation (HIS0159 – HIS061) to R6.04/ Win 10 LTSB with VNET-IP Cards, relocate VNET Router. Each workstation with 4 monitors - Install Rack/ switches | 500 |  |  | Historical cost | Corporate procurement Contract TBA | Contract Available with adequate ceiling & time |  |  | Road map provided by PACO discipline already, ECS major contract being progressed. Loaded in IAP.
54 | C_SOKU_ES1_Z14 | SWAMP EAST | Control System Upgrade @ Soku Gasplant | Phase 3 (Total cost = FUS$330k): - Integrate EXAQUANTUM and EXAOPC and Upgrade - Integrate Webserver and TA server and Upgrade - Re-engineer requirement for PRM Phase 4 (Total cost = FUS$330k): - Integrate EXAQUANTUM and EXAOPC and Upgrade - Integrate Webserver and TA server and Upgrade Phase 5 (Total cost = FUS$280k) - Replace FCS (VNET to VNET-IP) | 0 |  | 500 | [5 empty] | Road map provided by PACO discipline already, ECS major contract being progressed. Loaded in IAP.
84 | C_FLDX_WS1_Z16 | SWAMP WEST | AFREMO A & B: Rehabilitation of Corroded cluster platforms | Rehabilitation of Corroded AFREMO A & B cluster platforms @ F$1.8m 1. Sandblasting/painting & replacement of Badly corroded line/Valve on HP Pig Launcher 2. Sandblasting/painting of corroded Fuel Gas Supply line piping to Raw Water Pump 3. Surface painting of Badly Corroded Gas supply to Well control panel, Sump Pump and Raw Water Pump, Test separator 4. provision of drip pan for the drains Sump tanks at A&B (fountain Action) 5. Replace missing Pig Launcher Barrel Cover. 6. Unblock 2” drain lines Under the wellhead deck and sandblast/paint corroded piping’s/valves. 7. Replacement/painting of corroded Big joe Regulator, Valves and Flanges of Fuel gas scrubber 8. Rehabilitation of Afremo B corroded Sump Tank/drain lines, Boat landing access ladder, gratings, handrails and Fenders Construction @ F$305k / Cluster JUB & SB @ F$17k x 70 days / cluster = F$1.2m AGO @ F$0.75 x 250,000 litres / 60days (JUB, SB, Security boat) = F$188k Boat Landing fenders per cluster & other materials @ F$140k / cluster PMT @ N1m per personnel X 3 persons x 2 months - F$40k | 1800 |  |  | Contract rates: Construction @ F$305k / Cluster JUB & SB @ F$17k x 70 days / cluster = F$1.2m AGO @ F$0.75 x 250,000 litres / 60days (JUB, SB, Security boat) = F$188k Boat Landing fenders per cluster & other materials @ F$140k / cluster PMT @ N1m per personnel X 3 persons x 2 months - F$40k Total = F$1.8m | S18391 - Mechanical Modification Works - Swamp | Adequate ceiling but time extension required | Ovuorho | What is worst case scope scenairo | Execution contract NG01020936 identified for use. Loaded in IAP.
121 | C_ESCB_WS3_Z17 | SWAMP WEST | Facility Mechanical Upgrade West | Install a functional fire alarm system and zone it to the fire panel to indicate locations of trigger detectors in accordance with BS EN 54-11:2001+A1:2006 | 100 |  |  | Contract Rates | NG01008426 | Contract Available with adequate ceiling & time | Ovuorho |  | Okay
123 | C_ESCB_WS3_Z17 | SWAMP WEST | Facility Mechanical Upgrade West | Install exhaust flapper on 6 nos export pump exhausts pipe | 80 |  |  | Contract Rates | NG01005242 - Mechanical Modification Works in SPDC Producing Assets - Swamp | Adequate ceiling but time extension required | Ovuorho |  | Contract for execution identified NG01022439. Loaded in IAP.
125 | C_ESCB_WS3_Z17 | SWAMP WEST | Facility Mechanical Upgrade West | Changeout of obsolete lighting poles to Abacus Collapsible ones (Jacking mechanism) Abacus 12m light pols @ 21 x F$5k - F$105k 1 no. Hydraulic jack - F$5k 4C x 4mm XLPE Armoured cable @ F$4/m x F$1.5km - F$9k Other accessories - F$5k Construction - F$95k Total F$220k | 220 |  |  | Contract Rates: Abacus 12m light pols @ F$21 x F#5k - F$105k 1 no. Hydraulic jack - F$5k 4C x 4mm XLPE Armoured cable @ F$4/m x F$1.5km - F$9k Other accessories - F$5k Construction - F$95k Total F$220k | NG01008426 | Adequate ceiling but time extension required | Ovuorho |  | Okay Would need budget for procurement in 2018.
131 | C_OTUM_WS3_Z17 | SWAMP WEST | Facility Mechanical Upgrade West | Replace the overloaded and damaged cable trays across the flow station. | 150 |  |  | Contract Rates | S18391 - Mechanical Modification Works - Swamp | Adequate ceiling but time extension required | Ovuorho |  | Contract for execution identified NG01021292. Loaded in IAP.
139 | C_FORC_WS3_Z17 | SWAMP WEST | Facility Mechanical Upgrade West | Painting of Yokri Road side Manifolds (1-9) and incorporate hand rails at Yokri | 200 |  |  | Contract Rates | NG01005242 - Mechanical Modification Works in SPDC Producing Assets - Swamp | Adequate ceiling but time extension required | Ovuorho |  | Loaded in IAP, identifying execution contract.
150 | C_FORC_WS3_Z17 | SWAMP WEST | Facility Mechanical Upgrade West | Yokri helipad drawing production (painting and marking) | 35 |  |  | Contract Rates | NG01005242 - Mechanical Modification Works in SPDC Producing Assets - Swamp | Adequate ceiling but time extension required | Ovuorho |  | Loaded in IAP, identifying execution contract.
158 | C_FORC_WS3_Z17 | SWAMP WEST | Facility Mechanical Upgrade West | Anti corrosion painting of compressor house structure and repair of leaking roof | 250 |  | 120 | Contract Rates | NG01005242 - Mechanical Modification Works in SPDC Producing Assets - Swamp | Adequate ceiling but time extension required | Ovuorho |  | Loaded in IAP, identifying execution contract.