## Onshore
IMPLEMENTATION/TRANSITION PLAN - BROWNFIELD ENGINEERING AND MAINTENANCE SERVICES FOR SPDC
CONTRACT NUMBER | L03784
CONTRACT NAME | BROWNFIELD ENGINEERING AND MAINTENANCE SERVICES FOR EA FPSO and Various Minor Contracts for Onshore
CONTRACT HOLDER | Victor Abiagom
CONTRACT OWNER | DAVID MARTIN / Andrew Breeze
CATEGORY LEAD | AKINYEMI AKINYOADE
PRINCIPAL SHELL LOCATIONS/BUSINESSES AFFECTED | ALL SPDC ASSET HUBS
CONTRACTOR COMPANY NAME: | Various
Contractor Address:
Tel . No.
CONTRACTOR CONTRACT MANAGER | <Contractor Nominee>
Contract Start Date: | 2018-01-01
Contract Expiry Date: | 2020-12-31
Old Contracts | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | Action Party | STATUS
Compile list of third party activities being executed by vendor | [10 empty] | Live database in place | bar: 2017-11-01 to 2017-12-01
Compile list of ongoing jobs at the vendor's yard | [9 empty] | CH/Assets | Yet to commence | bar: 2017-11-01 to 2017-12-01
Compile list of undelivered procurement requests with vendor | [9 empty] | CH/Assets | Yet to commence | bar: 2017-11-01 to 2017-12-01
Compile list of third party activities being executed by vendor | [9 empty] | CH/Assets | Yet to commence | bar: 2017-11-01 to 2017-12-01
Compile list of tools on SPDC Locations (owned by both SPDC and Contractors) | [9 empty] | CH/Assets | bar: 2017-11-01 to 2017-12-01
Conduct risk assessment of ongoing activities by vendor, establish what will be done about uncompleted activities at new contract award | [9 empty] | CH/Assets, CM | Yet to commence | bar: 2017-11-01 to 2017-12-01
Relocate non-committed materials, equipment to new vendor's yard | [10 empty] | Not required
Estimate cost of moving materials, equipment to new vendor's yard | [10 empty] | Not required
Agree process for repossession of unused goods and services | [9 empty] | CH, Assets | bar: 2017-11-01 to 2017-12-01
Prepare proposal for time extension | [9 empty] | CH, CM | To be reviewed | bar: 2017-12-01
Engage NAPIMS on need for time extension + proposed duration | [9 empty] | CH, CM | To be reviewed | bar: 2017-12-01
Process written off materials and dispose | [9 empty] | CH, Assets | To be reviewed
Develop tracker for new requests | [9 empty] | CH | To be reviewed | bar: 2017-12-01
Close old POs and create new ones to accommodate outstanding activities on the new contract | [9 empty] | CH
Winding down period & ID/GI-D retrievals | [9 empty] | CH
New Contract - NG01016625
Commercial evaluation | [9 empty] | CH, CM | bar: 2017-11-01 to 2017-12-01
Revalidate MOUs as required | [9 empty] | CH, CM | bar: 2017-11-01 to 2017-12-01
Secure MTB approval for award and LDL | [9 empty] | CH, CM | bar: 2017-11-01 to 2017-12-01
Secure NAPIMS approval | [9 empty] | CH, CM | bar: 2017-11-01 to 2017-12-01
Secure NCDMB approval | [9 empty] | CM, NCD | bar: 2017-11-01 to 2017-12-01
Establish existing skill sets for transfer from old contracts | bar: 2017-11-01 to 2017-12-01
Review contract terms and conditions | bar: 2017-12-01
Sign new contract (Interim) | bar: 2017-12-01 to 2018-01-01
Engagement on transfer of skilled personnel from old to new vendor | bar: 2017-12-01 to 2018-01-01
Load new agreement in SAP and secure release | bar: 2017-12-01 to 2018-01-01
Secure ID cards/Access for new vendor's representatives | bar: 2017-12-01 to 2018-01-01
Receive, check and file insurance certificates/financial guarantees | bar: 2017-12-01 to 2018-01-01
Relocate materials, equipment to new vendor's yard | bar: 2017-12-01 to 2018-01-01
Set-up Contract Management Plan | bar: 2017-12-01 to 2018-01-01
Operational Activities
Mobilise and prepare sites | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set up RFQ process | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Exchange delivery/invoice addresses, bank/tax numbers | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up sign-off approval levels | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Agree order, call-off, shipment, receipt and payment process | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up invoice, payment and warning cycle times | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Align IT interfaces/protocols - Sharepoint access | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
HSSE Activities
Conduct HSSE workshop and fill-out initial checklist | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Ensure proper personnel and vehicle registration at each site for entry | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Lay down objectives, roles and responsibilities | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Agree drug testing and medical requirements for supplier personnel | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up hazards and effects management process | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up HSSE training and exchange protective equipment | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Approve vendor's HSSE Management Plan | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up, receive and file HSSE certification | bar: 2018-01-01 to 2018-02-01
Define risk management strategy | bar: 2018-01-01 to 2018-02-01
Turnaround Maintenance (2018, per Asset)
Establish status of third party activities | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2018-02-01
Compliance Activities
Review sub-suppliers' quality systems and monitoring | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Approve Supplier's plan for compliance to regulatory and quality standards" | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Review and Secure approval of NCD plan | bar: 2017-11-01 to 2017-12-01
Performance Activities
Set-up KPI templates | [9 empty] | CH | bar: 2017-11-01 to 2017-12-01
Set-up KPI reporting and monitoring processes | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Set-up incentives and penalties | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
List identified risks following risk assessment | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
List agreed risk mitigation actions | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Set-up fallback solution and contingency plan | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Identify counterparts and focal points | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Conduct kick off meetings (internal and external) | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Define authority levels and reporting relationships | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Agree targets and milestones for contract and relationship | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Set-up schedule for joint site visits and periodic review meetings | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Establish escalation process | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Identify all stakeholders | [9 empty] | CH, VENDORS | bar: 2017-11-01; 2018-01-01 to 2018-03-01
Revalidate roles and responsibilities for Shell and Vendor | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Set-up communication plan external/internal and update (what?, when?, whom?) - | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
| 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01
LEGEND
SPDC ACTIVITY | bar: 2017-11-01
SPDC AND NEW VENDOR ACTIVITY | bar: 2017-11-01
SPDC AND OLD VENDOR ACTIVITY | bar: 2017-11-01
SPDC AND NAPIMS/NCDMB ACTIVITY | bar: 2017-11-01

## Offshore
IMPLEMENTATION/TRANSITION PLAN - BROWNFIELD ENGINEERING AND MAINTENANCE SERVICES FOR SPDC
CONTRACT NUMBER | L03784
CONTRACT NAME | BROWNFIELD ENGINEERING AND MAINTENANCE SERVICES FOR EA FPSO and Various Minor Contracts for Onshore
CONTRACT HOLDER | DEJI BALOGUN
CONTRACT OWNER | DAVID MARTIN
CATEGORY LEAD | AKINYEMI AKINYOADE
PRINCIPAL SHELL LOCATIONS/BUSINESSES AFFECTED | ALL SPDC ASSET HUBS
CONTRACTOR COMPANY NAME: | Various
Contractor Address:
Tel . No.
CONTRACTOR CONTRACT MANAGER | <Contractor Nominee>
Contract Start Date: | 2018-01-01
Contract Expiry Date: | 2020-12-31
Old Contract -L03784 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | Action Party | STATUS
Compile list of third party activities being executed by vendor | [10 empty] | Live database in place | bar: 2017-11-01 to 2017-12-01
Compile list of ongoing jobs at the vendor's yard | [9 empty] | CH/Assets | Yet to commence | bar: 2017-11-01 to 2017-12-01
Compile list of undelivered procurement requests with vendor | [9 empty] | CH/Assets | Yet to commence | bar: 2017-11-01 to 2017-12-01
Compile list of third party activities being executed by vendor | [9 empty] | CH/Assets | Yet to commence | bar: 2017-11-01 to 2017-12-01
Compile list of tools offshore (owned by both SPDC and Contractors) | [9 empty] | CH/Assets | bar: 2017-11-01 to 2017-12-01
Conduct risk assessment of ongoing activities by vendor, establish what will be done about uncompleted activities at new contract award | [9 empty] | CH/ EA team/ CM | Yet to commence | bar: 2017-11-01 to 2017-12-01
Conduct risk assessment of ongoing activities by vendor, establish what will be done about uncompleted fabrication activities at new contract award | [9 empty] | CH | Not required | bar: 2017-11-01 to 2017-12-01
Relocate non-committed materials, equipment to new vendor's yard | [10 empty] | Not required
Estimate cost of moving materials, equipment to new vendor's yard | [10 empty] | Not required
Agree process for repossession of unused goods and services | bar: 2017-12-01
Prepare proposal for time extension | [10 empty] | Done | bar: 2017-12-01
Engage NAPIMS on need for time extension + proposed duration | [10 empty] | In progress | bar: 2017-12-01
Process written off materials and dispose | [10 empty] | In progress
Develop tracker for new requests | [10 empty] | Done | bar: 2017-12-01
Close old POs and create new ones to accommodate outstanding activities on the new contract
Winding down period & ID/GI-D retrievals
New Contract - NG01016625
Commercial evaluation | [9 empty] | CH, CM | bar: 2017-11-01 to 2017-12-01
Revalidate MOUs as required | [9 empty] | CH, CM | bar: 2017-11-01 to 2017-12-01
Secure MTB approval for award and LDL | [9 empty] | CH, CM | bar: 2017-11-01 to 2017-12-01
Secure NAPIMS approval | [9 empty] | CH, CM | bar: 2017-11-01 to 2017-12-01
Secure NCDMB approval | [9 empty] | CM, NCD | bar: 2017-11-01 to 2017-12-01
Establish existing skill sets for transfer from old contracts | bar: 2017-11-01 to 2017-12-01
Review contract terms and conditions | bar: 2017-12-01
Sign new contract (interim) | bar: 2017-12-01 to 2018-01-01
Engagement on transfer of skilled personnel from old to new vendor | bar: 2017-12-01 to 2018-01-01
Load new agreement in SAP and secure release | bar: 2017-12-01 to 2018-01-01
Secure ID cards/Access for new vendor's representatives | bar: 2017-12-01 to 2018-01-01
Receive, check and file insurance certificates/financial guarantees | bar: 2017-12-01 to 2018-01-01
Relocate materials, equipment to new vendor's yard | bar: 2017-12-01 to 2018-01-01
Set-up Contract Management Plan | bar: 2017-12-01 to 2018-01-01
Operational Activities
Mobilise and prepare sites | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set up RFQ process | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Exchange delivery/invoice addresses, bank/tax numbers | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up sign-off approval levels | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Agree order, call-off, shipment, receipt and payment process | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up invoice, payment and warning cycle times | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Align IT interfaces/protocols - Sharepoint access | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
HSSE Activities
Conduct HSSE workshop and fill-out initial checklist | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Ensure proper personnel and vehicle registration at each site for entry | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Lay down objectives, roles and responsibilities | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Agree drug testing and medical requirements for supplier personnel | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up hazards and effects management process | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up HSSE training and exchange protective equipment | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Approve vendor's HSSE Management Plan | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-02-01
Set-up, receive and file HSSE certification | bar: 2018-01-01 to 2018-02-01
Define risk management strategy | bar: 2018-01-01 to 2018-02-01
Turnaround Maintenance (2018)
Establish status of third party activities | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2018-02-01
Compliance Activities
Review sub-suppliers' quality systems and monitoring | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Approve Supplier's plan for compliance to regulatory and quality standards" | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Review and Secure approval of NCD plan | bar: 2017-11-01 to 2017-12-01
Performance Activities
Set-up KPI templates | [9 empty] | CH | bar: 2017-11-01 to 2017-12-01
Set-up KPI reporting and monitoring processes | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Set-up incentives and penalties | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
List identified risks following risk assessment | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
List agreed risk mitigation actions | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Set-up fallback solution and contingency plan | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Identify counterparts and focal points | [9 empty] | CH, ASSETS | bar: 2017-11-01 to 2017-12-01
Conduct kick off meetings (internal and external) | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Define authority levels and reporting relationships | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Agree targets and milestones for contract and relationship | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Set-up schedule for joint site visits and periodic review meetings | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Establish escalation process | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Identify all stakeholders | [9 empty] | CH, VENDORS | bar: 2017-11-01; 2018-01-01 to 2018-03-01
Revalidate roles and responsibilities for Shell and Vendor | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
Set-up communication plan external/internal and update (what?, when?, whom?) - | [9 empty] | CH, VENDORS | bar: 2018-01-01 to 2018-03-01
| 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | Action Party
LEGEND
SPDC ACTIVITY | bar: 2017-11-01
SPDC AND NEW VENDOR ACTIVITY | bar: 2017-11-01
SPDC AND OLD VENDOR ACTIVITY | bar: 2017-11-01
SPDC AND NAPIMS/NCDMB ACTIVITY | bar: 2017-11-01