## SPDC mtce & Assets
TRANSITION PLAN - Maintenance Intervention and Support Services for SPDC Assets (Crude Oil & Gas Facilities).
CONTRACT NUMBER | TBA
CONTRACT NAME | Maintenance Intervention and Support Services for SPDC Assets (Crude Oil & Gas Facilities).
CONTRACT HOLDER | KEN IBENEME
CONTRACT OWNER | TIJANI TUNDE
CATEGORY LEAD/CONTRACT MANAGER | EMEKA ESEKODY
PRINCIPAL SHELL LOCATIONS/BUSINESSES AFFECTED | ALL SPDC ASSET HUBS
CONTRACTOR COMPANY NAME: | TBA
Contractor Address:
Tel . No.
CONTRACTOR CONTRACT MANAGER | <Contractor Nominee>
Contract Start Date: | 2018-11-01
Contract Expiry Date: | 2020-10-31
Contract Number - TBA | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | >Nov 2018 | Action Party | STATUS
Close out MTB directives and secure sign-off of strategy submission | [13 empty] | CH, CM | bar: 2017-11-01
Transmit strategy to NAPIMS | [13 empty] | CH, CM | bar: 2017-11-01
Complete NC plan, sign-off and transmit to NCDMB | [13 empty] | CH, CM, NC | bar: 2017-11-01
Secure NAPIMS approval of strategy | [13 empty] | CH, CM | bar: 2017-12-01
Secure NCDMB approval of strategy | [13 empty] | CM, NCD | bar: 2018-01-01
Publish advert and issue technical ITT | [13 empty] | CM | bar: 2018-02-01
Evaluate technical bids and agree outcome with NAPIMS | [13 empty] | CM, CH, NAPIMS | bar: 2018-03-01
Secure MTB approval of Part A2 | [13 empty] | CH, CM | bar: 2018-04-01
Develop and issue commercial ITT | [13 empty] | CM | bar: 2018-05-01
Complete commercial evaluation and agree outcome with NAPIMS | [13 empty] | CH, CM, NAPIMS | bar: 2018-06-01
Secure Nigerian content compliance certificate (NCDMB approval for commercial evaluation) | [13 empty] | NC, NCDMB | bar: 2018-07-01
Secure MTB approval of Part B | [13 empty] | CH, CM | bar: 2018-08-01
Transmit approval and secure NAPIMS approval of contract award | [13 empty] | CM, CH, | bar: 2018-08-01
Award contract | [13 empty] | CM | bar: 2018-09-01
Complete documentations and expedite SAP release of contract | bar: 2018-10-01
Operational Activities
Mobilise and prepare sites | [13 empty] | CH, VENDORS
Set up RFQ process | [13 empty] | CH, VENDORS
Exchange delivery/invoice addresses, bank/tax numbers | [13 empty] | CH, VENDORS
Set-up sign-off approval levels | [13 empty] | CH, VENDORS
Agree order, call-off, shipment, receipt and payment process | [13 empty] | CH, VENDORS
Set-up invoice, payment and warning cycle times | [13 empty] | CH, VENDORS
Align IT interfaces/protocols - Sharepoint access | [13 empty] | CH, VENDORS
HSSE Activities
Conduct HSSE workshop and fill-out initial checklist | [13 empty] | CH, VENDORS
Ensure proper personnel and vehicle registration at each site for entry | [13 empty] | CH, VENDORS
Lay down objectives, roles and responsibilities | [13 empty] | CH, VENDORS
Agree drug testing and medical requirements for supplier personnel | [13 empty] | CH, VENDORS
Set-up hazards and effects management process | [13 empty] | CH, VENDORS
Set-up HSSE training and exchange protective equipment | [13 empty] | CH, VENDORS
Approve vendor's HSSE Management Plan | [13 empty] | CH, VENDORS
Set-up, receive and file HSSE certification
Define risk management strategy
Set-up KPI templates | [13 empty] | CH
Set-up KPI reporting and monitoring processes | [13 empty] | CH, ASSETS
Set-up incentives and penalties | [13 empty] | CH, ASSETS
List identified risks following risk assessment | [13 empty] | CH, ASSETS
List agreed risk mitigation actions | [13 empty] | CH, ASSETS
Set-up fallback solution and contingency plan | [13 empty] | CH, ASSETS
Identify counterparts and focal points | [13 empty] | CH, ASSETS
Conduct kick off meetings (internal and external) | [13 empty] | CH, VENDORS
Define authority levels and reporting relationships | [13 empty] | CH, VENDORS
Agree targets and milestones for contract and relationship | [13 empty] | CH, VENDORS
Set-up schedule for joint site visits and periodic review meetings | [13 empty] | CH, VENDORS
Establish escalation process | [13 empty] | CH, VENDORS
Identify all stakeholders | [13 empty] | CH, VENDORS
Revalidate roles and responsibilities for Shell and Vendor | [13 empty] | CH, VENDORS
Set-up communication plan external/internal and update (what?, when?, whom?) - | [13 empty] | CH, VENDORS
| 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | >Nov 2018
LEGEND
SPDC ACTIVITY | bar: 2017-11-01
SPDC AND NEW VENDOR ACTIVITY | bar: 2017-11-01
SPDC AND NAPIMS/NCDMB ACTIVITY | bar: 2017-11-01