## Sheet1
S/N | Tender Number | Tender Title | Pre-Work | [10 empty] | Contract Initiation | Approval of Contract Strategy | [5 empty] | Post MTB Approval of Part A1 | [5 empty] | Technical Bids and Evaluation | [16 empty] | Commercial Evaluation & Contract Award
|  |  | Business Need | Contract Holder appointment letter | Scope Documentation and Sourcing Strategy | Engage NAPIMS | Prepare Cost estimate | Prepare HSE – Risk assessment Matrix | Review HSE Risk assessment Matrix | Prepare NCD Strategy | Prepare Technical Evaluation criteria and high-level Technical Questionnaire | Prepare Commercial Evaluation Criteria | Prepare Advertisement template | Create Sourcing Project in Ariba | Check status of NipeX pre-qualified bidders for de-registered vendors | Finalise Part A1 | Signing of Part A1 submission | Submit Part A1 submission to the TB Secretariat | Obtain MTB approval | Transmit Approved Part A1 to NAPIMS | Create collaboration room | Load Opportunity phase and obtain approval from NAPIMS via NipeX and a formal letter | Forward Evaluation Criteria & Advert Template | Obtain NAPIMS approval of Part A1 submission | Obtain NCDMB approval of Part A1 submission | Publish Advert in Nipex and the National newspapers | Technical ITT | Download bidders in accordance with earlier approval. | Obtain NAPIMS approval of bidders list | Submit Technical ITT to NAPIMS in NipeX | Forward Technical ITT via e-mail to NCD | Upload Technical ITT | Publish Technical ITT | Upload Technical Scoring guide | Down load Technical bids | Assess technical capabilities of vendors | Conduct site visits and reconcile independent evaluations | Prepare Report | Sign Report | Prepare Part A2 submission | Obtain NCD approval | Obtain NCDMB approva of commercial ITT | Obtain NAPIMS approva of commercial ITT | Publish commercial ITT in NipeX | Download commercial bids | Independent evaluation/ preparation for NCDMB Certification | Sign Evaluation Results | Reconcile/align results with NCDMB | Prepare Part B submission | Tender Board approve Part B | Obtain NCDMB Certification | Send formal transmittal to NAPIMS | Contract document | Obtain NAPIMS approval | Sign contract
1 | NG01023917 | Maintenance intervention support services SPDC Assets (Oil & Gas) – MRTA major contract. | Q3 2017 | Q3 2017 | Q3 2017 | Q4 2017 | Q4 2017 | Q4 2017 | Q4 2017 | Q4 2017 | Q4 2017 | Q4 2017 | Q1 2018 | Q12018 | Q1 2018 | Q1 2018 | Q1 2018 | Q1 2018 | Q1 2018 | 09/03/18 | Q2 2018 | Q2 2018 | Q2 2018 | Q2 2018 | Q2 2018 | Q2 2018 | Q2 2018 | Q3 2018 | Q4 2018 | Q4 2018 | Q4 2018 | Q4 2018 | Q4 2018 | Q1 2019 | Q2 2019 | Q3 2019 | N/A | Q3 2019 | Q3 2019 | Q1 2020 | Q1 2020 | Q1 2020 | Q1 2020 | Q2 2020 | Q2 2020 | Q3 2020 | Q3 2020 | Q3 2020 | Q3 2020 | Q3 2020 | Q3 2020 | Q3 2020 | Q3 2020 | Q3 2020 | Q3 2020

## Sheet2
4 | NG01003581 | Corporate maintenance of Caterpillar Engines in SDPC | Patrick Attoe/Tola Odumade/Emeka Esekody | Award of contract at negotiated rates rejected by vendors. Transmittal seeking NAPIMS steers already sent. Awaiting NAPIMS response. | JV OIL: NAPIMS engaged. NAPIMS to revert with date/venue for tripartite meeting. Copy of NAPIMS letter already sent to DM | 2017-09-25 | Emeka Esekody | Strategy circulated for review by stakeholders. NAPIMS/MTB approved contract loaded and activated. Awaiting release | Strategy circulated for review by stakeholders. NAPIMS/MTB approved contract loaded and activated. Awaiting release | 2018-05-18
6 | NG01016625 | Brownfield Engineering and Maintenances Services Contract | Akinyemi Akinyoade/ Deji Balo | NAPIMS letter approving to progress to Commercial received 4 weeks ago. Currently, putting together a Part A2 to request MTB approval to endorse the Commercial Template for publishing. there are 5 categories on the contract. Category B replaces the current Production MAPO contract (manpower) | Progress with Commercial tender and award contract by Q4 2017 | 2017-09-14 | Akinyemi Akinyoade | Contract already commenced. Transition being monitored. | Contract already commenced. Transition being monitored.
8 | NG02003605 | Prov. of Elect. & Instr. Mtce Svces for BONGA (BMM Cat-C) | Seun Akinyemi/ Paul Orhoro | Presented Part-B to MTB. | Review MTB directives and prepare for rerepresentation | Open | IK Nwaokweanwa /Paul Orhoro | Contract now active | Contract now active | 2018-04-24