## Slide 1: Project Title: Replace corroded F/l session to restore Escr13S prod by April 2021
Business Case/Objectives:
Escravos Well13S was producing at 886 bbl to Escravos Flowstation when it was shut-in October 20, 2020 on flowline issue – Corrosion failure of a section of the flowline.
In the drive to meet Escravos/Otumara PU OP20 production target, Asset Engineering intervention is required to carry out sectional replacement of Escr13S flowline to restore the current LIP of 886 bbl.
Potential Benefits & Measurement:
Volume Benefit: Restoration of Escr13S to increase production availability of Escravos FS by 886bopd and to meet the PU’s OP20 production target.
Safety & Integrity: Asset Engineering to mobilize to site and carry out sectional replacement of the Escr13S.
Production gains:
Additional production of 886bopd
Implementation Cost: $100K
FCF approx. $1.796m
Critical Success Factors:
Complete sectional replacement of the Escr13S and hydrotest flowline and prove integral.
Escr13S is opened and producing without leaks.
  Project Sponsor: Oyedele Oyebode.
  Team Members: Uzuh Chuks, Eguridu Paul, Obadimeji Olalekan & Charles Miller
  Implementation/Project Lead: Anoruse Thomas
Action | Responsible Team | Timeline
Asset Engineering to scope required section of flowline. | Sagbe Seprebo | March 1, 2021
Secure FTO/CTS | Adedeji Tolulope | March 15, 2021
Secure Budget approval | Sagbe Seprebo | March 8, 2021
Carry out sectional replacement of Escr13S flowline | Sagbe Seprebo/Uche Egunatum | April 30, 2021
Open up Escr13S to flow | Uzuh Chuks /Eguridu Paul | L4: April 30, 2021