## Slide 1: De-bottlenecking of Estuary Cluster-5 Bulk lines TO optimize PRODUCTION
Current Conditions/Opportunity
Background/Business Case
Sign-off
(Initial) Goals
Define the problem or opportunity, as simply as possible, in terms of Who, What, When, Where and the Extent.
Why is this project being discussed, what is the problem that needs to be addressed?
De-bottlenecking of Estuary Cluster-5 Bulklines for Production optimization. Estuary Cluster-5 in West Asset has four flowing wells (W5L, 22T, 23L & 23S) bulked into one header and one flow line to the flow station thereby creating bulking effect. This led to W5L (400 bopd) & W23L (350 bopd) not producing optimally. The associated monthly deferment is 7500bbls. The project is aimed at eliminating this bulking effect that will ensure this deferment stopped.
What is in scope
To investigate the root causes and carry out remedial actions to debottleneck Estuary Cluster -5 at the point where the four wells are co-mingled.
These are the initial goals. You can add to this as more data becomes available.
To unlocked about 7500bbls/month deferment through the out 2018 starting from June.
To create additional flexibility for effective MER testing of the four wells by modifying the Cluster manifold when the Root cause/s is understood before end of May
Flowline/manifold integrity restorations – Assurance Issue
E.t.c
Think SMART and make the goals:
Specific, Measureable, Attainable, Relevant and Time-bound
Name : Akaka Alphonsus and North bank OPS staff Sponsor: Atanda Akintunde Sign-off date: February, 2018
Key milestones: Date:
What is the problem March, 2018
What is the Root cause April, 2018
How to fix it / Implement May-June, 2018
How to Sustain it (SOP) July-August, 2018
Benefits forecasted:
Total Expected Oil Gain = 7500 barrels of oil per month (Free Cash Flow of $226,615/yr = $3.656mln/yr Asset Engineering Estimates = $20,000. Completion Date – June, 2018 - changed to end July 2018
MUST HAVE
Timeline Commitment
Benefits Forecasted
The SWH Asset is deferring approx. 7500bbls /month as a result of this bulking problem.
We have just one Manifold ring out of three rings on the Cluster caused by leaks induced by corrosion
We have only one Flowline/riser available.. The other have a leak due to corrosion.
Go See and Scope the job – Alphonsus and Asset
Engineering
Notes: mins