## Activity
JOINT WORK PLAN - SOKPACO, SOKMECH, SOKELECT, MAINTENANCE EXECUTION, ASSET ENGINEERING, PROJECT & INSPECTION
|  |  |  | 2020-03-12 | [11 empty] | 2020-03-13 | [11 empty] | 2020-03-14 | [12 empty] | 2020-03-15 | [12 empty] | 2020-03-16 | [12 empty] | 2020-03-17 | [12 empty] | 2020-03-18 | [12 empty] | 19/03/2020 | [11 empty] | 20/03/2020 | [12 empty] | 21/3/2020 | [12 empty] | 22/3/2020 | [12 empty] | 23/3/2020 | [12 empty] | 24/3/2020 | [12 empty] | 25/3/2020 | [12 empty] | 26/3/2020 | [12 empty] | 27/3/2020 | [12 empty] | 28/3/2020 | [12 empty] | 29/3/2020 | [12 empty] | 30/3/2020 | [12 empty] | 2020-03-31 | [12 empty] | 2020-03-01 | [12 empty] | 2020-03-02 | [12 empty] | 2020-03-03 | [12 empty] | 2020-03-04 | [12 empty] | 2020-03-05 | [12 empty] | 2020-03-06
|  |  |  | FRIDAY | [11 empty] | FRIDAY | [11 empty] | SATURDAY | [12 empty] | SUNDAY | [12 empty] | MONDAY | [12 empty] | TUESDAY | [12 empty] | WEDNESDAY | [12 empty] | THURSDAY | [11 empty] | FRIDAY | [12 empty] | SATURDAY | [12 empty] | SUNDAY | [12 empty] | MONDAY | [12 empty] | TUESDAY | [12 empty] | WEDNESDAY | [12 empty] | THURSDAY | [12 empty] | FRIDAY | [12 empty] | SATURDAY | [12 empty] | SUNDAY | [12 empty] | MONDAY | [12 empty] | TUESDAY | [12 empty] | WEDNESDAY | [12 empty] | THURSDAY | [12 empty] | FRIDAY | [12 empty] | SATURDAY | [12 empty] | SUNDAY | [12 empty] | MONDAY
|  |  |  | DAY -7 | [11 empty] | DAY -6 | [11 empty] | DAY -5 | [12 empty] | DAY -4 | [12 empty] | DAY -3 | [12 empty] | DAY -2 | [12 empty] | DAY -1 | [12 empty] | DAY 1 Soku GP Plant Shutdown Depressurization | [11 empty] | DAY 2 | [12 empty] | DAY 3 | [12 empty] | DAY 4 | [12 empty] | DAY 5 | [12 empty] | DAY 6 | [12 empty] | DAY 7 | [12 empty] | DAY 8 | [12 empty] | DAY 9 | [12 empty] | DAY 10 | [12 empty] | DAY 11 | [12 empty] | DAY 12 | [12 empty] | DAY 13 | [12 empty] | DAY 14 | [12 empty] | DAY 15 | [12 empty] | DAY 16 | [12 empty] | DAY 17 | [12 empty] | DAY 18 | [12 empty] | DAY 19
Task No. | Task DESCRIPTION | Action Party | No. of personnel | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
O1 | SOKOPER - Shutdown, depressurization of Gas plant
1 | Trigger ESD and depressurize the gas Plant | Piate/ Uranta | 2 x SOKOPER 6 x FIELD OPER | bar: DAY 1 Soku GP Plant Shutdown Depressurization 7 to DAY 1 Soku GP Plant Shutdown Depressurization 13
P1 | 1 Yearly ESD Test | bar: DAY -7 7 to DAY -3 19; DAY 1 Soku GP Plant Shutdown Depressurization 7 to DAY 4 19; DAY 11 7 to DAY 19 19
1 | Activate e-permit and other necessary documents. | Usiagu/Oluseye | 1 (1 X SOKINST) | bar: DAY 1 Soku GP Plant Shutdown Depressurization 11; DAY 3 7; DAY 4 7; DAY 5 7; DAY 6 7
2 | Briefing/TBT Prior to ESD initation in CCR. | Usiagu/Oluseye | 20 ( 6 X SOKINST, 8 X SOKOPER, 1 X MSV) | bar: DAY 1 Soku GP Plant Shutdown Depressurization 10
3 | Presonnel at blowdown valve units to identify stuck valves. | Usiagu/Oluseye | 20 ( 6 X SOKINST, 8 X SOKOPER, 1 X MSV) | bar: DAY 1 Soku GP Plant Shutdown Depressurization 14 to DAY 1 Soku GP Plant Shutdown Depressurization 15
4 | Time depressurisation rate. | Usiagu/Oluseye | 2 (1 X SOKINST, 1 X SOKOPER) | bar: DAY 1 Soku GP Plant Shutdown Depressurization 16
5 | Open stuck blowdown valves/Reapair and reinstall failed valves | Usiagu/Oluseye | 5 (5 X SOKINST) | bar: DAY 1 Soku GP Plant Shutdown Depressurization 13 to DAY 1 Soku GP Plant Shutdown Depressurization 18; DAY 2 8 to DAY 2 11; DAY 2 13 to DAY 2 18; DAY 3 8 to DAY 3 11; DAY 3 13 to DAY 3 18; DAY 4 8 to DAY 4 11; DAY 4 13 to DAY 4 18
6 | Walk round the plant to identify any leaks and rectify if found | Usiagu/Oluseye | 8 (4 X SOKINST, 4 X SOKOPER) | bar: DAY 5 8 to DAY 5 11
7 | House keeping. | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 5 13 to DAY 5 18
8 | Prepare ,review and submit ESD report | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 6 8 to DAY 6 11; DAY 6 13 to DAY 6 18
P2 | Replacement of defective Junction Box , 69JE141 | bar: DAY -7 7 to DAY -3 19; DAY 1 Soku GP Plant Shutdown Depressurization 7 to DAY 4 19; DAY 11 7 to DAY 19 19
1 | Actvivate e-permit/tool box talk | Usiagu/Oluseye | 3 (3X SOKINST) | bar: DAY 2 7
2 | Carryout Electrical Isolation/ Verify Isolation /Walk the line | Usiagu/Oluseye | 3 (3 X SOKINST, 1 X SOKELECT) | bar: DAY 2 8
3 | Remove all instrument cable and terminal blocks | Usiagu/Oluseye | 3 (3 X SOKINST) | bar: DAY 2 9
4 | loose cable glands /lock nuts | Usiagu/Oluseye | 3 (3 X SOKINST) | bar: DAY 2 10
5 | remove old Junction box and install new junction box | Usiagu/Oluseye | 3 (3 X SOKINST) | bar: DAY 2 10 to DAY 2 11
6 | install instruments cables and terminate | Usiagu/Oluseye | 3 (3 X SOKINST) | bar: DAY 2 13 to DAY 2 17
7 | tight cable glands and lock nuts | Usiagu/Oluseye | 3 (3 X SOKINST) | bar: DAY 2 14 to DAY 2 17
8 | confirm tighteness | Usiagu/Oluseye | 3 (3 X SOKINST) | bar: DAY 2 17
9 | Safety "Ranger" (permit holder) to reviews steps | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 2 18
10 | House keeping. | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 2 18
P3 | Recertification of T5501 Relief Valve 55RV 002 | bar: DAY -7 7 to DAY -3 19; DAY 1 Soku GP Plant Shutdown Depressurization 7 to DAY 4 19; DAY 11 7 to DAY 19 19
1 | Actvivate e-permit/tool box talk | Usiagu/Oluseye | 8 (2 X SOKOPER, 3 X WORKSHOP. 3 X LOGISTICS) | bar: DAY 2 7
2 | Confirm Isolation /Pressure /walk the line | Usiagu/Oluseye | 2 (1 X SOKINST, 1 X SOKOPER) | bar: DAY 2 8
3 | loose RV bolts/nuts | Usiagu/Oluseye | 5 (2 X SOKINST, 3 X WORKSHOP) | bar: DAY 2 9
4 | Remove valve from Tank Top (crane/manual ops) | Usiagu/Oluseye | 8 (2 X SOKOPER, 3 X WORKSHOP. 3 X LOGISTICS) | bar: DAY 2 10 to DAY 2 11
5 | Send RV to IA worskop for recertification | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 2 11; DAY 2 13 to DAY 2 14
6 | Receive recertified RV in Soku gas plant | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 5 11; DAY 5 13 to DAY 5 17
7 | Install RV on T5501 | Usiagu/Oluseye | 8 (2 X SOKOPER, 3 X WORKSHOP. 3 X LOGISTICS) | bar: DAY 5 14 to DAY 5 17
8 | Commission and confirm tighteness | Usiagu/Oluseye | 4 (2 X SOKINST, 3 X WORKSHOP) | bar: DAY 5 17 to DAY 5 18
9 | Safety "Ranger" permit holder to review steps. | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 2 18; DAY 5 18; DAY 19 19
10 | House keeping. | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 2 18; DAY 5 18
P4 | Replacement of 32LCV001 | bar: DAY -7 7 to DAY -3 19; DAY 1 Soku GP Plant Shutdown Depressurization 7 to DAY 4 19; DAY 11 7 to DAY 19 19
1 | Actvivate e-permit/tool box talk | Usiagu/Oluseye | 9 (2 X SOKINST, 1 X SOKMECH, 2 X SOKOPER, 3 X LOGISTICS) | bar: DAY 3 7
2 | Confirm Isolation /Pressure /walk the line | Usiagu/Oluseye | 2 (1 X SOKINST, 1 X SOKOPER) | bar: DAY 3 8
3 | Break drain lines downstream and upstream Control valve | Usiagu/Oluseye | 4 (3 X SOKINST, 1 X SOKMECH) | bar: DAY 3 9
4 | loose bolts/nuts | Usiagu/Oluseye | 4 (3 X SOKINST, 1 X SOKMECH) | bar: DAY 3 10
5 | Uninstall control valve and drop valve with crane | Usiagu/Oluseye | 7 (3 X SOKINST, 1 X SOKMECH, 3 X LOGISTICS) | bar: DAY 3 10 to DAY 3 11; DAY 3 13
6 | Install new control valve (make use of new gasket) | Usiagu/Oluseye | 7 (3 X SOKINST, 1 X SOKMECH, 3 X LOGISTICS) | bar: DAY 3 13 to DAY 3 17; DAY 7 7
7 | tight bolts and nuts | Usiagu/Oluseye | 4 (3 X SOKINST, 1 X SOKMECH) | bar: DAY 3 14 to DAY 3 17
8 | Commission drain lines and confirm tighteness | Usiagu/Oluseye | 4 (2 X SOKINST, 2 X SOKOPER) | bar: DAY 3 17 to DAY 3 18
9 | Safety "Ranger" permit holder to review steps. | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 3 17 to DAY 3 18
10 | House keeping. | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 3 18
P5 | Replacement of 21LCV 010 | bar: DAY -7 7 to DAY -3 19; DAY 1 Soku GP Plant Shutdown Depressurization 7 to DAY 4 19; DAY 11 7 to DAY 19 19
1 | Actvivate e-permit/tool box talk | Usiagu/Oluseye | 9 (3 X SOKINST, 1 X SOKMECH, 2 X SOKOPER, 3 X LOGISTICS) | bar: DAY 4 7
2 | Confirm Isolation /Pressure /walk the line | Usiagu/Oluseye | 2 (1 X SOKINST, 1 X SOKOPER) | bar: DAY 4 8
3 | Break drain lines downstream and upstream Control valve | Usiagu/Oluseye | 4 (3 X SOKINST, 1 X SOKMECH) | bar: DAY 4 9
4 | loose bolts/nuts | Usiagu/Oluseye | 4 (3 X SOKINST, 1 X SOKMECH) | bar: DAY 4 10
5 | Uninstall control valve and drop valve with crane | Usiagu/Oluseye | 9 (3 X SOKINST, 1 X SOKMECH, 2 X SOKOPER, 3 X LOGISTICS) | bar: DAY 4 10 to DAY 4 11
6 | Install new control valve (make use of new gasket) | Usiagu/Oluseye | 9 (3 X SOKINST, 1 X SOKMECH, 2 X SOKOPER, 3 X LOGISTICS) | bar: DAY 4 13 to DAY 4 17
7 | tight bolts and nuts | Usiagu/Oluseye | 4 (3 X SOKINST, 1 X SOKMECH) | bar: DAY 4 14 to DAY 4 17
8 | Commission drain lines and confirm tighteness | Usiagu/Oluseye | 3 (2 X SOKINST, 1 X SOKOPER) | bar: DAY 4 17 to DAY 4 18
9 | Safety "Ranger" permit holder to review steps. | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 4 17 to DAY 4 18
10 | House keeping. | Usiagu/Oluseye | 2 (2 X SOKINST) | bar: DAY 4 18
M1 | SOKMECH - Replace 16" x 1500 manual valve updtream HIPPS valve, Train 1
1 | Confirm Isolation and depressurisation of the line | Okiomah/Taylor | 1 X Sokoper 1 X Sokmech | bar: DAY 1 Soku GP Plant Shutdown Depressurization 13 to DAY 1 Soku GP Plant Shutdown Depressurization 15; DAY 6 13
2 | Break the fasteners | Okiomah/Taylor | 1 X Sokmech 3 X Mtce Exec support | bar: DAY 1 Soku GP Plant Shutdown Depressurization 15 to DAY 1 Soku GP Plant Shutdown Depressurization 18; DAY 6 14 to DAY 6 18
3 | Cut and weld 2'' weldolet downstream 16" x 1500# Manual ball valve upstream Train-1 HIPPS | Okiomah/Taylor | bar: DAY 2 8 to DAY 2 11; DAY 6 14 to DAY 6 18
4 | Replace the manual valve | Okiomah/Taylor | 1 X Sokmech 3 X Mtce Exec support 3 x Crane crew | bar: DAY 2 13 to DAY 2 17
4 | Tighten the fasteners | Okiomah/Taylor | 1 X Sokmech 3 X Mtce Exec support | bar: DAY 3 8 to DAY 3 18; DAY 4 8 to DAY 4 18; DAY 5 8 to DAY 5 15
5 | Carry out housekeeping | Okiomah/Taylor | 1 X Sokmech 3 X Mtce Exec support | bar: DAY 5 16 to DAY 5 18
M2 | Replacement of 8nos 2"x1500# manual valves upstream & downstream GRU-2 lean glycol filters, S-4203A/B
1 | Isolate, depressurise and drain the line | Okiomah/Taylor | 1 x Sokmech 2 X Sokoper | bar: DAY 4 15 to DAY 4 18; DAY 5 13
2 | Remove 8nos 2"x1500# manual valves | Okiomah/Taylor | 1 X Sokmech 3 X Crane Crew 3 X Mtce Exec support | bar: DAY 5 9 to DAY 5 12; DAY 5 14 to DAY 5 18
3 | Install new valves and box up | Okiomah/Taylor | 1 X Sokmech 3 X Crane Crew 3 X Mtce Exec support | bar: DAY 6 8 to DAY 6 18; DAY 7 9 to DAY 7 15
4 | Carry out housekeeping | Okiomah/Taylor | 1 X Sokmech 3 X Mtce Exec support | bar: DAY 7 16 to DAY 7 18
M3 | Statutory inspection of vessel (87nos)
1 | Scaffolding and external UT survey | Okiomah/Taylor | 8 | bar: DAY -3 8 to DAY -1 19
2 | Isolate, depressurise and drain the line | Okiomah/Taylor | 2 x Sokelec | bar: DAY 1 Soku GP Plant Shutdown Depressurization 13 to DAY 1 Soku GP Plant Shutdown Depressurization 18
3 | Swing spetackle to open position and drain vessels | Okiomah/Taylor | 2 x Sokmech 1 x Sokoper | bar: DAY 2 7 to DAY 2 12
4 | Unbolt fasternsers and open manhole | Okiomah/Taylor | 1x CSR 12 X contractor crew | bar: DAY 3 8 to DAY 3 18; DAY 4 8 to DAY 4 17; DAY 5 8 to DAY 5 17; DAY 6 8 to DAY 6 12; DAY 7 8 to DAY 7 18
5 | Carry out internal inspection of the vessels | Okiomah/Taylor | 1x CSR 1 X Sokmech
6 | Box -up vessel,fasten bolts and swing spetacle to close position | Okiomah/Taylor | 1x CSR 12 X contractor crew
7 | Continue with external inspection and house keeping | Okiomah/Taylor | 2 x Sokmech 2 x Sokelec | bar: DAY 8 7 to DAY 8 11; DAY 8 13 to DAY 8 18
E1 | SOKELECT- 6YRLY HV Switchboard mtce
1 | Carry out positive isolation on the GNR Switchboard, tag and access the compartments | Ejenake/Ayor | 2 x SokElect | bar: DAY 2 8 to DAY 2 12
2 | Inspect and clean the compartment with vacuum cleaner and ethanol. Ensure tightness of loosed contacts. Carry out necessary continuity tests and reinstate back. | Obinna/Patel | 2 x SokElect | bar: DAY 2 13 to DAY 2 18; DAY 3 8 to DAY 3 12
3 | De-isolate and put in service. | Ejenake/Ayor | 2 x SokElect | bar: DAY 3 13 to DAY 3 15
E2 | SOKELECT- 6YRLY GNR MTCE
1 | Carry out positive isolation on the NER. Disconnect enclosures to assess the resistor components. | Ejenake/Ayor | 2 x SokElect | bar: DAY 3 16 to DAY 3 19
2 | Inspect and clean the resistors compartment with ethanol. Carry out necessary continuity tests and couple the enclosures back. | Obinna/ | 2 x SokElect | bar: DAY 4 8 to DAY 4 11
3 | De-isolate and put in service. | Ejenake/Ayor | 2 x SokElect | bar: DAY 4 12 to DAY 4 14
E3 | SOKELECT- Rerouting of Space heater Cable
1 | Inspect the appropriate cable tray route for the space heater cables. | Adeniran/Ameh | 2 x SokElect/Mtce EXC | bar: DAY 4 15 to DAY 4 19; DAY 5 8 to DAY 5 9
2 | Isolate and disconnect the cables. Reroute and terminate appropriately. | Ejenake/Ayor | 2 x SokElect/Mtce EXC | bar: DAY 4 15 to DAY 4 19; DAY 5 8 to DAY 5 9
E4 | SOKELECT- Replacement of ALCAD Batteries
1 | Carry out positive isolation on the ALCAD existing batteries. | Adeniran/Ameh | ASSET/ MTCE Exc | bar: DAY 5 11 to DAY 5 15
2 | Disconnect the battery terminals and decommission existing batteries. | Adeniran/Ameh | ASSET/ MTCE Exc | bar: DAY 5 16 to DAY 5 19
3 | Replace the new batteries and reconnect the terminals. Follow the manual and commission the batteries. | Adeniran/Ameh | 2 x SokElect/Mtce EXC | bar: DAY 6 8 to DAY 6 19
ME1 | MTCE EXECUTION - Replacement of Corroded Bolts and Nuts
1 | Set up scaffold on affected areas | MTCE EXECUTION | 1x CSR 2 X Mtce Exec support | bar: DAY 1 Soku GP Plant Shutdown Depressurization 13 to DAY 2 11; DAY 2 13 to DAY 3 9
2 | Remove corroded bolts, nuts, affected spools/flanges and defective gaskets, Replace corroded bolts, nuts and defective gaskets with new bolts, nuts and gaskets and flanges/spools respectively | MTCE EXECUTION | 1x CSR 6 X Mtce Exec support | bar: DAY 2 7 to DAY 2 11; DAY 2 13 to DAY 2 18; DAY 3 7 to DAY 3 11; DAY 3 13 to DAY 3 18; DAY 4 7 to DAY 4 11; DAY 4 13 to DAY 4 18
3 | Torque studs and nuts to required valves | MTCE EXECUTION | 1x CSR 6 X Mtce Exec support | bar: DAY 5 7 to DAY 5 11; DAY 5 13 to DAY 5 18; DAY 6 7 to DAY 6 11; DAY 6 13 to DAY 6 18
4 | Check for leaks | MTCE EXECUTION | 1x CSR 6 X Mtce Exec support | bar: DAY 7 7 to DAY 7 18
5 | Dismantle Scaffold | MTCE EXECUTION | 1x CSR 2 X Mtce Exec support | bar: DAY 6 8 to DAY 6 11; DAY 6 13 to DAY 6 18; DAY 7 7 to DAY 7 18
P1 | K2S Confirmed Fire logic implementation
1 | Actvivate e-permit/tool box talk | Adidi/Nuan | 4 (1 X SOKINST, 2 X YOKOGAWA, 1 X ENGINERING ) | bar: DAY 5 7; DAY 6 8; DAY 7 7
2 | Identification of tie-in point in logic drawing/cabinets | Adidi/Nuan | 4 (1 X SOKINST, 2 X YOKOGAWA, 1 X ENGINEERING ) | bar: DAY 5 8 to DAY 5 11
3 | Modification - wiring works | Adidi/Nuan | 2 ( 2 X YOKOGAWA ) | bar: DAY 5 13 to DAY 5 19
4 | Carry out RESET ESD test | Adidi/Nuan | 3 (1 X SOKINST, 2 X YOKOGAWA) | bar: DAY 6 9 to DAY 6 11
5 | Simulate fire from the field | Adidi/Nuan | 3 (1 X SOKINST, 2 X YOKOGAWA)
6 | Confirm that ESD is initiated | Adidi/Nuan | 3 (1 X SOKINST, 2 X YOKOGAWA) | bar: DAY 7 8 to DAY 7 9
7 | Safety "Ranger" permit holder to review steps. | Adidi/Nuan | 2 (2 X SOKINST) | bar: DAY 7 10 to DAY 7 11
8 | House keeping. | Adidi/Nuan | 2 (2 X SOKINST) | bar: DAY 7 10 to DAY 7 11
A1 | Piping Modification for Continuous Corrosion Inhibition injection through the EGGS-1 Pipeline at Soku GP |  | 5
1 | Erect Scaffold | Oraka/Obiakor | bar: DAY -4 7 to DAY -2 19
2 | Isolate the injection unit. | Oraka/Obiakor | bar: DAY 1 Soku GP Plant Shutdown Depressurization 13 to DAY 1 Soku GP Plant Shutdown Depressurization 18
3 | Run additional tubings to the new injection point | Oraka/Obiakor | bar: DAY 2 7 to DAY 2 11; DAY 2 13 to DAY 2 17
4 | Install valves and other components | Oraka/Obiakor | bar: DAY 2 13 to DAY 2 18; DAY 3 7 to DAY 3 12
5 | Unbolt the flange and install the quill | Oraka/Obiakor | bar: DAY 3 13 to DAY 3 17; DAY 4 7 to DAY 4 11
6 | Dismantle Scaffold | bar: DAY 4 14 to DAY 4 18; DAY 5 7 to DAY 5 11
7 | Site clean-up and demobilize | bar: DAY 5 9 to DAY 5 15
A2 | Route Soku GP LP NAG to Soku AG2 & AG3 Compressors |  | 32
1 | Erect Scaffold | Oraka/Obiakor | bar: DAY -7 7 to DAY -2 19
2 | Piping Pre-fab at Laydown Area | Oraka/Obiakor | self loader | bar: DAY -6 7 to DAY -4 19
3 | Radiography of Pre-fab piping | Oraka/Obiakor | bar: DAY -4 7 to DAY -2 19
4 | Isolate the LP NAG line and nitrogen sweep | Oraka/Obiakor | Crane - to move nitrogen tanks to site 19/03 | bar: DAY 1 Soku GP Plant Shutdown Depressurization 14 to DAY 1 Soku GP Plant Shutdown Depressurization 18; DAY 2 8 to DAY 2 12
5 | isolate the 30" flare header and nitrogen sweep the line | Oraka/Obiakor | bar: DAY 2 8 to DAY 2 12; DAY 2 14 to DAY 2 18; DAY 3 7 to DAY 3 11
6 | isolate the buyback relief lines to flare and nitrogen sweep the line | Oraka/Obiakor | Dropped | bar: DAY 3 7 to DAY 3 12; DAY 3 14 to DAY 3 18; DAY 6 13
7 | Decouple the buyback relief valves and relief lines. | Oraka/Obiakor | Dropped | bar: DAY 3 8 to DAY 3 9; DAY 6 13 to DAY 6 17
8 | Cut out the tie-in points on the 16" LP NAG supply to AG1 compressor | Oraka/Obiakor | Crane/ self loader | bar: DAY 3 10 to DAY 3 14; DAY 6 14 to DAY 6 17
9 | Beveling and fitting of two 16" flange joints and tack weld | Oraka/Obiakor | self loader | bar: DAY 3 15 to DAY 3 19
10 | welding of two 16" flange joints | Oraka/Obiakor | bar: DAY 4 8 to DAY 4 12; DAY 4 14 to DAY 4 18
11 | Cut out tie-in point on the 30" flare header | Oraka/Obiakor | Crane | bar: DAY 4 8 to DAY 4 12; DAY 4 14 to DAY 4 18
12 | Radiography of two 16" flange joints | Oraka/Obiakor | bar: DAY 4 19
13 | Beveling and fitting of 30" x 10" reducing tee on the 30" line | Oraka/Obiakor | bar: DAY 5 8 to DAY 5 12; DAY 5 14 to DAY 5 18
14 | Installation of 16" fabricated spools and bolt-up | Oraka/Obiakor | Crane | bar: DAY 5 8 to DAY 5 12; DAY 5 14 to DAY 5 18
15 | welding of two 30" joints on the 30" flare header | Oraka/Obiakor | Crane | bar: DAY 6 8 to DAY 6 12; DAY 6 14 to DAY 6 18; DAY 7 8 to DAY 7 12; DAY 7 14 to DAY 7 18
16 | Radiography of two 30" joints | Oraka/Obiakor | bar: DAY 6 19; DAY 7 19
17 | Bolting-up and torqing of flanges | Oraka/Obiakor | bar: DAY 8 8 to DAY 8 12
18 | leaking testing and Nitrogen preservation of line | Oraka/Obiakor | bar: DAY 8 13 to DAY 8 19
23 | Dismantle Scaffold | Oraka/Obiakor | bar: DAY 9 7 to DAY 9 11; DAY 9 13 to DAY 9 18; DAY 10 7 to DAY 10 11; DAY 10 13 to DAY 10 18; DAY 11 7 to DAY 11 11; DAY 11 13 to DAY 11 18
24 | Site Clean up and Demob | Oraka/Obiakor | bar: DAY 11 7 to DAY 11 11; DAY 11 13 to DAY 11 18; DAY 12 7 to DAY 12 11; DAY 12 13 to DAY 12 18
A3 | Retrofiting of Soku GP Demulfifier injection system |  | 5
1 | Erect Scaffold | Oraka/Obiakor | bar: DAY -3 7 to DAY -2 19
2 | Isolate and depresurise the spool | Oraka/Obiakor | bar: DAY 1 Soku GP Plant Shutdown Depressurization 13 to DAY 1 Soku GP Plant Shutdown Depressurization 17
3 | Disconnect and remove the spool. | Oraka/Obiakor | bar: DAY 2 7 to DAY 2 11
4 | Modify spool at the lay down area | Oraka/Obiakor | bar: DAY 2 14 to DAY 3 10
5 | Radiography of welded joints | Oraka/Obiakor | bar: DAY 3 11 to DAY 3 12
6 | Flushing and pressure testing of spool | Oraka/Obiakor | bar: DAY 3 8 to DAY 3 18
7 | Installation of modified spool | Oraka/Obiakor | bar: DAY 4 7 to DAY 4 12
8 | Commissioning and handover | Oraka/Obiakor | bar: DAY 4 14 to DAY 4 18
9 | Dismantle Scaffold | Oraka/Obiakor | bar: DAY 5 7 to DAY 5 11; DAY 5 13 to DAY 5 18
A4 | Glycol contactor piping replacement-CS to SS |  | 10
1 | Erect Scaffold | Oraka/Obiakor | bar: DAY -7 7 to DAY -2 19
2 | Piping Pre-fab at Laydown Area | Oraka/Obiakor | bar: DAY -7 7 to DAY -2 19
3 | Radiography of Pre-fab piping | Oraka/Obiakor | bar: DAY -7 7 to DAY -2 19
4 | Hydrotest of Pre-fab piping | Oraka/Obiakor | bar: DAY -7 7 to DAY -2 19
5 | Isolate the glycol contactor piping of train 3 | Oraka/Obiakor | bar: DAY 1 Soku GP Plant Shutdown Depressurization 13 to DAY 1 Soku GP Plant Shutdown Depressurization 18
6 | Flushing of glycol contactor liquid outlet lines of train 3 | Oraka/Obiakor | bar: DAY 2 7 to DAY 2 11
7 | Isolate the glycol contactor piping of train 1&2 | Oraka/Obiakor | bar: DAY 2 9 to DAY 2 14; DAY 2 19 to DAY 3 9
8 | Flushing of glycol contactor liquid outlet lines of train 1 & 2. | Oraka/Obiakor | bar: DAY 2 14 to DAY 2 18; DAY 3 8 to DAY 3 12
9 | Cutting-off of 2" Carbon steel pipings around glycol contactor train 3 | Oraka/Obiakor | bar: DAY 3 14 to DAY 3 18
10 | Welding of 4nos of 2" tie-in joints at train 3 glycol contactor area | Oraka/Obiakor | bar: DAY 4 7 to DAY 4 11; DAY 4 13 to DAY 4 18
11 | Replacement of carbon steel spools with matching duplex stainless spools for train 1& 2 | Oraka/Obiakor | bar: DAY 4 7 to DAY 4 11; DAY 4 13 to DAY 4 18; DAY 5 8 to DAY 5 12; DAY 5 14 to DAY 5 18
12 | Cutting-off of 2" Carbon steel pipings around glycol contactor train 1 | Oraka/Obiakor | bar: DAY 5 14 to DAY 5 18
13 | Welding of 5nos of 2" tie-in joints at train 1 glycol contactor area | Oraka/Obiakor | bar: DAY 6 8 to DAY 6 12; DAY 6 15 to DAY 6 19
14 | Cutting-off of 2" Carbon steel pipings around glycol contactor train 2 | Oraka/Obiakor | bar: DAY 6 15 to DAY 6 19
15 | Welding of 6nos of 2" tie-in joints at train 1 glycol contactor area | Oraka/Obiakor | bar: DAY 7 7 to DAY 7 11; DAY 7 13 to DAY 7 17
16 | Radiography of all welded joints for all the trains | Oraka/Obiakor | bar: DAY 7 8 to DAY 7 10; DAY 8 8 to DAY 8 15
17 | pressure testing of fabricated spools / bolt/ up | Oraka/Obiakor | bar: DAY 8 17 to DAY 8 19
19 | Leak testing and nitrogen line preservation for start-up | Oraka/Obiakor | bar: DAY 9 7 to DAY 9 11
20 | Dismantle Scaffold, Clear Site and Demob | Oraka/Obiakor | bar: DAY 9 7 to DAY 9 18; DAY 10 7 to DAY 10 11; DAY 10 13 to DAY 10 18
A5 | Cut and weld 2'' weldolet downstream 16" x 1500# Manual ball valve upstream Train-1 HIPPS |  | 4
1 | Isolate and depresurise the spool | Oraka/Obiakor | bar: DAY 1 Soku GP Plant Shutdown Depressurization 12 to DAY 1 Soku GP Plant Shutdown Depressurization 16
2 | Flushing and Nitrogen sweeping of the lines | Oraka/Obiakor | bar: DAY 1 Soku GP Plant Shutdown Depressurization 16 to DAY 2 8
3 | Cutting off of the obstructing flange. | Oraka/Obiakor | bar: DAY 2 8 to DAY 2 12
4 | Removal of the 16x 1500# ball valve. | Oraka/Obiakor | bar: DAY 2 14 to DAY 2 18; DAY 3 8 to DAY 3 12; DAY 3 14 to DAY 3 18
5 | Tie -in of 3nos of 2" joints | Oraka/Obiakor | bar: DAY 4 8 to DAY 4 12; DAY 4 14 to DAY 4 17
6 | Radiography of welded joints | Oraka/Obiakor | bar: DAY 4 18 to DAY 4 19
7 | pressure testing of fabricated spool and Hand over | Oraka/Obiakor | bar: DAY 5 8 to DAY 5 18
A6 | Soku GP turbo trays installation |  | 10
1 | Depressurize, Isolate and Drain Contactor | Oraka/Obiakor | bar: DAY 1 Soku GP Plant Shutdown Depressurization 14 to DAY 1 Soku GP Plant Shutdown Depressurization 18
2 | Carry out Positive Isolation of Process Connection | Oraka/Obiakor | bar: DAY 2 7 to DAY 2 11
3 | Flush & Drain Residual HC from Contactor | Oraka/Obiakor | bar: DAY 2 8 to DAY 2 12
4 | Open Contactor Manholes and install air blowers | Oraka/Obiakor | bar: DAY 2 14 to DAY 2 18
5 | Erect scaffold | bar: DAY 3 7 to DAY 4 18
6 | Inspect Inlet Device, Lower Mist Eliminator | Oraka/Obiakor | bar: DAY 4 19 to DAY 5 11
7 | Remove Feed Inlet Piping | Oraka/Obiakor | bar: DAY 5 9 to DAY 5 11
8 | Remove Existing Liquid Distributor above Pack | Oraka/Obiakor | bar: DAY 5 13 to DAY 5 17
9 | Remove Existing Upper Mist Eliminator | Oraka/Obiakor | bar: DAY 6 7 to DAY 6 17
10 | Remove Existing Packing | Oraka/Obiakor | bar: DAY 6 14 to DAY 6 17
11 | Weld new caps to chimney tray | Oraka/Obiakor | bar: DAY 7 7 to DAY 7 17
12 | Install Expansion Rings for Odd & Even Turbo | Oraka/Obiakor | bar: DAY 8 7 to DAY 8 17
13 | Install Expansion Rings for Secondary & Primary | Oraka/Obiakor | bar: DAY 9 7 to DAY 9 17
14 | Install Odd & Even Turbo Trays on Expansion | Oraka/Obiakor | bar: DAY 10 7 to DAY 10 17; DAY 11 7 to DAY 11 17; DAY 12 7 to DAY 12 17
15 | Install Secondary Mist Elimnator on Expansion | Oraka/Obiakor | bar: DAY 13 7 to DAY 13 18
16 | Install Support for Versi-Swirl | Oraka/Obiakor | bar: DAY 14 8 to DAY 14 18
17 | Install Versi-Swirl Deck | Oraka/Obiakor | bar: DAY 15 7 to DAY 15 17
18 | Install Primary Mist Eliminator on Expansion | Oraka/Obiakor | bar: DAY 16 7 to DAY 16 17
19 | Install Feed Inlet Piping | Oraka/Obiakor | bar: DAY 17 7 to DAY 17 12
20 | Conduct Final Inspection before Box-up | Oraka/Obiakor | bar: DAY 17 13 to DAY 17 17
21 | Box-up the vessel | Oraka/Obiakor | bar: DAY 18 7 to DAY 18 10
22 | Dismantle Scaffold | Oraka/Obiakor | bar: DAY 10 11 to DAY 10 16; DAY 10 18 to DAY 11 16; DAY 16 13 to DAY 16 18; DAY 17 7 to DAY 17 18
23 | Site Clean up and Demob | Oraka/Obiakor | bar: DAY 11 18 to DAY 12 17; DAY 18 7 to DAY 18 19
R1 | INLINE STATIC MIXER /WATER CUT METER INSTALLATION |  | 20
1 | Load out @ fab yard to jetty and Load onto barge @ KI | ODIMAA DOUGLAS | 4 (1 X Foreman, 2X Mechanical filters , 1 X Helper, ) | bar: DAY -3 8 to DAY -3 18
2 | Movement of barge to work site | ODIMAA DOUGLAS | Logistic | bar: DAY -2 8 to DAY -2 17; DAY -1 8 to DAY -1 17
3 | Movement of Personnel to work site (SPDC flight) | ODIMAA DOUGLAS | 6 (1 XCSR, 1QC mech,1xQC Instr, 1X HSE, 2X Fire crew ) | bar: DAY -1 8 to DAY -1 17
4 | Medical Examination and Site Preparation | ODIMAA DOUGLAS | 20(All personnel ) | bar: DAY -1 8 to DAY -1 17
5 | OffLoad SD materials (logistics requried) | ODIMAA DOUGLAS | 6 (1 X Foreman, 2x Mechanical filters , 1 X Helper 1 welder, 1 welder mate ) | bar: DAY 1 Soku GP Plant Shutdown Depressurization 8 to DAY 1 Soku GP Plant Shutdown Depressurization 17
6 | Isolation (Mechanical) | ODIMAA DOUGLAS | Asset | bar: DAY 1 Soku GP Plant Shutdown Depressurization 12 to DAY 2 10
7 | Flushing / Depressurization | ODIMAA DOUGLAS | Asset | bar: DAY 1 Soku GP Plant Shutdown Depressurization 16 to DAY 2 12
8 | Unbolt the line and cut off section for installation of spool and welding at tie points (lifting required) | ODIMAA DOUGLAS | 11 (1 X Foreman, 2 Mechanical filters , 1 X Helper 1 welder, 1 welder mate, 2x firemen 3xlifting crew ) | bar: DAY 2 9 to DAY 2 13
9 | Install new Prefabricated Piping spools with valves (lifting required) | ODIMAA DOUGLAS | 7(1 X Foreman, 2 Mechanical filters , 1 X Helper 3xlifting crew) | bar: DAY 2 9 to DAY 2 18
10 | Install new piping supports | ODIMAA DOUGLAS | 3 (1 X Foreman, 1 Mechanical filters , 1 X Helper ) | bar: DAY 2 9 to DAY 2 18
11 | NDT | ODIMAA DOUGLAS | 2 (1 X NDT Technician, 1 assistant NDT Techinicain ) | bar: DAY 2 14 to DAY 2 19
12 | Install Gauges and WCM (lifting required) | ODIMAA DOUGLAS | 7 (1 X Foreman, 2 Mechanical filters , 1 X Helper 3xlifting crew) | bar: DAY 3 9 to DAY 3 18
13 | Bolting up installed pre fabricated spools, mixers, WCM and valves | ODIMAA DOUGLAS | 4 (1 X Foreman, 2 Mechanical filters , 1 X Helper ) | bar: DAY 3 9 to DAY 3 19
14 | Power Brushing and touch up paint | ODIMAA DOUGLAS | 2 (1 X Painter , 1 X Helper ) | bar: DAY 4 9 to DAY 4 19
15 | Instrumentation works and System integration | ODIMAA DOUGLAS | 5 (1 X Foreman, 2 instrument technician , 1 X Helper, 1x 1ntergrator ) | bar: DAY 5 9 to DAY 5 18; DAY 6 9 to DAY 6 18
16 | Commissioning | ODIMAA DOUGLAS | 3(2 X Instrument Engineers, 1 X Helper1x 1ntergrator ) | bar: DAY 6 9 to DAY 6 18; DAY 7 9 to DAY 7 18; DAY 8 10 to DAY 8 19
17 | Site cleaning and housekeeping | ODIMAA DOUGLAS | 4 (1 X Foreman, 2 Mechanical filters , 1 X Helper ) | bar: DAY 9 9 to DAY 9 19
18 | Demobilization | ODIMAA DOUGLAS | 3(1 X Foreman, 2 X Helper )
LEGEND
Shutdown Required
Shutdown Not Required