## Slide 1: INSTALLATION OF PDHG ON EA-51 BY AUGUST 2019
Potential Benefits & Measures
Background/Business Case
Project Plan
Eliminate requirement for yearly BHP survey – ca $110K
Reduction in scheduled deferments app. 1.5days annually (774bopd x 1.5 = 1,161 barrels)
Enhanced reservoir management & optimization
Remote monitoring capabilities (over the PI network)
Compliance with WRFM min requirement
TCI (Inhouse design and implementation)
Milestones Timeline
Critical analysis & scope of the PDHG 15 Feb , 2019
Ordering & Confirmation Materials 28 March, 2019
Installation cable trays 28 April 2019
Established Controls points 10 May 2019
Support Installation of device & test 10 June 2019
Documentations as built drawing 10 August 2019
Critical Success Factors
Team Members
Currently, we do manual BHP survey which cost the Asset circa $110k per well, with attendant deferment volumes. The installation of PDHG in EA-51 will enable us get accurate real-time data from the well, which is then used for WRFM & well optimization.
This initiative is a pilot project and is planned to be implemented across the EA Field thereby eliminating the logistics cost of bringing a SEWOP for such activities and associated production deferment.
The total cost of the project is about $220k. However , the EA Ops & Mtce Team will be handling some scope as DIY, thereby reducing the cost to about $120k and OEM Offshore days by 7. On implementation, production deferment avoidance will be app. 1.5days annually (774bopd x 1.5 = 1,161 barrels).
Successful identification of the appropriate spares
Successful ordering of critical materials
Successful HAZID report
Successful MoC review/approval
Project Sponsor: Maichibi Meshach
Project Owner: Chris Ugochukwu / Florence Oyedele
Project Lead: Dele Adigun / Jude Igbinawan
Project Members:
Wilson Oborokumo – PACO Supr
James Agwulonu/Amaku Michael – Maint Supervisor
Amaefuna, Magnus - FMT Coordinator
Stanley Baribote - OPS TL
Umoh Magdalene/Akpaibor Pius - WRFM
Nwachi Ogbonna - AM Integration Supt
Agboola Olufemi/Iboi Andy - SSP
High Level Timeline
LO/L1 25 March 2019
L2 01 April 2019
L3 30 April 2019
L4 31 August 2019
L5 30 September 2019.
Notes: mins