## Equipment Status
IPSC (BBLS)
| TUNU NODE |  |  | 2017 (Gross) | 2018 (Gross) | 2019 (Gross) | 2020 (Gross) | 2021 (Gross) | Proposed "N" | Spare | Excess | Remarks
| TUNU F/S | PUMP-1 | SULZER MSSD PUMP/CAT G3412 | 16401.30 | 22348.98 | 22604.99 | 21766.96 | 30744.5
|  | PUMP-2 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-3 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-4 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-5 | SULZER MSSD PUMP/CAT G3412 | [5 empty] | 3 | 1 | 1 | Decommission the excess and relocate to Central W/S
|  | GAS GEN | CAT G-3512 GAS GENERATOR
|  | DIESEL GEN | CAT D-3412 DIESEL GENERATOR
| BENISEDE F/S | PUMP-2 | SULZER MSSD PUMP/CAT G3412 | 32902.52 | 35778.78 | 35625.16 | 35258.73 | 36469.34
|  | PUMP-4 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-6 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-8 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-10 | SULZER MSSD PUMP/CAT G3412 | [5 empty] | 3 | 2 | 0
|  | GAS GEN | CAT G-3412 GAS GENERATOR
|  | DIESEL GEN | CAT ENGINE/ D3306
| OPUKUSHI F/S | PUMP-2 | FLOW SERVE PUMP 2 /CAT G3412 | 28160.67 | 37936.71 | 37332.63 | 36582.14 | 45758.32
|  | PUMP-4 | FLOW SERVE PUMP 4
|  | PUMP-5 | SULZER PUMP 5 /CAT G3412
|  | PUMP-7 | FLOW SERVE PUMP 7
|  | PUMP-9 | FLOW SERVE PUMP 9 /CAT G3412 | [5 empty] | 3 | 2 | 0
|  | I C GEN-1 | GAS GEN SET 1 / G3516
|  | I C GEN-2 | ICG GAS SET 1 / G3516
|  | GAS GEN | 3306
|  | DIESEL GEN | DIESEL GEN SET 1 D3406
| OGBOTOBO F/S | PUMP-1 | FLOWSERVE Pump Type/Size: DVMX 4X6X10M | Awaits re-entry | Awaits re-entry | 107.523 | 14214.97 | 30992.13
|  | PUMP-2 | FLOWSERVE Pump Type/Size: DVMX 4X6X10M
|  | PUMP-3 | FLOWSERVE Pump Type/Size: DVMX 4X6X10M | [5 empty] | 2 | 1 | 0
GAS GEN
|  | DIESEL GEN | CAT D3508/
ESCRAVOS NODE
| ESCRAVOS BEACH F/S | PUMP-1 | CAT G342 ENGINE/EMSCO PUMP | 16177.88 | 23057.92 | 24696.87 | 23882.65 | 23882.65
|  | PUMP-2 | CAT G342 ENGINE/EMSCO PUMP
|  | PUMP-3 | CAT G342 ENGINE/EMSCO PUMP
|  | PUMP-4 | CAT G342 ENGINE/EMSCO PUMP
|  | PUMP-5 | CAT G342 ENGINE/EMSCO PUMP
|  | PUMP-6 | CAT G342 ENGINE/EMSCO PUMP | [5 empty] | 3 | 2 | 1 | Decommission the excess and relocate to Yokri to replace FWI (2 nos), the decommission FWI pumps to transfer to W/S for keep.
|  | GAS GEN | CAT G3406ENGINE/R4
|  | DIESEL GEN | CAT/
| OTUMARA F/S | PUMP-1 | SULZER MSSD PUMP/CAT G3412 | 62348.63 | 74705.29 | 74066.40 | 74230.41 | 78152.74
|  | PUMP-3 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-4 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-6 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-7 | SULZER MSSD PUMP/CAT G3412
|  | PUMP-8 | SULZER MSSD PUMP/CAT G3412 | [5 empty] | 4 | 2 | 0
|  | GAS GEN | CAT G3412
|  | DIESEL GEN | CAT
| OTUMARA IGPES EXTERRAN | COMP 1 | COMPRESSOR UNIT 1
|  | COMP 2 | COMPRESSOR UNIT 2
NORTHBANK NODE
| SOUTHBANK F/S | PUMP-1 | SULZER MSSD PUMP/CAT G3408 | 32244.37 | 54778.5 | 62297.96 | 63188.27 | 62108.87
|  | PUMP-2 | SULZER MSSD PUMP/CAT 3408
|  | PUMP-4 | CAT G3408 ENGINE/EMSCO PUMP
|  | PUMP-5 | CAT G3408 ENGINE/EMSCO PUMP
|  | PUMP-7 | CAT G3408 ENGINE/EMSCO PUMP
|  | PUMP-9 | CAT G3408 ENGINE/EMSCO PUMP | [5 empty] | 4 | 2 | 0
|  | GAS GEN | CAT G3408 ENGINE
|  | DIESEL GEN | CAT D3306 ENGINE
| NORTHBANK F/S | PUMP-2 | CAT G3408ENGINE/EMSCO PUMP | 11553.87 | 15429.33 | 16804.07 | 15646.01 | 15555.53
|  | PUMP-5 | CAT G342 ENGINE/EMSCO PUMP
|  | PUMP-6 | CAT G3408ENGINE/EMSCO PUMP | [5 empty] | 2 | 1 | 0
|  | GAS GEN | ICG GAS SET G3508
|  | DIESEL GEN | CAT D3306 ENGINE
|  | ICG (GAS GEN) | FYIP ICG (GAS GEN) / G3516
|  | ICG (DIESEL GEN) | FYIP ICG (DIESEL GEN) / G3516
| YOKRI F/S | PUMP-1 | CAT G3408 ENGINE/EMSCO PUMP | 22105.42 | 27419.6 | 33973.6 | 34611.22 | 34241.8
|  | PUMP-2 | CAT G3408 ENGINE/EMSCO PUMP
|  | PUMP-3 | CAT 3306/FWI PUMP
|  | PUMP-4 | CAT 3306/FWI PUMP
|  | PUMP-5 | CAT G3408 ENGINE/EMSCO PUMP
|  | PUMP-6 | CAT G342ENGINE/EMSCO PUMP | [5 empty] | 4 | 2 | 0 | Replace FWI pumps (2 nos) with 1 Emsco pump from Escravos
|  | GAS GEN | CAT 3306
|  | GAS GEN | INTERDEPENDECY G3508
|  | DIESEL GEN | D3512
| YOKRI C/S | GAS COMP-1 | GASLIFT COMPRESSOR
|  | GAS COMP-2 | GASLIFT COMPRESSOR
2
NOTE:
1 | N = no. of required pumps compare with station IPSC
2 | Philosophy = N+1 (when N is less than 3)
3 | Philosophy becomes N+2 (when N = or greater than 3),
4 | FWI pumps are obsolete with minimal OEM support, spares are scare with high maintenance cost. Pump throughput circa 3Kbopd, 2 nos can be replaced by 1 Emsco pump as proposed above.
5 | The 3 pumps (1 sulzer pump from Tunu and 2 FWI pumps from Yokri) will be relocated to W/S, to serve as a swing unit.

## 5 year IPSC plan
5 year IPSC ( plan for Swamp West Hub
|  | 2017 | 2018 | 2019 | 2020 | 2021
ESCRAVOS_BEACH1_FS | ESCB/1 | 16177.88 | 23057.92 | 24696.87 | 23882.65 | 23385.72
FORCADOS1_FS | FORC/2 | 32244.37 | 54778.5 | 62297.96 | 63188.27 | 62108.87
FORCADOS3_FS | FORC/3 | 11553.87 | 15429.33 | 16804.07 | 15646.01 | 15555.53
FORCADOS4_FS | FORC/4 | 22105.42 | 27419.6 | 33973.6 | 34611.22 | 34241.8
OTUMARA1_FS | OTUM/1 | 62348.63 | 74705.29 | 74066.40 | 74230.41 | 78152.74
BENISEDE1_FS | BENS/1 | 32902.52 | 35778.78 | 35625.16 | 35258.73 | 36469.34
OGBOTOBO1_FS | OGBO/1 | 0 | 0 | 107.523 | 14214.97 | 30992.13
OPUKUSHI1_FS | OPUK/1 | 28160.67 | 37936.71 | 37332.63 | 36582.14 | 45758.32
TUNU1_FS | TUNU/1 | 16401.30 | 22348.98 | 22604.99 | 21766.96 | 30744.5

## Execution plan
HIGH LEVEL TIME LINE
|  |  | July, 2017 |  |  | August, 2017 |  |  |  | September, 2017 |  |  |  | October, 2017 |  |  |  | Nov, 2017
S/N | Description of Activities | Duration | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2
Days
1 | Develop a detailed project work scope and categorise quick fix. | 3
2 | Develop and determine no. of pumps required per facility (N) using 5 yrly IPSC plan | 3
3 | Field visit for inspection and assessment | 20
4 | E-MoC and Z6 approval | 15
5 | Field Execution / hook up | 20
6 | Equipment Commissioning | 5
7 | 72 hr reliability test | 3
8 | Demobilization | 2