## Sheet1
| Date | Activity | STATUS
1 | 2017-03-10 | Determine cause of AGG plants not running stably on two gas gensets only. | completed
2 | 2017-03-17 | Determine if the problem is load rejection, overload or genset trip. | completed
3 | 2017-03-24 | Determine if problem is electrical or mechanical | completed
4 | 2017-03-29 | Check for mechanical failures | completed
5 | 2017-03-31 | Check for electrical overload or imbalance | completed
6 | 2017-04-09 | conduct phase balancing tests | completed
7 | 2017-04-11 | Investigate generator reliability challenges | completed
8 | 2017-04-12 | Review load list and distribution (main and essential bus bars) | completed
9 | 2017-04-13 | Check unit capacity control system | completed
10 | 2017-04-15 | Review auto load management program | completed
11 | 2017-04-19 | Check unit cooling system | completed
12 | 2017-06-20 | Commission unit on load and run for 72hrs | in progress 45%
13 | 2017-07-20 | Secure overhaul spares | in progress 65%
14 | 2017-07-23 | Overhaul Generators due | in progress 55%
15 | 2017-07-30 | Resolve Mechanical problems discovered | in progress 45%
16 | 2017-07-30 | Resolve Electrical problems discovered | in progress 45%
17 | 2017-07-30 | Recore all leaking radiators in Agbada, Obigbo and ImoR. | in progress 85%
18 | 2017-07-30 | Commence TOH for 2 diesel gen sets. | Not started
19 | 2017-09-30 | PM quality/frequency | in progress 45%
20 | 2007-11-30 | PROCURE NEW GENERATOR | in progress 15%