## Slide 1: PROJECT CHARTER :Disposal and Recycling of old furniture in PHC
Problem Statement
Several obsolete float items used for temporary furnishing of RA houses for the purpose of accommodating cross-postee and returnee staffs are presently warehoused in different locations in the RA. Also disused office furniture from upgraded PHC IA blocks B1 and B2 have been stockpiled in some makeshift stores in PHC IA. While the bulk of these furniture and other household items including workstations, cabinets, beds, washing machines etc are irreparable and can only be disposed at their salvage values, a lot can be retrofitted and deployed to meet various business needs across Real Estate base and field assets. These items have been kept in the stores for a range of 4-20 years and the opportunity exists to eliminate cost of storage of these items and make CAPEX savings through recycling of some of these furniture.
Objective
This initiative seeks to; Inventorise all disused float items and obsolete office furniture in PHC IA/RA and ascertain their physical conditions. Disposal of all obsolete furniture items to eliminate cost of storing these items in the various warehouses. Retrofit and recycle abandoned household and office furniture items
Cost Saving Targets
High level assumptions – US$305K savings, largely from cost avoidance for storage of old items and procurement of new items
Scope
Float furniture in PHC RA Disused office furniture in PHC RA and IA
Key Stakeholders
Project Steering : David Nosike, Okereke IK, Eneni Sowande Implementation Lead: Frank Chiaha / John Uduaghan Project Team: Franklin Chiaha, John Uduaghan, Aboderin Yemi, Enonche Vanessa, IA/RA CLO External Stakeholders: Community vendors
Deliverables
Up-to-date Asset register of all obsolete float items and office furniture in PH IA & RA. Write-off of all obsolete float items and office furniture . Retrofitting and deployment of usable float and furniture items.
Key Risks : Mitigations
Community demand for items : Engage identified stakeholders Disposal on junk items : Engage waste management team Handling of materials: Follow item handling/movement procedures
Key Activities and Timelines