## Slide 1: Power System Integration Bonny FS
  Business Unit: Production
  Project Sponsor: David Martin
  Champion: Chuks Ikeobi
  Project Manager: Nketah/Brossa
  Facilitator/Coach:
PROJECT OWNERSHIP
Reduce generator maintenance, optimize energy consumption and minimize GHG emission by supplying Oloma flow station power from the AGG
OPPORTUNITY STATEMENT
SCOPE
BUSINESS CASE
  Team Members:
  Ojo Akindele
  Agbolu Promise
  Akpojevwa, Lucky
  Megbuwe, Anemieyeseigha
GOAL
POTENTIAL ROADBLOCKS/ ISSUES
Gross Hard Benefits:
BENEFITS
PROJECT STATUS
G
Y
R
On Track
Delayed
Stopped
Quick approval of the e-MoC.
50%
0%
13/04/17
06/04/17
06/04/17
23/03/17
10%
23/03/17
16/03/17
Health
% Compl
Completion Date
Start Date
Overall % Compl
100%
IDENTIFY
ENGAGE STK
STK APPROVAL
0%
13/06/17
13/04/17
IMPLEMENT
Cost efficiency improvements by saving circa F$150k/year
Fuel optimization by Reducing number of Gas Generators running simultaneously.
Increased availability of Cathodic Protection Transformer Rectifier (CPTR)
GHG emissions reduction
Soft Benefits:
Reduced noise level in the flow station
Bonny Flowstation is powered by a Gas Engine Generator (G3306, 70KVA). When the Bonny AGS project was delivered in 2015, it also came with two (2) Gas Engine Generators (G3512, 350KVA each) and a Diesel Generator (Olympian, 100KVA) for Blackstart. The Flow station and AGS Power generation systems are completely independent, hence, at any given time two generating sets have to be ON to power facilities that are adjacent (within the same perimeter fence). Given that the AGS Generators is sufficiently rated to power both facilities, it makes business sense to integrate both power distribution networks and decommission one set of the Generators. The Redundant Generator would become available for other SPDC locations to use.
Reduce the number of Gas Generators running simultaneously and optimise fuel gas and AGO usage.
Optimise energy consumption and minimize GHG emission
Reduce generator maintenance OPEX and maintenance man-hours