## LT Plan One-Pager
SPDC LONG TERM TURNAROUND PLAN: 2023 TO 2027
Ambition: Achieve scheduled deferment less than 5% yearly for SPDC
Hubs | Facility | 2023 | 2024 | 2025 | 2026 | 2027 | Comments
TAM Count à |  | 18 | 16 | 15 | 19 | 17
Pipelines | TRP | 21 | 21 | 21 | 21 | 21 | 1-yearly shutdown for defect repairs 5-yearly IP runs (2026)
| TNP | 168 | 84 | 14 | 14 | 14 | Post IP Repairs on the 28" TNP will be executed 14 days monthly(Jan - Dec)with little or no impact(PSD) on production (24 and 28 pipeline sytems available) in 2023; The same cycle will be repeated in 2024(Jan - June)
| TEP(20" OTUM - ESCB) | 14 | 21 |  | 21 |  | 2-yearly shutdown for IP defect & IC repairs 5-yearly IP runs (2023)
| TEP(24" ESCB - FORC RV MFD) | 14 | 21 |  | 21 |  | 2-yearly shutdown for IP defect & IC repairs 5-yearly IP runs (2023)
| TEP/TFP(20"/24" & 28" OTUM -ESCB - FORC RV MFD - FORC TERM.) | 14 | 21 |  | 21 |  | 2-yearly shutdown for IP defect & IC repairs 5-yearly IP runs (2023)
| K2S | 14 | 18 |  | 18 |  | 2-yearly shutdown for defect repairs 5-yearly IP runs (2023)
| EGGS |  |  | 18 | 21 |  | 1-yearly shutdown for defect repairs 5-yearly IP runs (2025) - This is a partial shutdown activity(PSD) - drop in the volume to regulate the speed of the IP tool.
East Asset | DIEBU CREEK FS | 3 | 3 | 3 | 7 | 3 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| ETELEBOU FS | 7 | 3 | 3 | 3 | 7 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| UBIE FS | 7 | 3 | 3 | 3 | 7 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| GBARAN GP | 7 | 21 | 7 | 21 | 7 | 1-yearly pitstop for ESD, Electrical inspections 2-yearly TAM for major repairs, upgrades
| ADIBAWA (FS, AGG) | 3 | 3 | 7 | 3 | 3 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| NUNRIVER FS | 3 | 7 | 3 | 3 | 3 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| BELEMA (AG and FS) | [5 empty] | Down on security
| SOKU FS | 3 | 3 | 3 | 14 | 3 | 1-yearly pitstop/sd for desanding 2-yearly TAM
| OLOMA FS | 3 | 3 | 3 | 7 | 3 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| BNAG | 14 | 3 | 3 | 3 | 3 | 1-yearly pitstop for ESD
| SOKU GP | 14 | 35 | 14 | 35 | 14 | 1-yearly TAM for 2 x 4k inspection for LPC vane replacements 2 -yearly for turbine/compressor major overhaul
| OBELE FS | 3 | 3 | 3 | 7 | 3 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| OKOGP | 25 | 25 | 25 | 25 | 25 | 1-yearly TAM for FGC annual inspection
| IMO RIVER AGG | [5 empty] | TBD
| IMO RIVER 1 FS | [5 empty] | TBD
| ISIMIRI FS | [5 empty] | TBD
| OGUTA FS | 3 | 7 | 3 | 3 | 3 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| AHIA FS | 3 | 3 | 3 | 7 | 3 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
| UMUECHEM FS | 7 | 3 | 3 | 3 | 3 | 1-yearly pitstop/sd for desanding 4-yearly TAM for major repairs
Swamp West | BENISEDE F/S | 7 | 21 | 7 | 21 | 7 | 1-yearly pitstop for desanding 2-yearly TAM for major repairs
| BENISEDE BOOSTER | [5 empty] | Booster 1yearly Mtc to be done with no prod impact: N+1 installed
| OGBOTOBO FS | 7 | 21 | 7 | 21 | 7 | 1-yearly pitstop for desanding 2-yearly TAM for major repairs
| OGBOTOBO BOOSTER | [5 empty] | Booster 1yearly Mtc to be done with no prod impact: N+1 installed
| TUNU FS | 7 | 21 | 7 | 21 | 7 | 1-yearly pitstop for desanding 2-yearly TAM for major repairs
| TUNU CPF | 11 | 25 | 11 | 25 | 11 | 1-yearly TAM for Turbine inspections and other works (2x yearly)
| OPUKUSHI FS | 7 | 21 | 7 | 21 | 7 | 1-yearly pitstop for desanding 2-yearly TAM for major repairs
| OPUKUSHI BOOSTER | [5 empty] | Booster 1yearly Mtc to be done with no prod impact: N+2 installed
| ESCRAVOS FS | 14 | 7 | 7 | 21 | 7 | 1-yearly pitstop for desanding 2-yearly TAM for major repairs
| ESCRAVOS BOOSTER | [5 empty] | Booster 1yearly Mtc to be done with no prod impact: N+1 installed
| NORTHBANK FS | 7 | 14 | 7 | 14 | 7 | 1-yearly pitstop for desanding 2-yearly TAM for major repairs
| NORTHBANK BOOSTER | [5 empty] | Booster 1yearly Mtc to be done with no prod impact: N+1 installed
| YOKRI FS | 3 | 14 | 3 | 14 | 7 | 1-yearly pitstop for desanding 2-yearly TAM for major repairs
| YOKRI BOOSTER | [5 empty] | Booster 1yearly Mtc to be done with no prod impact: N+1 installed
| OTUMARA FS | 8 | 14 | 8 | 14 | 8 | 1-yearly pitstop for desanding 2-yearly TAM for major repairs
| OTUMARA CPF | 40 | 14 | 8 | 14 | 40 | 1-yearly TAM for Turbine inspections and other works (2x yearly)
| SOUTHBANK/ESTUARY FS | 15 | 15 | 15 | 15 | 15 | 1-yearly TAM for compressor inspections, desanding and other works
| EA | 21 | 3 | 21 | 3 | 21 | 1-yearly pitstop for ESD 2-yearly TAM
|  | 2023 | 2024 | 2025 | 2026 | 2027
Legend
PitStop >3days
Operational SD <3days
Turnaround