## Schedule
POWER OPUKUSHI MILITARY CAMP FROM THE AG BOOSTER STATION
WEEKS
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Planning
eMOC (initation to approval)
Electrical inspection and protable applicance testing (PAT) at military camp
Contracting and Procurement
Cost estimation
Contract award
Close out of recommendations from electrical inspection and PAT
FTO Issuance
Procurement of earth electrodes
Procurement of feeder qnd isolator panels
Procurement of cables and accessories
Execution
Review of contractor HSSE plan
Review of contractor work method statement
Preparation of work packs and permits
Contractor mobilization to site
Excavation for miltary camp hookup
Cable laying and termination for military camp hookup
Installation of military camp earth grid
Hook up and commissioning