## Slide 1: Swamp West Light Fleet Utilization Improvement Project
Aminu Olasunmbo – Project Lead
Akeem Adepoju – Lean Coach

## Slide 2
Improvement of Light Fleet Utilization in Swamp West
  Business Unit: Swamp West Hub/Logistics
  Project Sponsor: Maichibi Meshach
  Project Champion: Ojabo Victor/Alamu Abimbola
  Project Team: Aminu Olasunmbo, Erekosima Erex, Jude-Egbuwe Titilola, Ogholoh Maxwell, Atu Chibuike, Itene Richard and Uzor Gabriel
  Lean Coach: Adepoju Akeem
PROJECT OWNERSHIP
OPPORTUNITY STATEMENT
IN:
- Dedicated light vehicles(SPDC owned only) supporting Swamp West hub
SCOPE
BUSINESS CASE
GOAL
POTENTIAL ROADBLOCKS/ ISSUES
OUT:
- Vehicles being used by Project teams, NNPC, DPR, Security, etc
Gross Hard Benefits*:
- N17m annual cost reduction
Soft Benefits:
- improved vehicles’ utilization
BENEFITS
There are 42 numbers of dedicated light vehicles supporting Swamp West hub Operations. 62% of these vehicles usually run below monthly average Kilometre of the total fleet size. Total cost of Operate & Maintain stands at N125.6M per annum.
In view of 38% average utilization, opportunity exists to optimize use of these light vehicles by creating pool services and reducing redundancies. This is expected to reduce cost of Operate & Maintain by 10%.
Optimization of dedicated light vehicles in Swamp West hub will deliver:
- at least 10% reduction in current number of dedicated light vehicles
- Annual cost reduction of N17m on O&M.
Achieve at least 10% reduction in number of dedicated light vehicles in Swamp West hub by Q3 2017 without any negative impact to Production or Project activities.
Resistance from FOT team
Possible Contracting constraint on Equipment off-hiring
50%
0%
27/03/17
01/06/17
PROJECT STATUS
0%
0%
Health
% Compl
Completion Date
Start Date
Overall % Compl
4%
NS
IDENTIFY
IMPROVE
SUSTAIN
NS
CLOSE
17/02/17
24/03/17
28/04/17
01/05/17
31/05/17
16/06/17

## Slide 3
Chart: FOT Light Fleet Utilization - Dec 2015
| RGM-579RD | NCH-409ST | KRK-275BX | NCH-410ST | NCH-426ST | KRK-277BX | AL930-BNY | DEG-526EQ | DEG-511EQ | KRK-694BX | DEG-523EQ | RGM-584RD | DEG-520EQ | NCH-429ST | DEG-518EQ | DEG-514EQ | NCH-332ST | DEG-516EQ | NCH-336ST | DEG-506EQ | AH402-RGM | RGM-582RD | DEG-508EQ | RGM-583RD | NCH-412ST | DEG-515EQ | NCH-331ST | DEG-537EQ | DEG-510EQ | NCH-342ST | RGM-561RD | AH408-ABM | NCH-413ST | NCH-427ST
Vehicle Utilization (% KM Driven per Monthly Average)- Dec 2015 | 2.6664 | 2.1612 | 2.1059 | 2.0141 | 1.8585 | 1.6364 | 1.463 | 1.4583 | 1.2999 | 1.1959 | 1.1771 | 1.1256 | 1.0253 | 0.99813 | 0.88285 | 0.86785 | 0.82287 | 0.81443 | 0.81256 | 0.80975 | 0.75726 | 0.75539 | 0.71978 | 0.69447 | 0.67104 | 0.63918 | 0.52577 | 0.48547 | 0.42737 | 0.36457 | 0.3224 | 0.31678 | 0.073102 | 0.051546

## Slide 4
Chart: FOT Light Fleet Utilization - Jan 2017
| DEG-537EQ | KRK-275BX | DEG-520EQ | DEG-511EQ | DEG-526EQ | DEG-502EQ | KRK-694BX | DEG-523EQ | KRK-277BX | RGM-584RD | NCH-332ST | NCH-336ST | NCH-342ST | AL930-BNY | RGM-582RD | NCH-331ST | NCH-426ST | RGM-583RD | AH402-RGM | DEG-516EQ | NCH-427ST | DEG-510EQ | DEG-515EQ | RGM-561RD | NCH-412ST | NCH-409ST | RGM-579RD
Vehicle Utilization (% KM Driven per Monthly Average) -Jan 2017 | 3.1236 | 3.0674 | 1.7804 | 1.5812 | 1.2503 | 1.2319 | 1.1736 | 1.1655 | 1.1256 | 1.097 | 1.0868 | 1.0531 | 0.86721 | 0.84883 | 0.7906 | 0.77528 | 0.72829 | 0.72217 | 0.69969 | 0.59448 | 0.57406 | 0.524 | 0.44229 | 0.30235 | 0.24719 | 0.1573 | 0

## Slide 5
Chart: FOT Light Fleet Utilization - Feb 2017
| KRK-275BX | RGM-579RD | DEG-537EQ | DEG-511EQ | NCH-426ST | DEG-520EQ | RGM-584RD | DEG-515EQ | DEG-502EQ | KRK-694BX | DEG-526EQ | DEG-523EQ | AH402-RGM | KRK-277BX | NCH-409ST | NCH-331ST | NCH-332ST | DEG-516EQ | NCH-342ST | NCH-336ST | RGM-582RD | RGM-583RD | DEG-510EQ | AL930-BNY | RGM-561RD | NCH-412ST | AH408-ABM | DEG-514EQ | NCH-413ST | DEG-506EQ | DEG-518EQ | NCH-429ST | NCH-427ST | NCH-410ST | NCH-343ST
Vehicle Utilization (% KM Driven per Monthly Average) - Feb 2017 | 3.1672 | 2.4164 | 2.3055 | 2.0563 | 1.9212 | 1.7926 | 1.4582 | 1.41 | 1.3505 | 1.3408 | 1.3344 | 1.3296 | 1.3167 | 1.2476 | 0.99357 | 0.98553 | 0.98553 | 0.87621 | 0.84727 | 0.82154 | 0.81029 | 0.77653 | 0.71865 | 0.67524 | 0.57074 | 0.45498 | 0.24759 | 0.21061 | 0.13987 | 0.13183 | 0.10932 | 0.10611 | 0.086817 | 0.0016077 | 0

## Slide 6
Chart: FOT Fleet Utilization History
| 31/12/2015 | 31/01/2017 | 28/02/2017
Fleet Size | 34 | 27 | 38
% Fleet Under-Utilization | 62 | 56 | 58

## Slide 7
FOT Under – Utilized Fleet

## Slide 8
Proposed Fleet Vs Current Fleet
Comparison shows only 14 out 38 vehicles meet Fleet average utilization
About 7 of the under-utilized vehicles covered less than 150 Km per month
Total Annual Spend on Light Vehicles to be reduced by N17m by releasing 10 of the under-utilized vehicles
Chart: 
| Fleet Size | Estimated O&M Cost(Nm)
Current Fleet | 38 | 125.6309
Proposed Fleet | 28 | 108.4726

## Slide 9
Proposals
Keep vehicles to only critical teams
Establish a demand-led Light Fleet System by creating pool vehicles: 4nos hilux vehicles to be retained for Central pool
Eliminate non-critical Self-driven vehicles: 10nos
  Create Shuttles - Replace Hilux with One Hiace/Mini Bus (There are two existing Coaster buses at FOT)