## Sheet1
| 2020 | [5 empty] | 2020
| Bonny Terminal Offshore - August 2020 | [5 empty] | Forcados Terminal offshore - October 2020
S/N | SPM Subsea Inspection activities | IMR/SPM | Nr of SPM | duration | Location | S/N | SPM Subsea Inspection activities | IMR/SPM | Nr of SPM | Duration | Location
1 | 6M Subsea Hose Inspection | 2 | 3 | 6 | SPM 1,2&3 | 1 | 6M Subsea Hose Inspection | 2 | 1 | 2 | SPM 2
2 | 6M Anchor chain inspection | 3 | 3 | 9 | SPM 1,2&3 | 2 | 6M Anchor chain inspection | 3 | 1 | 3 | SPM 2
3 | 6M PLEM inspection | 3 | 3 | 9 | SPM 1,2&3 | 3 | 6M PLEM inspection | 3 | 1 | 3 | SPM 2
4 | 6M PLEM Cameron Valve Inspection | 1 | 3 | 3 | SPM 1,2&3 | 4 | 6M PLEM Cameron Valve Inspection | 1 | 1 | 1 | SPM 2
5 | 6M PLEM remote umbilical inspection | 0.5 | 3 | 1.5 | SPM 1,2&3 | 5 | 6M PLEM remote umbilical inspection | 0.5 | 1 | 0.5 | SPM 2
6 | 6M SPAR buoy inspection | 0.5 | 3 | 1.5 | SPM 1,2&3 | 6 | 6M SPAR buoy inspection | 0.5 | 1 | 0.5 | SPM 2
7 | 6M underbuoy reducer inspection | 1 | 3 | 3 | SPM 1,2&3 | 7 | 6M underbuoy reducer inspection | 1 | 1 | 1 | SPM 2
8 | 1Y UnderBuoy body UT and cathodic protection inspection | 2 | 3 | 6 | SPM 1,2&3 | 8 | 1Y UnderBuoy body UT and cathodic protection inspection | 2 | 1 | 2 | SPM 2
9 | SPM3 Floating hose string (and MBC) change out | 5 | 1 | 5 | SPM 1,2&3 | 9 | SPM2 Mooring hawser changeout | 2 | 1 | 2 | SPM 2
|  |  |  | 44 | [5 empty] | 15
| Additional Scope | [5 empty] | Additional Scope
1 | Re-tension SPM 1 & 3 Anchor Chains | 3 | 2 | 6 | SPM 1,2&3 | 1 | Re-tension SPM 2 Anchor Chains | 3 | 1 | 3 | SPM 2
2 | Installation/Retrofit of Anodes | 8 | 1 | 8 | SPM 1,2&3 | 2 | Transit Days |  |  | 3 | SPM 2
|  |  |  | 14 | [5 empty] | 6
3 | Mob/Demob transit Days |  |  | 2
| Total |  |  | 60 | [5 empty] | 21