## Sheet1
S/N | INVESTIGATION | Why1 | Why2 | Why3 | Why4 | Why5 | Why6 | Why7 | ACTIONS | Action S/N | STATUS | Target date | New date
1 | AGC1 GG Overspeed Module Trips | Why1: · Faulty amplifier; Why2: · Ageing | Change out amplifiers (all 6 of them) | 1 | ? | 2021-04-01
[9 empty] | The connection should be checked for wiring damage | 2 | ? | 2021-04-01
2 | Excessive Recycling on AGC1 1st Stage Anti Surge Valve | 1. ASV received an Open signal from CCC Evidence: CCC issue confirmed by site team | 1. The CCC saw impending surge condition on 1st stage. Evidence: CCC issue confirmed by site team | 1. The CCC master controller worked to keep the 1st stage suction pressure at 12 barg. | 1. The 1st stage discharge is struggling to dump gas into the inter-stage header. | 1. The 2nd stage throttle valve pressure setpoint and its anti-surge controller suction setpoints are currently higher than what is required for the compressor. | 1. The pressure regime of XHP (and HP) wells have declined with time and 2nd stage setpoints in question are still set with design limits. Evidence: 1.1 CCC report and site team confirms this – (End) Cause. |  | Process Engineering and multi-discipline team on site to review and carry out required changes on throttle valves and anti-surge controller set points as recommended by Vendor. (still open: Main culprit) | 3 | Open | 2021-06-01 | Sept '21
|  | Why3: 1. Supply from the wells is below optimal volume Evidence: Well Decline confirmed by site team - (End) Cause | Open up more AG wells (AGC1 now has enough gas as AGC 2 unit is down? – confirm this) | 4 | Closed | Closed
|  | Why3: 1. PT-106 (1st stage discharge pressure) gave faulty input to the CCC Evidence: CCC vendor report – (End) Cause | Replace faulty PT-106 (Completed: PT106 has been troubleshot and is currently functional well) | 5 | Closed | Closed
|  | Why1: 1. ASV feedback positioner developed a fault Evidence: UCV-105 identified as requiring positioner calibration (End) – Cause | Recalibrate UCV-105 positioner (Status to be confirmed: Still flat-lined from SSC trends) | 6 | Open | 2021-04-01 | Sept '21
3 | Frequent clogging of AGC seal gas filters | 1.1 Presence of unwanted components in the line exceeding expected limit Evidence: Observation from the filter housing, dry gas seals and seal gas line (heavy end liquids as it looked like). | 2.1 Presence of wet gas Evidence: 2.1 Observation from the filter housing. Heavy hydrocarbon liquids found in the Dry Gas Seal. Seal gas supply is from the compressor itself. | 3.1a Condensation occurring across filters due to pressure drop Evidence: 3.1 Most likely as rapid filter DP build up is localized to LP seal gas system which feeds from associated gas wells and many other vessels at lower pressures. (LP AG wells have higher associated content) | 4.1a Source of LP Primary seal gas contains heavier hydrocarbons Evidence: LP gas is process gas from oil stabilization process. | 5.1 Supply line is tapped from the scrubber LP discharge line which has been scrubbed just once (consider increasing scrubbing prior to entry into the AGC or tapping from the discharge of HP line) (End) - Cause |  |  | Disconnect the seal gas supply from the LP compressor body, and connect the DGS LP gas system to the supply from the HP gas compressor (better quality gas supply) / rectify process control issues on oil stabilization unit | 7 | Open |  | Sept '21
|  | Why3: 3.3a Heater not working to keep gas temperature high enough to prevent liquid drop out Evidence: 3.3 PI trend data show heater not working sufficiently; Why4: 4.1b Heaters found to have been wired wrongly, signal may not have been powering the heater Evidence: Heaters found to have been wired wrongly, signal may not have been powering the heater, | Correct issues with the circuiting across heaters and get heaters working optimally | 8 | Closed | Closed
|  | Why2: 2.2 Grinding surfaces of the stationary and rotational seals Evidence: 2.2 Presence of shavings on opening of the DGS also Non drive End dry gas seal differential pressure transmitter on both LP and HP were reading zeros on PAS indicating failed seals; Why3: 3.1b Presence of wet gas Evidence: 3.1b Observation of hydrocarbon liquid from Dry gas seal and barrier seal replacement activity. Also, traces found in filter housing during changeout – see attachment | Action 7 covers for this | 7 | Open