## Sheet1
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Activities |  |  | 6 - 12 Feb. | 13 - 19 Feb. | 20 - 26 Feb. | 27 Feb. - 5 Mar. | 6 - 12 Mar. | 13 - 19 Mar. | 20 - 26 Mar. | 27 Mar. - 2 April | 3 - 9 April | 10 - 16 April | 17 - 23 April | 24 - 30 April
Update Project Scope
Get Most Recent Costs for Key Items from Market
Engage ElectricalTechnical Authorities on Project Scope
Stakeholders Connect / Steering Committee Connect
Napims Engagement
Site Visit for Design by Contractor
Project Schedule from Contractor
Site Visit for Scoping by Daystar
Project Cost & Schedule from Daystar
Site Visit to Solar Installation for Cathodic Protection at Assa.
Costing of Accompanying Solutions Lighting, fittings, sumo etc
Final Cost Determination
Vendor Selection
MOC Process & Approval
Contracting Process / Contract Award
Mobilization
Site Preparation
Stand Alone Street Lighting Installation at Ahia
Inverter Installation at Ahia
Cathodic Protection PV Array, Battery and Controller Installation
IT Facility PV Array, Controller Installation
DC Clean Earth Pit for Cathodic Protection
Comissioning / Testing
Commence Site Preparation for Oguta Flowstation