## Company Estimate (hidden)
Company Estimate
ITEM NO. | DESCRIPTION | UoM | QTY | UNIT COST US$ | TOOLS & EQUIPMENT$ | Man-power $ | Contractors Mark-UP $ | Total cost USD
1 | Procurement and Installation of all Mechanical Materials to Complete the Tie-in of PIG Receiver AGB2-A-2301 & 2302
1.1 | MECHANICAL SCOPE OF WORKS (PROCURE & INSTALL)
1.1.1 | PIPES
1.1.1.1 | 2"- SCH.40 ASTM A106-B (Instrument Air Line) (11412) | M | 30 | 6.0673 | 0.3183 | 0.47746 | 0.91009 | 233.193
1.1.1.2 | 3"- SCH.40 ASTM A106-B (61412) | M | 370 | 12.7507 | 0.66894 | 1.0034 | 1.9126 | 6044.1935
1.1.1.3 | 4"- SCH.40 ASTM A333-6 (11492) | M | 61 | 18.1781 | 0.95367 | 1.4305 | 2.7267 | 1420.6253
1.1.1.4 | 8"- 26mm Thickness ASTM A333-6 (151432) | M | 29 | 139.3809 | 7.3123 | 10.9685 | 20.9071 | 5178.4947
1.1.2 | TEE |  |  |  | 0 | 0
1.1.2.1 | 10" X 3" Branch Outlet 61412 | PC | 1 | 131.9672 | 6.9234 | 10.3851 | 19.7951 | 169.0707
1.1.2.2 | 3" x 3" Equal Tee 61412 ASTM A234-WPB | PC | 1 | 6.586 | 0.34552 | 0.51828 | 0.9879 | 8.4377
1.1.2.3 | 3" x 3/4" Branch Outlet 61412 | PC | 2 | 37.7049 | 1.9781 | 2.9672 | 5.6557 | 96.6118
1.1.3 | ELBOW |  |  |  | 0 | 0
1.1.3.1 | 2" - 150#, Elbow 90 deg LR bw (ASTM A234-WPB) | PC | 7 | 5.6557 | 0.29672 | 0.44507 | 0.84836 | 50.7212
1.1.3.2 | 4" - 150#, Elbow 90 deg LR bw (ASTM A420-WPL6) | PC | 14 | 22.623 | 1.1869 | 1.7803 | 3.3934 | 405.7697
1.1.3.3 | 8" - 1500#, Elbow 90 deg LR bw (ASTM A420-WPL6) | PC | 14 | 149.5 | 7.8432 | 11.7648 | 22.425 | 2681.4616
1.1.4 | FLANGES |  |  |  | 0 | 0
1.1.4.1 | 2" - 150#, SCH 40, WN, RF FLANGE, ASTM A105 | PC | 2 | 9.0117 | 0.47278 | 0.70917 | 1.3518 | 23.0908
1.1.4.2 | 3"-600#, SCH 40, WN, RF FLANGE, ASTM A105 | PC | 14 | 16.6953 | 0.87588 | 1.3138 | 2.5043 | 299.4506
1.1.4.3 | 4" - 150#, SCH 40, WN, RF FLANGE, ASTM A350-LF2 cl 1 | PC | 4 | 17.9692 | 0.94271 | 1.4141 | 2.6954 | 92.0852
1.1.4.4 | 8" - 1500#, 1.024" TH, WN, RF FLANGE, ASTM A105 | PC | 4 | 237.5018 | 12.46 | 18.69 | 35.6253 | 1217.1085
1.1.4.5 | 3/4" - 600#, SCH 80, WN, RF FLANGE, ASTM A105 | PC | 2 | 4.1061 | 0.21542 | 0.32312 | 0.61591 | 10.5211
1.1.4.6 | 3/4" - 600#, SCH 80, Blind Flange, ASTM A105 | PC | 2 | 18.4028 | 0.96546 | 1.4482 | 2.7604 | 47.1538
1.1.4.7 | 3" 600# SPEC BLIND ASTM A516-60/65/70 | PC | 2 | 30.3822 | 1.5939 | 2.3909 | 4.5573 | 77.8488
1.1.5 | GASKETS |  |  |  | 0 | 0
1.1.5.1 | 2"-150# | PC | 2 | 4.918 | 0.25801 | 0.38702 | 0.7377 | 12.6015
1.1.5.2 | 3"-600# | PC | 14 | 11.4754 | 0.60203 | 0.90305 | 1.7213 | 205.8252
1.1.5.3 | 4"-150# | PC | 4 | 9.8361 | 0.51603 | 0.77404 | 1.4754 | 50.4062
1.1.5.4 | 8"-1500# | PC | 4 | 25.5738 | 1.3417 | 2.0125 | 3.8361 | 131.0561
1.1.5.5 | 3/4"-600# | PC | 4 | 0.62842 | 0.032968 | 0.049453 | 0.094262 | 3.2204
1.1.1.6 | BOLTS & NUTS |  |  |  | 0 | 0
1.1.1.6.1 | 5/8" x 90mm (for 2" Class 150# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 24 | 3.1499 | 0.16525 | 0.24788 | 0.47248 | 96.8517
1.1.1.6.2 | 5/8" x 130mm (for 3" Class 600# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 96 | 4.5498 | 0.2387 | 0.35804 | 0.68247 | 559.5876
1.1.1.6.3 | 5/8" x 100mm (for 4" Class 150# Flanges, RF) (ASTM A320-L7/A194-4) | PC | 32 | 3.1499 | 0.16525 | 0.24788 | 0.47248 | 129.1356
1.1.1.6.4 | 1-5/8" x 340mm (for 8" Class 1500# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 48 | 41.0567 | 2.1539 | 3.2309 | 6.1585 | 2524.8008
1.1.1.6.5 | 5/8" x 150mm (for 3" Class 600# Blind/Spacer, RF) (ASTM A193-B7/A194-2H) | PC | 16 | 4.7248 | 0.24788 | 0.37182 | 0.70872 | 96.8517
1.2 | ELECTRICAL, INSTRUMENTATIONS AND CONTROLS SCOPE OF WORKS (PROCURE & INSTALL) |  |  |  | 0 | 0 | 0 | 0
1.2.1 | Cables |  |  |  | 0 | 0 | 0 | 0
1.2.1.1 | Foundation Fieldbus cable, Type A (XLPE/MS/LSZH/SWA/LSZH) 1 X 0.8 mm² | M | 300 | 1.6472 | 0.088119 | 0.037765 | 0.24707 | 606.037
1.2.1.2 | Foundation Fieldbus cable, Type A (XLPE/MS/LSZH/SWA/LSZH) 1 X 0.8 mm² | M | 1,000 | 1.6472 | 0.088119 | 0.037765 | 0.24707 | 2020.1232
1.2.1.3 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 5 X 1.0 mm² | M | 1,000 | 1.8605 | 0.09953 | 0.042656 | 0.27907 | 2281.7219
1.2.1.4 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 5 X 2.5 mm² | M | 1,000 | 2.2871 | 0.12235 | 0.052437 | 0.34306 | 2804.9193
1.2.1.5 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 1 X 1.0 mm² | M | 300 | 1.6472 | 0.088119 | 0.037765 | 0.24707 | 606.037
1.2.1.6 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 2 X 1.0 mm² | M | 300 | 1.6946 | 0.090655 | 0.038852 | 0.25418 | 623.4769
1.2.1.7 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 20 X 1.0 mm² | M | 500 | 2.5952 | 0.13884 | 0.059501 | 0.38928 | 1591.392
1.2.1.8 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 5 X 1.0 mm² | M | 1,000 | 1.8605 | 0.09953 | 0.042656 | 0.27907 | 2281.7219
1.2.2 | Junction Box |  |  |  | 0 | 0 | 0 | 0
1.2.2.1 | PAS Junction Box-1 Field barrier installed | PC | 2 | 606.5574 | 32.4494 | 13.9069 | 90.9836 | 1487.7944
1.2.2.2 | SIS Junction Box | PC | 2 | 606.5574 | 32.4494 | 13.9069 | 90.9836 | 1487.7944
1.2.2.3 | F & G Junction Box | PC | 2 | 606.5574 | 32.4494 | 13.9069 | 90.9836 | 1487.7944
1.2.3 | Cable Marker |  |  |  | 0 | 0 | 0 | 0
1.2.3.1 | PVC Conductor and cable markers, 3 -3.7 mm, 12 x 4.6 mm, White Cable Mark ( 0,1,A,B,C,D,E,G,I,M,P,S,T,V,X,Z,” -“) | PCK | 20 | 11.7835 | 0.63039 | 0.27017 | 1.7675 | 289.0323
1.2.3.2 | Stainless Steel Cable Markers (W *L: 15 mm * 90mm) | PCK | 1 | 8.7508 | 0.46815 | 0.20064 | 1.3126 | 10.7323
1.2.4 | Cable Lugs |  |  |  | 0 | 0 | 0 | 0
1.2.4.1 | Wire end ferrules with plastic collar-Size _1.0mm², 2.5mm² | PCK | 2 | 1.185 | 0.063395 | 0.027169 | 0.17775 | 2.9067
1.2.5 | FIRE AND GAS |  |  |  | 0 | 0 | 0 | 0
1.2.5.1 | Point gas Detectors – Draeger_ PIR type 334 Part # 68 10 100 | PC | 4 | 3800 | 203.2909 | 87.1247 | 570 | 18641.6622
1.2.5.2 | Open Path Gas Detector – Draeger_Pulsar2 | PC | 2 | 15000 | 802.464 | 343.9132 | 2250 | 36792.7544
1.2.5.3 | Manual Call Point -MEDC_ BG2EDC4NR | PC | 2 | 800 | 42.7981 | 18.342 | 120 | 1962.2802
1.2.5.4 | Sounder -MEDC_ DBIPBS024ANTNR | PC | 2 | 1500 | 80.2464 | 34.3913 | 225 | 3679.2754
1.2.5.5 | Beacon -MEDC_ XB15B02406BND+TR | PC | 2 | 9500 | 508.2272 | 217.8117 | 1425 | 23302.0778
1.2.6 | CONTROL SYSTEM |  |  |  | 0 | 0 | 0 | 0
1.2.6.1 | PAS |  |  |  | 0 | 0 | 0 | 0
1.2.6.1.1 | Analog Input - DeltaV Analog Input cards - Part No. - VE4003S2B3 | Nos. | 6 | 2079.6926 | 111.2586 | 47.6822 | 311.9539 | 15303.5235
1.2.6.1.2 | Digital Input - DeltaV Digital Input cards - Part No. - VE4001S2T2B4 | Nos. | 4 | 2002.6669 | 107.1379 | 45.9162 | 300.4 | 9824.4842
1.2.6.2 | SIS |  |  |  | 0 | 0 | 0 | 0
1.2.6.2.1 | Analog Input - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 2 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 10783.6794
1.2.6.2.2 | Digital Output - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 2 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 10783.6794
1.2.6.2.3 | Digital Input - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 2 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 10783.6794
1.2.6.3 | FGS |  |  |  | 0 | 0 | 0 | 0
1.2.6.3.1 | Analog Input - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 6 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 32351.0382
1.2.6.3.2 | Digital Output - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 4 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 21567.3588
1.2.6.3.3 | Digital Input - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 2 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 10783.6794
1.3 | ENGINEERING & DESIGN SCOPE OF WORKS | MH | 566 |  |  |  |  | 0
1.3.1 | Instruments & Controls |  | 266 |  |  |  |  | 0
1.3.1.1 | Consolidated Instrument Cable Schedule (SDA-S17893-AGBG1-IN-4308-00002) |  | 10 | 33.259 |  |  | 4.9889 | 382.4787
1.3.1.2 | Instrument Termination Diagram (SDA-S17893-AGBG1-IN-2389-00006-XXX |  | 8 | 31.9803 |  |  | 4.797 | 294.219
1.3.1.3 | Instrument Location and Cable Routing Diagram (SDA-S17893-AGBG1-IN-8801-00001-001,002) |  | 12 | 31.9803 |  |  | 4.797 | 441.3285
1.3.1.4 | PAS Loop Wiring Drawing (SDA-S17893-AGBG1-IN-2347-00003-001) |  | 12 | 31.9803 |  |  | 4.797 | 441.3285
1.3.1.5 | SIS-FGS Loop Wiring (SDA-17893-AGBG1-IN-2347-00004-0001) |  | 8 | 31.9803 |  |  | 4.797 | 294.219
1.3.1.6 | PAS System Cabinet & Marshalling Layout Drawing (SDA-S17893-AGBG1-4004-00006-001) |  | 8 | 31.9803 |  |  | 4.797 | 294.219
1.3.1.7 | SIS System Cabinet & Marshalling Layout Drawing (SDA-S17893-AGBG1-4004-00007-001) |  | 24 | 31.9803 |  |  | 4.797 | 882.657
1.3.1.8 | Emergeny & Safety System Block Diagram (SDA-S17893-AGBG1-IN-0980-00001-XXX) |  | 16 | 31.9803 |  |  | 4.797 | 588.438
1.3.1.9 | Overall System Architecture Drawing (SDA-17893-AGBG1-IN-0901-00003-001) |  | 16 | 31.9803 |  |  | 4.797 | 588.438
1.3.1.10 | I/O Range, alarm and trip setting reports / consolidated, alarm, trip and setting list (SDA-S17893-AGBG1-IN-4302-00001 |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.11 | Cause and Effect Matrix (SDA-S17893-AGBG1-IN-6604-00001-001) |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.12 | Consolidated Instrument Index (SDA-S17893-AGBG1-IN-6612-00005) |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.13 | PAS I/O List |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.14 | SIS-FGS I/O List |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.15 | Field Auxiliary Under FAR Cable Route / Tray lay-out |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.16 | Fire & Gas Cable Schedule |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.17 | Fire & Gas & Effect |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.18 | Fire & Gas Instrument Index |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.19 | Fire & Gas I/O List |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.20 | Fire & Gas Zone Lay-out |  | 8 | 31.9803 |  |  | 4.797 | 294.219
1.3.1.21 | Fire & Gas Detector Lay-out |  | 8 | 31.9803 |  |  | 4.797 | 294.219
1.3.1.22 | Instrument Datasheet-Beacon |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.23 | Instrument Datasheet-Sounder |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.24 | Instrument Datasheet-Manual Call Point |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.25 | Instrument Datasheet-Open Path Gas Detector |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.26 | Instrument Datasheet-Pont Gas Detector |  | 8 | 33.259 |  |  | 4.9889 | 305.983
1.3.1.27 | Fire & Gas Junction Box Instrument Termination Diagram |  | 16 | 31.9803 |  |  | 4.797 | 588.438
1.3.2 | Pipe Design Works |  | 200 |  |  |  | 0 | 0
1.3.2.1 | Isometrics |  | 50 | 31.9803 |  |  | 4.797 | 1838.8689
1.3.2.2 | Piping GA |  | 20 | 31.9803 |  |  | 4.797 | 735.5475
1.3.2.3 | Pipe Support Drawings |  | 10 | 31.9803 |  |  | 4.797 | 367.7738
1.3.2.4 | 3D Model |  | 40 | 31.9803 |  |  | 4.797 | 1471.0951
1.3.2.5 | Plot Plan |  | 16 | 31.9803 |  |  | 4.797 | 588.438
1.3.2.6 | Stress Analysis |  | 40 | 31.9803 |  |  | 4.797 | 1471.0951
1.3.2.7 | Tie-in Schedule |  | 8 | 31.9803 |  |  | 4.797 | 294.219
1.3.2.8 | MTO's |  | 16 | 31.9803 |  |  | 4.797 | 588.438
1.3.3 | Civil Design Works |  | 100 | 31.9803 |  |  | 4.797 | 3677.7377
1.4 | Site Works - Civil and Fabrication Scope of Works | [6 empty] | 0
1.4.1 | Survey works | lot | 1 | 568.0656 |  |  |  | 568.0656
1.4.2 | Fabrication & Installation of Pipe Support | lot | 1 | 4718.8173 | 6445.8197 | 4234.7541 | 707.8226 | 16107.2136
1.4.3 | Foundation Works | lot | 1 | 3342.3141 |  |  |  | 3342.3141
1.5 | Testing Inspection, Pre-com and Commissioning & Pipe Stress Analysis | [6 empty] | 0
1.5.1 | Testing Inspection, Pre-com and Commissioning | lot | 1 | 5850.4262 |  |  | 877.5639 | 6727.9902
1.5.2 | Pipe Stress Analysis | lot | 1 |  |  |  | 0 | 0
2 | PIG RECEIVER AND WELL SIGNAL SCOPE (ADDITIONAL WORKS) | [6 empty] | 0
2.1 | INSTRUMENTATIONS AND CONTROLS SCOPE OF WORKS (PROCURE & INSTALL) | [6 empty] | 0
2.1.1 | CABLES | [6 empty] | 0
2.1.1.1 | Turck Foundation Fieldbus cable, Type A ( PEI-MS-PE-SWA-PVC) 1x0.8mm² (Green) | M | 700 | 1.6472 | 0.216 | 0.11631 | 0.24707 | 1558.5847
2.1.1.2 | Amoured collective screen ( PEI-MS-PE-SWA-PVC) 5x1.5mm² (Blue) | M | 700 | 1.8605 | 0.24397 | 0.13137 | 0.27907 | 1760.4158
2.1.1.3 | Amoured collective screen ( PEI-MS-PE-SWA-PVC) 5x1.5mm² (Green) | M | 700 | 1.8605 | 0.24397 | 0.13137 | 0.27907 | 1760.4158
2.1.1.4 | Amoured collective screen ( PEI-MS-PE-SWA-PVC) 20x1.5mm² (Black) | M | 700 | 2.5952 | 0.34032 | 0.18325 | 0.38928 | 2455.6119
2.1.1.5 | Amoured collective screen ( PEI-MS-PE-SWA-PVC) 5x1.5mm² (Black) | M | 700 | 1.8605 | 0.24397 | 0.13137 | 0.27907 | 1760.4158
2.1.2 | DCS |  |  |  | 0 | 0 | 0 | 0
2.1.2.1 | Redundant H1 Fieldbus I/O Interface Cards with Integrated Segment Power; Two wide Termination Block with Connections for 2 H1 Segments (Model No. SE4037P1) | SET | 1 | 1185.01 | 155.3973 | 83.6755 | 177.7515 | 1601.8342
2.1.2.2 | Fieldbus Segment Protector R2, 12 Outputs, DIN rail mounted (Model No. R2-SP-N4) | SET | 1 | 177.4908 | 23.2754 | 12.5329 | 26.6236 | 239.9227
2.1.2.3 | NETWORK COMPONENT |  |  |  | 0 | 0 | 0 | 0
2.1.2.3.1 | Control Network Cable 100 meters (VE6102) | ROLL | 2 | 164.7164 | 21.6002 | 11.6309 | 24.7075 | 445.3099
2.1.2.3.2 | 10BaseT Cable Connector Kit with Crimp Tool (VE6103C1) | SET | 2 | 15.1432 | 1.9858 | 1.0693 | 2.2715 | 40.9396
2.1.3 | SIS |  |  |  | 0 | 0 | 0 | 0
2.1.3.1 | Redundant Logic Solver (VS3202) | PC | 1 | 4396.3871 | 576.5239 | 310.4359 | 659.4581 | 5942.805
2.1.3.2 | SISNet Terminator Assembly (VS6051) | SET | 1 | 2097.4677 | 275.0532 | 148.1056 | 314.6202 | 2835.2466
2.1.3.3 | Redundant SISNet Repeater (VS6002) | PC | 1 | 6219.2254 | 815.5633 | 439.1495 | 932.8838 | 8406.822
2.1.3.4 | 2-Wide Power/Controller Carrier (VE3051C0) | PC | 1 | 1901.9411 | 249.4126 | 134.2991 | 285.2912 | 2570.9439
2.1.3.5 | 8-Wide I/O Interface Carrier with Carrier Shield Bar, Single Enhanced Carrier Extender Cable, and Redundant SISNet Coax Cables (VE4050E1C2) | PC | 1 | 1824.9154 | 239.3118 | 128.8602 | 273.7373 | 2466.8247
2.1.3.6 | System Power Supply, 24 Vdc Input (SE5009) | PC | 1 | 232.5822 | 30.4999 | 16.423 | 34.8873 | 314.3924
2.1.4 | FGS |  |  |  | 0 | 0 | 0 | 0
2.1.4.1 | Redundant Logic Solver (VS3202) | PC | 1 | 4396.3871 | 576.5239 | 310.4359 | 659.4581 | 5942.805
2.1.4.2 | SISNet Terminator Assembly (VS6051) | SET | 1 | 2097.4677 | 275.0532 | 148.1056 | 314.6202 | 2835.2466
2.1.4.3 | Redundant SISNet Repeater (VS6002) | PC | 1 | 6219.2254 | 815.5633 | 439.1495 | 932.8838 | 8406.822
2.1.4.4 | 2-Wide Power/Controller Carrier (VE3051C0) | PC | 1 | 1901.9411 | 249.4126 | 134.2991 | 285.2912 | 2570.9439
2.1.4.5 | 8-Wide I/O Interface Carrier with Carrier Shield Bar, Single Enhanced Carrier Extender Cable, and Redundant SISNet Coax Cables (VE4050E1C2) | PC | 1 | 1824.9154 | 239.3118 | 128.8602 | 273.7373 | 2466.8247
2.1.4.6 | System Power Supply, 24 Vdc Input (SE5009) | PC | 1 | 232.5822 | 30.4999 | 16.423 | 34.8873 | 314.3924
2.1.5 | OTHER COMPONENTS |  |  |  | 0 | 0 | 0 | 0
2.1.5.1 | Control Cable, Lapp kabel 1.5 mm2, White, TBD | ROLL | 200 | 1.6472 | 0.216 | 0.11631 | 0.24707 | 445.3099
2.1.5.2 | Non Ex Relay module, Output in fail-safe technology, Up to SIL3, Single Channel, KFD0-RSH-1 | PC | 8 | 472.819 | 62.0035 | 33.3865 | 70.9228 | 5113.0549
2.1.5.3 | DI 1-channel isolated barrier, 24v DC (Power Rail), Dry contact or NAMUR inputs, Relay contact output, LFD, Reversible mode of operation, upto SIL2, KFD2-SR2- Ex1.W.LB | PC | 30 | 87.6907 | 11.4994 | 6.192 | 13.1536 | 3556.072
2.1.5.4 | K-System Intrinsic Safety Seperately Powered Isolated Barriers – Analog Input 2 /3 Wire Transmitters, KFD2-STC4- Ex1-Y122583 | PC | 38 | 106.6509 | 13.9858 | 7.5308 | 15.9976 | 5478.2731
2.1.5.5 | AO 1-channel isolated barrier, 24v DC (Power Rail), Current output up to 700 Ω load, HART I/P and valve positioner, LFD, upto SIL2, KFD2 SCD2- Ex1.LK | PC | 5 | 655.0842 | 85.905 | 46.2565 | 98.2626 | 4427.5418
2.1.5.6 | Power Feed Module, KFD2-EB2 | PC | 3 | 187.2316 | 24.5528 | 13.2207 | 28.0847 | 759.2694
2.1.5.7 | Universal Power Rail (2m, )UPR-03 | PC | 3 | 396.9784 | 52.0581 | 28.0313 | 59.5468 | 1609.8434
2.1.5.8 | End Cap for Universal power rail, UPR-E | PC | 3 | 42.7363 | 5.6043 | 3.0177 | 6.4104 | 173.3061
2.1.5.9 | Isolated FF power conditioner; 28 -30VDC @ 500 mA, HD2-FBPS- 1.500 | PC | 22 | 1074.8041 | 140.9453 | 75.8936 | 161.2206 | 31963.0002
2.1.5.10 | Motherboard for Redundant Power Conditioners hub (Power supply of four FOUNDATION Fieldbus H1 segments), MB-FB-4R | PC | 1 | 1232.8015 | 161.6644 | 87.0501 | 184.9202 | 1666.4362
2.1.5.11 | Diagnostic Module, HD2-DM-B | PC | 1 | 217.5093 | 28.5233 | 15.3587 | 32.6264 | 294.0176
2.1.5.12 | Modular Surge Protector for Fieldbus System, DP-LBF-1.34 | PC | 2 | 13.1789 | 1.7282 | 0.93058 | 1.9768 | 35.6291
2.1.5.13 | Base Module- Surge Protector, DB-LB | PC | 2 | 60.0627 | 7.8764 | 4.2411 | 9.0094 | 162.3792
2.1.5.14 | Surge Protector, SD32X | PC | 100 | 154.9628 | 20.3212 | 10.9422 | 23.2444 | 20947.063
2.1.5.15 | Surge Protector Dual Channel, SLP32D | PC | 50 | 267.9946 | 35.1437 | 18.9235 | 40.1992 | 18113.0486
2.1.5.16 | ISP7000 Insulating SpacersI, SP7000 | PC | 25 | 43.8454 | 5.7497 | 3.096 | 6.5768 | 1481.6967
2.1.5.17 | Relay socket mounting, PYF08A-E | PC | 8 | 5.2718 | 0.69132 | 0.37225 | 0.79077 | 57.0089
2.1.5.18 | Clip, PYC-A1 | PC | 8 | 0.71632 | 0.093936 | 0.050581 | 0.10745 | 7.7463
2.1.5.19 | Endplate, PFP-M | PC | 6 | 1.3491 | 0.17691 | 0.095261 | 0.20236 | 10.9418
2.1.5.20 | Plug-in Relay, MY2N-D2- DC24S | PC | 8 | 20.265 | 2.6575 | 1.4309 | 3.0398 | 219.1453
2.1.5.21 | 24VDC 40 Amp Bulk Power Supply for DeltaV, TBD | PC | 1 | 232.5822 | 30.4999 | 16.423 | 34.8873 | 314.3924
2.1.5.22 | 12VDC 40 Amp Bulk Power Supply for DeltaV, TBD | PC | 1 | 232.5822 | 30.4999 | 16.423 | 34.8873 | 314.3924
2.1.5.23 | Redundancy Module (Oring Diode)40 Amp Bulk Power Supply for DeltaV & SIS, TBD | PC | - | 193.3344 | 0 | 0
2.1.5.24 | 24VDC 40 Amp Bulk Power Supply for DeltaVSIS/FGS, TBD | PC | 1 | 232.5822 | 30.4999 | 16.423 | 34.8873 | 314.3924
2.1.5.25 | 24-port singlemode LC/SC duplex fiber optic patch panel, TBD | PC | 1 | 135.9535 | 17.8284 | 9.5999 | 20.393 | 183.7748
2.1.5.26 | 27U cabinet to install the fiber optic patch panel, TBD | PC | 1 | 860.3173 | 112.8184 | 60.7484 | 129.0476 | 1162.9317
2.1.5.27 | Fibre Optic to Ethernet converter, TBD | PC | 1 | 594.4176 | 77.9495 | 41.9728 | 89.1626 | 803.5025
2.1.5.28 | Network switch, TBD | PC | 1 | 55.6955 | 7.3037 | 3.9327 | 8.3543 | 75.2862
2.2 | ENGINEERING & DESIGN SCOPE OF WORKS | MH | 445 | 159.9016 | 0 | 0 | 23.9852 | 81829.6639
2.3 | Testing Inspection & Pre-com and Commissioning | LOT | 1 | 8025.6393 | 0 | 0 | 1203.8459 | 9229.4852
TOTAL AMOUNT FOR THIS VARIATION | [7 empty] | 541205.6985

## METS Estimate
ITEM NO. | DESCRIPTION |  | UoM | QTY | UNIT COST | Profit, O/H | Total Unit Cost | TOTAL COST, IN NAIRA | TOTAL COST IN USD
|  |  |  | a | b | c | d = b + c | e = d x a | f = e / 305
1 | PROCUREMENT | [6 empty] | 578966448.93 | 1898250.65
1.1 | MECHANICAL | [6 empty] | 10518630.59 | 34487.31
1.1.1 | PIPES | [6 empty] | 6260162.22 | 20525.12
1.1.1.1 | 2"- SCH.40 ASTM A106-B (Instrument Air Line) (11412) |  | M | 30 | 3568.5 | 1070.55 | 4639.05 | 139171.5 | 456.3
1.1.1.2 | 3"- SCH.40 ASTM A106-B (61412) |  | M | 191 | 7417.8 | 2225.34 | 9643.14 | 1841839.74 | 6038.82
1.1.1.3 | 4"- SCH.40 ASTM A333-6 (11492) |  | M | 59 | 18345.6 | 5503.68 | 23849.28 | 1407107.52 | 4613.47
1.1.1.4 | 8"- 26mm Thickness ASTM A333-6 (151432) |  | M | 33 | 66947.4 | 20084.22 | 87031.62 | 2872043.46 | 9416.54
1.1.2 | TEE | [6 empty] | 82803.24 | 271.49
1.1.2.1 | 10" X 3" Branch Outlet 61412 |  | PC | 1 | 45793.8 | 13738.14 | 59531.94 | 59531.94 | 195.19
1.1.2.2 | 3" x 3" Equal Tee 61412 ASTM A234-WPB |  | PC | 1 | 4475.25 | 1342.58 | 5817.83 | 5817.83 | 19.07
1.1.2.3 | 3" x 3/4" Branch Outlet 61412 |  | PC | 3 | 4475.25 | 1342.58 | 5817.83 | 17453.48 | 57.22
1.1.3 | ELBOW | [6 empty] | 1122828.82 | 3681.41
1.1.3.1 | 2" - 150#, Elbow 90 deg LR bw (ASTM A234-WPB) |  | PC | 9 | 2237.63 | 671.29 | 2908.91 | 26180.21 | 85.84
1.1.3.2 | 3" - 600#, Elbow 90 deg LR bw (ASTM A234-WPLB) |  | PC | 11 | 8950.5 | 2685.15 | 11635.65 | 127992.15 | 419.65
1.1.3.2 | 4" - 150#, Elbow 90 deg LR bw (ASTM A420-WPL6) |  | PC | 12 | 15856.43 | 4756.93 | 20613.35 | 247360.23 | 811.02
1.1.3.3 | 8" - 1500#, Elbow 90 deg LR bw (ASTM A420-WPL6) |  | PC | 10 | 55484.33 | 16645.3 | 72129.62 | 721296.23 | 2364.91
1.1.4 | FLANGES | [6 empty] | 542750.78 | 1779.51
1.1.4.1 | 2" - 150#, SCH 40, WN, RF FLANGE, ASTM A105 |  | PC | 2 | 5896.8 | 1769.04 | 7665.84 | 15331.68 | 50.27
1.1.4.2 | 3"-600#, SCH 40, WN, RF FLANGE, ASTM A105 |  | PC | 10 | 16461.9 | 4938.57 | 21400.47 | 214004.7 | 701.65
1.1.4.3 | 4" - 150#, SCH 40, WN, RF FLANGE, ASTM A350-LF2 cl 1 |  | PC | 4 | 19919.25 | 5975.78 | 25895.03 | 103580.1 | 339.61
1.1.4.4 | 8" - 1500#, 1.024" TH, WN, RF FLANGE, ASTM A105 |  | PC | 4 | 35000 | 10500 | 45500 | 182000 | 596.72
1.1.4.5 | 3/4" - 600#, SCH 80, WN, RF FLANGE, ASTM A105 |  | PC | 1 | 4475.25 | 1342.58 | 5817.83 | 5817.83 | 19.07
1.1.4.6 | 3/4" - 600#, SCH 80, Blind Flange, ASTM A105 |  | PC | 1 | 5961.15 | 1788.35 | 7749.5 | 7749.5 | 25.41
1.1.4.7 | 3" 600# SPEC BLIND ASTM A516-60/65/70 |  | PC | 1 | 10974.6 | 3292.38 | 14266.98 | 14266.98 | 46.78
1.1.5 | GASKETS | [6 empty] | 290718.38 | 953.18
1.1.5.1 | 2"-150# |  | PC | 4 | 2827.91 | 848.37 | 3676.29 | 14705.15 | 48.21
1.1.5.2 | 3"-600# |  | PC | 22 | 4642.31 | 1392.69 | 6035.01 | 132770.14 | 435.31
1.1.5.3 | 4"-150# |  | PC | 8 | 6095.25 | 1828.58 | 7923.83 | 63390.6 | 207.84
1.1.5.4 | 8"-1500# |  | PC | 8 | 7087.5 | 2126.25 | 9213.75 | 73710 | 241.67
1.1.5.5 | 3/4"-600# |  | PC | 4 | 1181.25 | 354.38 | 1535.63 | 6142.5 | 20.14
1.1.1.6 | BOLTS & NUTS | [6 empty] | 970392.15 | 3181.61
1.1.1.6.1 | 5/8" x 90mm (for 2" Class 150# Flanges, RF) (ASTM A193-B7/A194-2H) |  | PC | 36 | 826.88 | 248.06 | 1074.94 | 38697.75 | 126.88
1.1.1.6.2 | 5/8" x 130mm (for 3" Class 600# Flanges, RF) (ASTM A193-B7/A194-2H) |  | PC | 108 | 1157.63 | 347.29 | 1504.91 | 162530.55 | 532.89
1.1.1.6.3 | 5/8" x 100mm (for 4" Class 150# Flanges, RF) (ASTM A320-L7/A194-4) |  | PC | 48 | 921.38 | 276.41 | 1197.79 | 57493.8 | 188.5
1.1.1.6.4 | 1-5/8" x 340mm (for 8" Class 1500# Flanges, RF) (ASTM A193-B7/A194-2H) |  | PC | 72 | 7371 | 2211.3 | 9582.3 | 689925.6 | 2262.05
1.1.1.6.5 | 5/8" x 150mm (for 3" Class 600# Blind/Spacer, RF) (ASTM A193-B7/A194-2H) |  | PC | 12 | 1393.88 | 418.16 | 1812.04 | 21744.45 | 71.29
1.1.1.7 | VALVE | [6 empty] | 1248975 | 4095
1.1.1.7.1 | 3/4" Ball Valve #61412 |  | PC | 1 | 45750 | 13725 | 59475 | 59475 | 195
1.1.1.7.2 | 3" Ball Valve #61412 |  | PC | 2 | 228750 | 68625 | 297375 | 594750 | 1950
1.1.1.7.3 | 3" Check Valve #61412 |  | PC | 2 | 228750 | 68625 | 297375 | 594750 | 1950
1.2 | ELEC., INST. AND CONTROLS | [6 empty] | 568447818.34 | 1863763.34
1.2.1 | Cable Marker | [6 empty] | 1033760 | 3389.38
1.2.1.1 | PVC Conductor and cable markers, 3 -3.7 mm, 12 x 4.6 mm, White Cable Mark ( 0,1,A,B,C,D,E,G,I,M,P,S,T,V,X,Z,” -“) |  | PCK | 20 | 35000 | 10500 | 45500 | 910000 | 2983.61
1.2.1.2 | Stainless Steel Cable Markers (W *L: 15 mm * 90mm) |  | PCK | 1 | 95200 | 28560 | 123760 | 123760 | 405.77
1.2.2 | Cable Lugs | [6 empty] | 39000 | 127.87
1.2.2.1 | Wire end ferrules with plastic collar-Size _1.0mm², 2.5mm² |  | PCK | 2 | 15000 | 4500 | 19500 | 39000 | 127.87
1.2.3 | CABLES | [6 empty] | 19947689.13 | 65402.26
1.2.3.1 | Turck Foundation Fieldbus cable, Type A ( PEI-MS-PE-SWA-PVC) 1x0.8mm² (Green) |  | M | 700 | 6917.4 | 2075.22 | 8992.62 | 6294834 | 20638.8
1.2.3.2 | Amoured collective screen (XLPE/MS/LSZH/SWA/SZH) 10 x 1.5mm² (Blue) |  | M | 700 | 3900 | 1170 | 5070 | 3549000 | 11636.07
1.2.3.3 | Amoured collective screen (XLPE/MS/LSZH/SWA/SZH) 14 x 1.5mm² (Black) |  | M | 700 | 4465 | 1339.5 | 5804.5 | 4063150 | 13321.8
1.2.3.4 | Amoured collective screen (XLPE/MS/LSZH/SWA/SZH) 10 x 1.5mm² (Black) |  | M | 700 | 3900 | 1170 | 5070 | 3549000 | 11636.07
1.2.3.5 | Amoured collective screen (XLPE/MS/LSZH/SWA/SZH) 5 x 1.5mm² (Black) |  | M | 700 | 2738.14 | 821.44 | 3559.58 | 2491705.13 | 8169.53
1.2.3.6 | 70mm2 green/yellow PVC insulated stranded copper cable c/w 70mm2 "c" shape connectors, 70mm2 compression type lug and earth bosses |  | M | 700 | 7500 | 2250 | 9750 | 6825000 | 22377.05
1.2.4 | DCS | [6 empty] | 11692654.16 | 38336.57
1.2.4.1 | Redundant H1 Fieldbus I/O Interface Cards with Integrated Segment Power; Two wide Termination Block with Connections for 2 H1 Segments (Model No. SE4037P1) |  | SET | 1 | 7493850 | 2248155 | 9742005 | 9742005 | 31941
1.2.4.2 | Fieldbus Segment Protector R2, 12 Outputs, DIN rail mounted (Model No. R2-SP-N4) |  | SET | 1 | 691740 | 207522 | 899262 | 899262 | 2948.4
1.2.4.3 | Control Network Cable 100 meters (VE6102) |  | ROLL | 2 | 864.68 | 259.4 | 1124.08 | 2248.16 | 7.37
1.2.4.4 | 10BaseT Cable Connector Kit with Crimp Tool (VE6103C1) |  | SET | 2 | 403515 | 121054.5 | 524569.5 | 1049139 | 3439.8
1.2.5 | SIS | [6 empty] | 15684628.05 | 51425.01
1.2.5.1 | Redundant Logic Solver (VS3202) |  | PC | 1 | 5533920 | 1660176 | 7194096 | 7194096 | 23587.2
1.2.5.2 | SISNet Terminator Assembly (VS6051) |  | SET | 1 | 190228.5 | 57068.55 | 247297.05 | 247297.05 | 810.81
1.2.5.3 | Redundant SISNet Repeater (VS6002) |  | PC | 1 | 3746925 | 1124077.5 | 4871002.5 | 4871002.5 | 15970.5
1.2.5.4 | 2-Wide Power/Controller Carrier (VE3051C0) |  | PC | 1 | 317047.5 | 95114.25 | 412161.75 | 412161.75 | 1351.35
1.2.5.5 | 8-Wide I/O Interface Carrier with Carrier Shield Bar, Single Enhanced Carrier Extender Cable, and Redundant SISNet Coax Cables (VE4050E1C2) |  | PC | 1 | 1268190 | 380457 | 1648647 | 1648647 | 5405.4
1.2.5.6 | System Power Supply, 24 Vdc Input (SE5009) |  | PC | 1 | 1008787.5 | 302636.25 | 1311423.75 | 1311423.75 | 4299.75
1.2.6 | FGS | [6 empty] | 15699615.75 | 51474.15
1.2.6.1 | Redundant Logic Solver (VS3202) |  | PC | 1 | 5533920 | 1660176 | 7194096 | 7194096 | 23587.2
1.2.6.2 | SISNet Terminator Assembly (VS6051) |  | SET | 1 | 201757.5 | 60527.25 | 262284.75 | 262284.75 | 859.95
1.2.6.3 | Redundant SISNet Repeater (VS6002) |  | PC | 1 | 3746925 | 1124077.5 | 4871002.5 | 4871002.5 | 15970.5
1.2.6.4 | 2-Wide Power/Controller Carrier (VE3051C0) |  | PC | 1 | 317047.5 | 95114.25 | 412161.75 | 412161.75 | 1351.35
1.2.6.5 | 8-Wide I/O Interface Carrier with Carrier Shield Bar, Single Enhanced Carrier Extender Cable, and Redundant SISNet Coax Cables (VE4050E1C2) |  | PC | 1 | 1268190 | 380457 | 1648647 | 1648647 | 5405.4
1.2.6.6 | System Power Supply, 24 Vdc Input (SE5009) |  | PC | 1 | 1008787.5 | 302636.25 | 1311423.75 | 1311423.75 | 4299.75
1.2.7 | OTHER COMPONENTS | [6 empty] | 497525471.26 | 1631231.05
1.2.7.1 | Control Cable, Lapp kabel 1.5 mm2, White, TBD |  | ROLL | 200 | 28822.5 | 8646.75 | 37469.25 | 7493850 | 24570
1.2.7.2 | Non Ex Relay module, Output in fail-safe technology, Up to SIL3, Single Channel, KFD0-RSH-1 |  | PC | 8 | 1671705 | 501511.5 | 2173216.5 | 17385732 | 57002.4
1.2.7.3 | DI 1-channel isolated barrier, 24v DC (Power Rail), Dry contact or NAMUR inputs, Relay contact output, LFD, Reversible mode of operation, upto SIL2, KFD2-SR2- Ex1.W.LB |  | PC | 38 | 1959930 | 587979 | 2547909 | 96820542 | 317444.4
1.2.7.4 | K-System Intrinsic Safety Seperately Powered Isolated Barriers – Analog Input 2 /3 Wire Transmitters, KFD2-STC4- Ex1-Y122583 |  | PC | 45 | 3228120 | 968436 | 4196556 | 188845020 | 619164
1.2.7.5 | AO 1-channel isolated barrier, 24v DC (Power Rail), Current output up to 700 Ω load, HART I/P and valve positioner, LFD, upto SIL2, KFD2-SCD2- Ex1.LK |  | PC | 5 | 864675 | 259402.5 | 1124077.5 | 5620387.5 | 18427.5
1.2.7.6 | Power Feed Module, KFD2-EB2 |  | PC | 3 | 224815.5 | 67444.65 | 292260.15 | 876780.45 | 2874.69
1.2.7.7 | Universal Power Rail (2m, )UPR-03 |  | PC | 3 | 247873.5 | 74362.05 | 322235.55 | 966706.65 | 3169.53
1.2.7.8 | End Cap for Universal power rail, UPR-E |  | PC | 3 | 28822.5 | 8646.75 | 37469.25 | 112407.75 | 368.55
1.2.7.9 | Isolated FF power conditioner; 28 -30VDC @ 500 mA, HD2-FBPS- 1.500 |  | PC | 22 | 3746925 | 1124077.5 | 4871002.5 | 107162055 | 351351
1.2.7.10 | Motherboard for Redundant Power Conditioners hub (Power supply of four FOUNDATION Fieldbus H1 segments), MB-FB-4R |  | PC | 1 | 259402.5 | 77820.75 | 337223.25 | 337223.25 | 1105.65
1.2.7.11 | Diagnostic Module, HD2-DM-B |  | PC | 1 | 51880.5 | 15564.15 | 67444.65 | 67444.65 | 221.13
1.2.7.12 | Modular Surge Protector for Fieldbus System, DP-LBF-1.34 |  | PC | 2 | 172935 | 51880.5 | 224815.5 | 449631 | 1474.2
1.2.7.13 | Base Module- Surge Protector, DB-LB |  | PC | 2 | 63409.5 | 19022.85 | 82432.35 | 164864.7 | 540.54
1.2.7.14 | Surge Protector, SD32X |  | PC | 100 | 86467.5 | 25940.25 | 112407.75 | 11240775 | 36855
1.2.7.15 | Surge Protector Dual Channel, SLP32D |  | PC | 50 | 209827.8 | 62948.34 | 272776.14 | 13638807 | 44717.4
1.2.7.16 | ISP7000 Insulating SpacersI, SP7000 |  | PC | 25 | 99149.4 | 29744.82 | 128894.22 | 3222355.5 | 10565.1
1.2.7.17 | Relay socket mounting, PYF08A-E |  | PC | 8 | 14411.25 | 4323.38 | 18734.63 | 149877 | 491.4
1.2.7.18 | Clip, PYC-A1 |  | PC | 8 | 720.56 | 216.17 | 936.73 | 7493.85 | 24.57
1.2.7.19 | Endplate, PFP-M |  | PC | 6 | 1919.58 | 575.87 | 2495.45 | 14972.71 | 49.09
1.2.7.20 | Plug-in Relay, MY2N-D2- DC24S |  | PC | 8 | 21616.88 | 6485.06 | 28101.94 | 224815.5 | 737.1
1.2.7.21 | 24VDC 40 Amp Bulk Power Supply for DeltaV, TBD |  | PC | 1 | 749385 | 224815.5 | 974200.5 | 974200.5 | 3194.1
1.2.7.22 | 12VDC 40 Amp Bulk Power Supply for DeltaV, TBD |  | PC | 1 | 317047.5 | 95114.25 | 412161.75 | 412161.75 | 1351.35
ITEM NO. | DESCRIPTION |  | UoM | QTY | UNIT COST | Profit, O/H | Total Unit Cost | TOTAL COST, IN NAIRA | TOTAL COST IN USD
|  |  |  | a | b | c | d = b + c | e = d x a | f = e / 305
1.2.7.23 | Redundancy Module (Oring Diode)40 Amp Bulk Power Supply for DeltaV & SIS |  | PC | 1 | 500000 | 150000 | 650000 | 650000 | 2131.15
1.2.7.24 | 24VDC 40 Amp Bulk Power Supply for DeltaVSIS/FGS |  | PC | 1 | 396500 | 118950 | 515450 | 515450 | 1690
1.2.7.25 | 24-port singlemode LC/SC duplex fiber optic patch panel |  | PC | 1 | 366000 | 109800 | 475800 | 475800 | 1560
1.2.7.26 | 27U cabinet to install the fiber optic patch panel, TBD |  | PC | 1 | 640500 | 192150 | 832650 | 832650 | 2730
1.2.7.27 | Fibre Optic to Ethernet converter |  | PC | 1 | 122000 | 36600 | 158600 | 158600 | 520
1.2.7.28 | Network switch |  | PC | 1 | 114375 | 34312.5 | 148687.5 | 148687.5 | 487.5
1.2.7.29 | SERVER | [6 empty] | 38556180 | 126413.7
1.2.7.29.1 | Power Edge T610 Tower Server; English Win Server 2008 Std Image Included; Xeon 5530 2.4 GHz CPU; 20-inch LCD Monitor; 146GB Drive; Raid 0; 4 GB RAM; DVD+/- RW Drive; RD1000 Back-up Unit; 4 Ethernet Ports (AGG Control Room) |  | SET | 1 | 648000 | 194400 | 842400 | 842400 | 2761.97
1.2.7.29.2 | Monitoring Module (Analog and Discrete) |  | EA | 100 | 198000 | 59400 | 257400 | 25740000 | 84393.44
1.2.7.29.3 | Simple Control Module |  | EA | 25 | 81000 | 24300 | 105300 | 2632500 | 8631.15
1.2.7.29.4 | Intermediate Control Modules |  | EA | 20 | 35280 | 10584 | 45864 | 917280 | 3007.48
1.2.7.29.5 | OPC SCADA Modules |  | EA | 100 | 64800 | 19440 | 84240 | 8424000 | 27619.67
2 | ENGINEERING & DESIGN SCOPE OF WORKS, 1 man-day consits of the following: 1 No. Engineering Manager x 10% 1 No. Discipline Lead x 20% 1 No. Discipline Engineer x 40% 1 No. Designer / AutoCAD Operator x 100% | MH | MANDAYS | 399 | - |  |  | 12582763 | 41254.96
2.1 | EI&C | 1665 |  | 208 | 31516 |  |  | 6559267.5 | 21505.8
2.1.1 | Consolidated Instrument Cable Schedule (SDA-S17893-AGBG1-IN-4308-00002) | 32 |  | 4 |  |  |  | - | -
2.1.2 | Fire & Gas Cable Schedule (SDA-S17893-AGBG1-IN-4308-00001) | 8 |  | 1 |  |  |  | - | -
2.1.3 | Controls Narrative (SDA-S17893-AGBG1-IN-5680-00001) | 16 |  | 2 |  |  |  | - | -
2.1.4 | Instrument Junction Box Termination (SDA-S17893-AGBG1-IN-2389-00004) | 25 |  | 3 |  |  |  | - | -
2.1.5 | Cable Routing Diagram (SDA-S17893-AGBG1-IN-8801-00001-001, 002) | 80 |  | 10 |  |  |  | - | -
2.1.6 | PAS Loop Wiring Diagram (SDA-S17893-AGBG1-2347-00003-001) | 100 |  | 13 |  |  |  | - | -
2.1.7 | SIS-FGS Loop Wiring System Drawing (SDA-S17893-AGBG1-IN-2347-00004-001) | 50 |  | 6 |  |  |  | - | -
2.1.8 | Emergeny & Safety System Block Diagram (SDA-S17893-AGBG1-IN-0980-00001-001) | 32 |  | 4 |  |  |  | - | -
2.1.9 | Overall System Architecture Drawing (SDA-17893-AGBG1-IN-0901-00003-001) | 32 |  | 4 |  |  |  | - | -
2010-01-02 | I/O Range, alarm and trip setting reports / consolidated, alarm, trip and setting list (SDA- S17893-AGBG1-IN-4302-00001 | 16 |  | 2 |  |  |  | - | -
2011-01-02 | Consolidated Cause and Effect Matrix (SDA-S17893-AGBG1-IN-6604-00001-001) | 20 |  | 3 |  |  |  | - | -
2012-01-02 | Fire & Gas Cause and Effect Matrix (SDA-S17893-AGBG1-IN-6604-00001-002) | 20 |  | 3 |  |  |  | - | -
2013-01-02 | Consolidated Instrument Index (SDA-S17893-AGBG1-IN-6612-00003) | 20 |  | 3 |  |  |  | - | -
2014-01-02 | Fire & Gas Instrument Index | 16 |  | 2 |  |  |  | - | -
2015-01-02 | PAS I/O List (SDA-S17893-AGBG1-IN-6612-00003) | 16 |  | 2 |  |  |  | - | -
2016-01-02 | SIS I/O List (SDA-S17893-AGBG1-IN-6612-00004) | 20 |  | 3 |  |  |  | - | -
2017-01-02 | Fire & Gas Cable Device Instrument Details (SDA-S17893-AGBG1-IN8801-0001-001 to 009 | 40 |  | 5 |  |  |  | - | -
2018-01-02 | SIS, FGS, & PAS Panel Wiring Drawing | 40 |  | 5 |  |  |  | - | -
2019-01-02 | SIS, FGS, & PAS Panel Layout Drawing | 40 |  | 5 |  |  |  | - | -
2020-01-02 | Overall Earthing Layout Drawing | 120 |  | 15 |  |  |  | - | -
2021-01-02 | Cable MCT Diagram | 60 |  | 8 |  |  |  | - | -
2022-01-02 | Interface Detail Drawing between the AG Compressor, Agbada AG and Agbada Flowstation | 50 |  | 6 |  |  |  | - | -
2023-01-02 | Cabinet Termination Drawing | 60 |  | 8 |  |  |  | - | -
2024-01-02 | Cause & Effect Matrix (AG Compressor & AGG) | 70 |  | 9 |  |  |  | - | -
2025-01-02 | Robershaw Hook up drawing update | 60 |  | 8 |  |  |  | - | -
2026-01-02 | Instrument I/O List | 30 |  | 4 |  |  |  | - | -
2027-01-02 | Building Overall Architectural Lay-out Drawings | 160 |  | 20 |  |  |  | - | -
2028-01-02 | Building Structural Calculation Report | 120 |  | 15 |  |  |  | - | -
2021-01-02 | Building Structural General Arrangement Drawing | 120 |  | 15 |  |  |  | - | -
2022-01-02 | Structural Detailed Drawings | 192 |  | 24 |  |  |  | - | -
2.2 | Pipe Design Works |  |  | 176 | 31516 |  |  | 5550755.5 | 18199.2
2.2.1 | Isometrics | 378 |  | 47 |  |  |  | - | -
2.2.2 | Piping GA | 322 |  | 40 |  |  |  | - | -
2.2.3 | Pipe Support Drawings | 322 |  | 40 |  |  |  | - | -
2.2.4 | 3D Model | 72 |  | 9 |  |  |  | - | -
2.2.5 | Plot Plan | 35 |  | 4 |  |  |  | - | -
2.2.6 | Stress Analysis | 80 |  | 10 |  |  |  | - | -
2.2.7 | Tie-in Schedule | 28 |  | 4 |  |  |  | - | -
2.2.8 | MTO's | 50 |  | 6 |  |  |  | - | -
2.2.9 | Review of critical Line List | 10 |  | 1 |  |  |  | - | -
2010-02-02 | Site Visit / Report | 112 |  | 14 |  |  |  | - | -
2.3 | Civil Design Works | 120 |  | 15 | 31516 |  |  | 472740 | 1549.97
3 | Site Works / Construction | [6 empty] | 192033933.67 | 629619.45
3.1 | Site Works - Civil and Fabrication Scope of Works | [6 empty] | 14910852.99 | 48888.04
3.1.1 | Survey works |  | lot | 1 | 750000 |  |  | 750000 | 2459.02
3.1.2 | Fabrication & Installation of Pipe Support (including manpower, equipment, tools & materials) |  | lot | 1 | 3400000 |  |  | 3400000 | 11147.54
3.1.4 | Field Auxiliary Room (6x4.5M) |  | lot | 1 | 10760852.99 |  |  | 10760852.99 | 35281.49
3.2 | Site Works - Mechanical Works | [6 empty] | 18155589.18 | 59526.52
3.2.2 | Fabrication & Installation of Mechanical Bulks (equipment, tools & manpower) |  | lot | 1 | 18155589.18 |  |  | 18155589.18 | 59526.52
3.3 | Site Works - EI&C | [6 empty] | 158967491.5 | 521204.89
3.3.1 | Fabrication & Installation of El&C Bulks (equipment tools & materials) |  | lot | 1 | 158967491.5 |  |  | 158967491.5 | 521204.89
4 | Testing Inspection, Pre-com and Commissioning & Pipe Stress Analysis | [6 empty] | 4200000 | 13770.49
4.1.1 | Testing Inspection, Pre-com and Commissioning |  | lot | 1 | 3000000 |  |  | 3000000 | 9836.07
4.1.2 | Pipe Stress Analysis |  | lot | 1 | 1200000 |  |  | 1200000 | 3934.43
TOTAL AMOUNT FOR THIS VARIATION ORDER REQUEST NO. 052_Rev 4 | [7 empty] | 787783145.6 | 2582895.56

## Mechanical (hidden)
Company Estimate | [19 empty] | Qty Variance
[10 empty] | ITEM NO. | DESCRIPTION | UoM | QTY | UNIT COST | Profit, O/H | Total Unit Cost | TOTAL COST, IN NAIRA | TOTAL COST IN USD |  | METS - SPDC
ITEM NO. | DESCRIPTION | UoM | QTY | UNIT COST US$ | TOOLS & EQUIPMENT$ | Man-power $ | Contractors Mark-UP $ | Total cost USD | TOTAL UNIT COST |  |  |  | a | b | c | d = b + c | e = d x a | f = e / 305 |  |  | (METS - SPDC)/SPDC | Qty Variance (METS - SPDC) |  | unit cost variance with out mark up |  | unit cost variance with mark up | Total Cost Variance NGN | Variance USD | Variance FUSD | % of total variance (NGN)
1 | Procurement and Installation of all Mechanical Materials to Complete the Tie-in of PIG Receiver AGB2-A-2301 & 2302 | [8 empty] | 1 | PROCUREMENT | [5 empty] | 578966448.93 | 1898250.65
1.1 | MECHANICAL SCOPE OF WORKS (PROCURE & INSTALL) | [6 empty] | 21866.1748 |  | 1.1 | MECHANICAL | [5 empty] | 10518630.59 | 34487.31 |  |  | 57.72% | [7 empty] | 12621.1352
1.1.1 | PIPES | [8 empty] | 1.1.1 | PIPES | [5 empty] | 6260162.22 | 20525.12 | 1.1.1
1.1.1.1 | 2"- SCH.40 ASTM A106-B (Instrument Air Line) (11412) | M | 30 | 6.0673 | 0.3183 | 0.47746 | 0.91009 | 233.193 | 7.7731 | 1.1.1.1 | 2"- SCH.40 ASTM A106-B (Instrument Air Line) (11412) | M | 30 | 3568.5 | 1070.55 | 4639.05 | 139171.5 | 456.3 | 1.1.1.1 | 0 | 95.67% | 0 | 3.9269 | 5.6327 | 7.4369 | 9.1427 |  |  | 223.107 | 1.768%
1.1.1.2 | 3"- SCH.40 ASTM A106-B (61412) | M | 370 | 12.7507 | 0.66894 | 1.0034 | 1.9126 | 6044.1935 | 16.3357 | 1.1.1.2 | 3"- SCH.40 ASTM A106-B (61412) | M | 191 | 7417.8 | 2225.34 | 9643.14 | 1841839.74 | 6038.82 | 1.1.1.2 | -179 | -0.0889% | -179 | 7.985 | 11.5699 | 15.2812 | 18.8661 |  |  | -5.3735 | -0.04258%
1.1.1.3 | 4"- SCH.40 ASTM A333-6 (11492) | M | 61 | 18.1781 | 0.95367 | 1.4305 | 2.7267 | 1420.6253 | 23.2889 | 1.1.1.3 | 4"- SCH.40 ASTM A333-6 (11492) | M | 59 | 18345.6 | 5503.68 | 23849.28 | 1407107.52 | 4613.47 | 1.1.1.3 | -2 | 224.7% | -2 | 36.8606 | 41.9715 | 54.9054 | 60.0163 |  |  | 3192.8447 | 25.3%
1.1.1.4 | 8"- 26mm Thickness ASTM A333-6 (151432) | M | 29 | 139.3809 | 7.3123 | 10.9685 | 20.9071 | 5178.4947 | 178.5688 | 1.1.1.4 | 8"- 26mm Thickness ASTM A333-6 (151432) | M | 33 | 66947.4 | 20084.22 | 87031.62 | 2872043.46 | 9416.54 | 1.1.1.4 | 4 | 81.84% | 4 | 40.9309 | 80.1188 | 106.7808 | 145.9687 |  |  | 4238.0453 | 33.58%
1.1.2 | TEE |  |  |  | 0 | 0 |  |  | 0 | 1.1.2 | TEE | [5 empty] | 82803.24 | 271.49 | 1.1.2 |  |  | 0 | 0 | 0 | 0 | 0
1.1.2.1 | 10" X 3" Branch Outlet 61412 | PC | 1 | 131.9672 | 6.9234 | 10.3851 | 19.7951 | 169.0707 | 169.0707 | 1.1.2.1 | 10" X 3" Branch Outlet 61412 | PC | 1 | 45793.8 | 13738.14 | 59531.94 | 59531.94 | 195.19 | 1.1.2.1 | 0 | 15.45% | 0 | -18.9271 | 18.1764 | 26.116 | 63.2195 |  |  | 26.1193 | 0.2069%
1.1.2.2 | 3" x 3" Equal Tee 61412 ASTM A234-WPB | PC | 1 | 6.586 | 0.34552 | 0.51828 | 0.9879 | 8.4377 | 8.4377 | 1.1.2.2 | 3" x 3" Equal Tee 61412 ASTM A234-WPB | PC | 1 | 4475.25 | 1342.58 | 5817.83 | 5817.83 | 19.07 | 1.1.2.2 | 0 | 126% | 0 | 6.2353 | 8.087 | 10.6372 | 12.4889 |  |  | 10.6323 | 0.08424%
1.1.2.3 | 3" x 3/4" Branch Outlet 61412 | PC | 2 | 37.7049 | 1.9781 | 2.9672 | 5.6557 | 96.6118 | 48.3059 | 1.1.2.3 | 3" x 3/4" Branch Outlet 61412 | PC | 3 | 4475.25 | 1342.58 | 5817.83 | 17453.48 | 57.22 | 1.1.2.3 | 1 | -40.77% | 1 | -33.633 | -23.032 | -29.2311 | -18.6301 |  |  | -39.3918 | -0.3121%
1.1.3 | ELBOW |  |  |  | 0 | 0 |  |  | 0 | 1.1.3 | ELBOW | [5 empty] | 1122828.82 | 3681.41 | 1.1.3 |  |  |  | 0 | 0 | 0 | 0
1.1.3.1 | 2" - 150#, Elbow 90 deg LR bw (ASTM A234-WPB) | PC | 7 | 5.6557 | 0.29672 | 0.44507 | 0.84836 | 50.7212 | 7.2459 | 1.1.3.1 | 2" - 150#, Elbow 90 deg LR bw (ASTM A234-WPB) | PC | 9 | 2237.63 | 671.29 | 2908.91 | 26180.21 | 85.84 | 1.1.3.1 | 2 | 69.24% | 2 | 0.090604 | 1.6808 | 2.2915 | 3.8817 |  |  | 35.1188 | 0.2783%
[9 empty] | 0 | 1.1.3.2 | 3" - 600#, Elbow 90 deg LR bw (ASTM A234-WPLB) | PC | 11 | 8950.5 | 2685.15 | 11635.65 | 127992.15 | 419.65 |  |  |  | 11 | 29.3459 | 29.3459 | 38.1497 | 38.1497 |  |  | 419.65 | 3.325%
1.1.3.2 | 4" - 150#, Elbow 90 deg LR bw (ASTM A420-WPL6) | PC | 14 | 22.623 | 1.1869 | 1.7803 | 3.3934 | 405.7697 | 28.9836 | 1.1.3.2 | 4" - 150#, Elbow 90 deg LR bw (ASTM A420-WPL6) | PC | 12 | 15856.43 | 4756.93 | 20613.35 | 247360.23 | 811.02 | 1.1.3.2 |  | 99.87% | -2 | 23.0047 | 29.3653 | 38.6012 | 44.9618 |  |  | 405.2503 | 3.211%
1.1.3.3 | 8" - 1500#, Elbow 90 deg LR bw (ASTM A420-WPL6) | PC | 14 | 149.5 | 7.8432 | 11.7648 | 22.425 | 2681.4616 | 191.533 | 1.1.3.3 | 8" - 1500#, Elbow 90 deg LR bw (ASTM A420-WPL6) | PC | 10 | 55484.33 | 16645.3 | 72129.62 | 721296.23 | 2364.91 | 1.1.3.3 | -4 | -11.81% | -4 | -9.6171 | 32.4158 | 44.9576 | 86.9906 |  |  | -316.5516 | -2.508%
1.1.4 | FLANGES |  |  |  | 0 | 0 |  |  | 0 | 1.1.4 | FLANGES | [5 empty] | 542750.78 | 1779.51 | 1.1.4 |  |  |  | 0 | 0 | 0 | 0
1.1.4.1 | 2" - 150#, SCH 40, WN, RF FLANGE, ASTM A105 | PC | 2 | 9.0117 | 0.47278 | 0.70917 | 1.3518 | 23.0908 | 11.5454 | 1.1.4.1 | 2" - 150#, SCH 40, WN, RF FLANGE, ASTM A105 | PC | 2 | 5896.8 | 1769.04 | 7665.84 | 15331.68 | 50.27 | 1.1.4.1 | 0 | 117.7% | 0 | 7.7884 | 10.3221 | 13.5885 | 16.1222 |  |  | 27.1792 | 0.2153%
1.1.4.2 | 3"-600#, SCH 40, WN, RF FLANGE, ASTM A105 | PC | 14 | 16.6953 | 0.87588 | 1.3138 | 2.5043 | 299.4506 | 21.3893 | 1.1.4.2 | 3"-600#, SCH 40, WN, RF FLANGE, ASTM A105 | PC | 10 | 16461.9 | 4938.57 | 21400.47 | 214004.7 | 701.65 | 1.1.4.2 | -4 | 134.3% | -4 | 32.5841 | 37.2781 | 48.7761 | 53.4702 |  |  | 402.1994 | 3.187%
1.1.4.3 | 4" - 150#, SCH 40, WN, RF FLANGE, ASTM A350-LF2 cl 1 | PC | 4 | 17.9692 | 0.94271 | 1.4141 | 2.6954 | 92.0852 | 23.0213 | 1.1.4.3 | 4" - 150#, SCH 40, WN, RF FLANGE, ASTM A350-LF2 cl 1 | PC | 4 | 19919.25 | 5975.78 | 25895.03 | 103580.1 | 339.61 | 1.1.4.3 | 0 | 268.8% | 0 | 42.2877 | 47.3399 | 61.8804 | 66.9326 |  |  | 247.5248 | 1.961%
1.1.4.4 | 8" - 1500#, 1.024" TH, WN, RF FLANGE, ASTM A105 | PC | 4 | 237.5018 | 12.46 | 18.69 | 35.6253 | 1217.1085 | 304.2771 | 1.1.4.4 | 8" - 1500#, 1.024" TH, WN, RF FLANGE, ASTM A105 | PC | 4 | 35000 | 10500 | 45500 | 182000 | 596.72 | 1.1.4.4 | 0 | -50.97% | 0 | -189.523 | -122.7477 | -155.0968 | -88.3215 |  |  | -620.3885 | -4.915%
1.1.4.5 | 3/4" - 600#, SCH 80, WN, RF FLANGE, ASTM A105 | PC | 2 | 4.1061 | 0.21542 | 0.32312 | 0.61591 | 10.5211 | 5.2605 | 1.1.4.5 | 3/4" - 600#, SCH 80, WN, RF FLANGE, ASTM A105 | PC | 1 | 4475.25 | 1342.58 | 5817.83 | 5817.83 | 19.07 | 1.1.4.5 | -1 | 81.26% | -1 | 9.4124 | 10.5669 | 13.8143 | 14.9688 |  |  | 8.5489 | 0.06774%
1.1.4.6 | 3/4" - 600#, SCH 80, Blind Flange, ASTM A105 | PC | 2 | 18.4028 | 0.96546 | 1.4482 | 2.7604 | 47.1538 | 23.5769 | 1.1.4.6 | 3/4" - 600#, SCH 80, Blind Flange, ASTM A105 | PC | 1 | 5961.15 | 1788.35 | 7749.5 | 7749.5 | 25.41 | 1.1.4.6 | -1 | -46.11% | -1 | -4.0321 | 1.142 | 1.8313 | 7.0054 |  |  | -21.7438 | -0.1723%
1.1.4.7 | 3" 600# SPEC BLIND ASTM A516-60/65/70 | PC | 2 | 30.3822 | 1.5939 | 2.3909 | 4.5573 | 77.8488 | 38.9244 | 1.1.4.7 | 3" 600# SPEC BLIND ASTM A516-60/65/70 | PC | 1 | 10974.6 | 3292.38 | 14266.98 | 14266.98 | 46.78 | 1.1.4.7 | -1 | -39.91% | -1 | -2.9421 | 5.6001 | 7.8526 | 16.3947 |  |  | -31.0688 | -0.2462%
1.1.5 | GASKETS |  |  |  | 0 | 0 |  |  | 0 | 1.1.5 | GASKETS | [5 empty] | 290718.38 | 953.18 | 1.1.5 |  |  |  | 0 | 0 | 0 | 0
1.1.5.1 | 2"-150# | PC | 2 | 4.918 | 0.25801 | 0.38702 | 0.7377 | 12.6015 | 6.3008 | 1.1.5.1 | 2"-150# | PC | 4 | 2827.91 | 848.37 | 3676.29 | 14705.15 | 48.21 | 1.1.5.1 | 2 | 282.6% | 2 | 2.9711 | 4.3538 | 5.7526 | 7.1354 |  |  | 35.6085 | 0.2821%
1.1.5.2 | 3"-600# | PC | 14 | 11.4754 | 0.60203 | 0.90305 | 1.7213 | 205.8252 | 14.7018 | 1.1.5.2 | 3"-600# | PC | 22 | 4642.31 | 1392.69 | 6035.01 | 132770.14 | 435.31 | 1.1.5.2 | 8 | 111.5% | 8 | 0.51889 | 3.7453 | 5.0851 | 8.3115 |  |  | 229.4848 | 1.818%
1.1.5.3 | 4"-150# | PC | 4 | 9.8361 | 0.51603 | 0.77404 | 1.4754 | 50.4062 | 12.6015 | 1.1.5.3 | 4"-150# | PC | 8 | 6095.25 | 1828.58 | 7923.83 | 63390.6 | 207.84 | 1.1.5.3 | 4 | 312.3% | 4 | 7.3829 | 10.1484 | 13.3782 | 16.1437 |  |  | 157.4338 | 1.247%
1.1.5.4 | 8"-1500# | PC | 4 | 25.5738 | 1.3417 | 2.0125 | 3.8361 | 131.0561 | 32.764 | 1.1.5.4 | 8"-1500# | PC | 8 | 7087.5 | 2126.25 | 9213.75 | 73710 | 241.67 | 1.1.5.4 | 4 | 84.4% | 4 | -9.5263 | -2.3361 | -2.555 | 4.6352 |  |  | 110.6139 | 0.8764%
1.1.5.5 | 3/4"-600# | PC | 4 | 0.62842 | 0.032968 | 0.049453 | 0.094262 | 3.2204 | 0.8051 | 1.1.5.5 | 3/4"-600# | PC | 4 | 1181.25 | 354.38 | 1535.63 | 6142.5 | 20.14 | 1.1.5.5 | 0 | 525.4% | 0 | 3.0679 | 3.2445 | 4.2298 | 4.4064 |  |  | 16.9196 | 0.1341%
1.1.1.6 | BOLTS & NUTS |  |  |  | 0 | 0 |  |  | 0 | 1.1.1.6 | BOLTS & NUTS | [5 empty] | 970392.15 | 3181.61 | 1.1.1.6 |  |  |  | 0 | 0 | 0 | 0
1.1.1.6.1 | 5/8" x 90mm (for 2" Class 150# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 24 | 3.1499 | 0.16525 | 0.24788 | 0.47248 | 96.8517 | 4.0355 | 1.1.1.6.1 | 5/8" x 90mm (for 2" Class 150# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 36 | 826.88 | 248.06 | 1074.94 | 38697.75 | 126.88 | 1.1.1.6.1 | 12 | 31% | 12 | -1.3244 | -0.4388 | -0.51109 | 0.37452 |  |  | 30.0283 | 0.2379%
1.1.1.6.2 | 5/8" x 130mm (for 3" Class 600# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 96 | 4.5498 | 0.2387 | 0.35804 | 0.68247 | 559.5876 | 5.829 | 1.1.1.6.2 | 5/8" x 130mm (for 3" Class 600# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 108 | 1157.63 | 347.29 | 1504.91 | 162530.55 | 532.89 | 1.1.1.6.2 | 12 | -4.771% | 12 | -2.0335 | -0.75431 | -0.89491 | 0.38431 |  |  | -26.6976 | -0.2115%
1.1.1.6.3 | 5/8" x 100mm (for 4" Class 150# Flanges, RF) (ASTM A320-L7/A194-4) | PC | 32 | 3.1499 | 0.16525 | 0.24788 | 0.47248 | 129.1356 | 4.0355 | 1.1.1.6.3 | 5/8" x 100mm (for 4" Class 150# Flanges, RF) (ASTM A320-L7/A194-4) | PC | 48 | 921.38 | 276.41 | 1197.79 | 57493.8 | 188.5 | 1.1.1.6.3 | 16 | 45.97% | 16 | -1.0146 | -0.12896 | -0.10831 | 0.7773 |  |  | 59.3644 | 0.4704%
1.1.1.6.4 | 1-5/8" x 340mm (for 8" Class 1500# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 48 | 41.0567 | 2.1539 | 3.2309 | 6.1585 | 2524.8008 | 52.6 | 1.1.1.6.4 | 1-5/8" x 340mm (for 8" Class 1500# Flanges, RF) (ASTM A193-B7/A194-2H) | PC | 72 | 7371 | 2211.3 | 9582.3 | 689925.6 | 2262.05 | 1.1.1.6.4 | 24 | -10.41% | 24 | -28.4328 | -16.8894 | -21.1826 | -9.6393 |  |  | -262.7508 | -2.082%
1.1.1.6.5 | 5/8" x 150mm (for 3" Class 600# Blind/Spacer, RF) (ASTM A193-B7/A194-2H) | PC | 16 | 4.7248 | 0.24788 | 0.37182 | 0.70872 | 96.8517 | 6.0532 | 1.1.1.6.5 | 5/8" x 150mm (for 3" Class 600# Blind/Spacer, RF) (ASTM A193-B7/A194-2H) | PC | 12 | 1393.88 | 418.16 | 1812.04 | 21744.45 | 71.29 | 1.1.1.6.5 | -4 | -26.39% | -4 | -1.4831 | -0.15472 | -0.11212 | 1.2163 |  |  | -25.5617 | -0.2025%
1.1.1.7 | [8 empty] | 0 | 1.1.1.7 | VALVE | [5 empty] | 1248975 | 4095 | 1.1.1.7 |  |  |  | 0 | 0 | 0 | 0
1.1.1.7.1 | [8 empty] | 0 | 1.1.1.7.1 | 3/4" Ball Valve #61412 | PC | 1 | 45750 | 13725 | 59475 | 59475 | 195 | 1.1.1.7.1 | 1 |  | 1 | 150 | 150 | 195 | 195 |  |  | 195 | 1.545%
1.1.1.7.2 | [8 empty] | 0 | 1.1.1.7.2 | 3" Ball Valve #61412 | PC | 2 | 228750 | 68625 | 297375 | 594750 | 1950 | 1.1.1.7.2 | 2 |  | 2 | 750 | 750 | 975 | 975 |  |  | 1950 | 15.45%
1.1.1.7.3 | [9 empty] | 1.1.1.7.3 | 3" Check Valve #61412 | PC | 2 | 228750 | 68625 | 297375 | 594750 | 1950 | 1.1.1.7.3 | 2 |  | 2 | 750 | 750 | 975 | 975 |  |  | 1950 | 15.45%
[24 empty] | TOTAL VARIANCE USD |  |  |  |  | 12621.1452

## Elect and PACO (hidden)
Company Estimate
[10 empty] | ITEM NO. | DESCRIPTION | UoM | QTY | UNIT COST | Profit, O/H | Total Unit Cost | TOTAL COST, IN NAIRA | TOTAL COST IN USD |  |  | Qty Variance
ITEM NO. | DESCRIPTION | UoM | QTY | UNIT COST US$ | TOOLS & EQUIPMENT$ | Man-power $ | Contractors Mark-UP $ | Total cost USD |  |  |  |  | a | b | c | d = b + c | e = d x a | f = e / 305 | SPDC | METS | METS - SPDC | (METS - SPDC)/SPDC | Qty Variance (METS - SPDC) |  | unit cost variance with out mark up |  | unit cost variance with mark up | Total Cost Variance NGN | Variance USD | Variance FUSD | % of total variance (NGN)
1.2 | ELECTRICAL, INSTRUMENTATIONS AND CONTROLS SCOPE OF WORKS (PROCURE & INSTALL) |  |  |  | 0 | 0 | 0 | 224140.656 |  | 1.2 | ELEC., INST. AND CONTROLS | [5 empty] | 568447818.34 | 1863763.34
1.2.1 | Cables |  |  |  | 0 | 0 | 0 | 12815.4292 |  | 1.2.3 | CABLES | [5 empty] | 19947689.13 | 65402.26
1.2.1.1 | Foundation Fieldbus cable, Type A (XLPE/MS/LSZH/SWA/LSZH) 1 X 0.8 mm² | M | 300 | 1.6472 | 0.088119 | 0.037765 | 0.24707 | 606.037 | 2.0201 | 1.2.3.1 | Turck Foundation Fieldbus cable, Type A ( PEI-MS-PE-SWA-PVC) 1x0.8mm² (Green) | M | 700 | 6917.4 | 2075.22 | 8992.62 | 6294834 | 20638.8 | 1.2.1.1 | 1.2.3.1 | 400 | 3306% | 400 | 20.6599 | 21.0328 | 27.4639 | 27.8368 |  |  | 20032.763
1.2.1.2 | Foundation Fieldbus cable, Type A (XLPE/MS/LSZH/SWA/LSZH) 1 X 0.8 mm² | M | 1,000 | 1.6472 | 0.088119 | 0.037765 | 0.24707 | 2020.1232 | 2.0201 | [12 empty] | -100% | -1000 | -2.0201 | -1.6472 | -2.0201 | -1.6472 |  |  | -2020.1232
1.2.1.3 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 5 X 1.0 mm² | M | 1,000 | 1.8605 | 0.09953 | 0.042656 | 0.27907 | 2281.7219 | 2.2817 | [12 empty] | -100% | -1000 | -2.2817 | -1.8605 | -2.2817 | -1.8605 |  |  | -2281.7219
1.2.1.4 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 5 X 2.5 mm² | M | 1,000 | 2.2871 | 0.12235 | 0.052437 | 0.34306 | 2804.9193 | 2.8049 | [12 empty] | -100% | -1000 | -2.8049 | -2.2871 | -2.8049 | -2.2871 |  |  | -2804.9193
1.2.1.5 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 1 X 1.0 mm² | M | 300 | 1.6472 | 0.088119 | 0.037765 | 0.24707 | 606.037 | 2.0201 | [12 empty] | -100% | -300 | -2.0201 | -1.6472 | -2.0201 | -1.6472 |  |  | -606.037
1.2.1.6 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 2 X 1.0 mm² | M | 300 | 1.6946 | 0.090655 | 0.038852 | 0.25418 | 623.4769 | 2.0783 | [12 empty] | -100% | -300 | -2.0783 | -1.6946 | -2.0783 | -1.6946 |  |  | -623.4769
1.2.1.7 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 20 X 1.0 mm² | M | 500 | 2.5952 | 0.13884 | 0.059501 | 0.38928 | 1591.392 | 3.1828 | [12 empty] | -100% | -500 | -3.1828 | -2.5952 | -3.1828 | -2.5952 |  |  | -1591.392
1.2.1.8 | Amoured collective screen (XLPE/MS/LSZH/SWA/LSZH) 5 X 1.0 mm² | M | 1,000 | 1.8605 | 0.09953 | 0.042656 | 0.27907 | 2281.7219 | 2.2817 | [12 empty] | -100% | -1000 | -2.2817 | -1.8605 | -2.2817 | -1.8605 |  |  | -2281.7219
[9 empty] | 0 | 1.2.3.2 | Amoured collective screen (XLPE/MS/LSZH/SWA/SZH) 10 x 1.5mm² (Blue) | M | 700 | 3900 | 1170 | 5070 | 3549000 | 11636.07 |  |  | 700 |  | 700 | 12.7869 | 12.7869 | 16.623 | 16.623 |  |  | 11636.07
[9 empty] | 0 | 1.2.3.3 | Amoured collective screen (XLPE/MS/LSZH/SWA/SZH) 14 x 1.5mm² (Black) | M | 700 | 4465 | 1339.5 | 5804.5 | 4063150 | 13321.8 |  |  | 700 |  | 700 | 14.6393 | 14.6393 | 19.0311 | 19.0311 |  |  | 13321.8
[9 empty] | 0 | 1.2.3.4 | Amoured collective screen (XLPE/MS/LSZH/SWA/SZH) 10 x 1.5mm² (Black) | M | 700 | 3900 | 1170 | 5070 | 3549000 | 11636.07 |  |  | 700 |  | 700 | 12.7869 | 12.7869 | 16.623 | 16.623 |  |  | 11636.07
[9 empty] | 0 | 1.2.3.5 | Amoured collective screen (XLPE/MS/LSZH/SWA/SZH) 5 x 1.5mm² (Black) | M | 700 | 2738.14 | 821.44 | 3559.58 | 2491705.13 | 8169.53 |  |  | 700 |  | 700 | 8.9775 | 8.9775 | 11.6708 | 11.6708 |  |  | 8169.53
[9 empty] | 0 | 1.2.3.6 | 70mm2 green/yellow PVC insulated stranded copper cable c/w 70mm2 "c" shape connectors, 70mm2 compression type lug and earth bosses | M | 700 | 7500 | 2250 | 9750 | 6825000 | 22377.05 |  |  | 700 |  | 700 | 24.5902 | 24.5902 | 31.9672 | 31.9672 |  |  | 22377.05
1.2.2 | Junction Box |  |  |  | 0 | 0 | 0 | 4463.3833 | 0
1.2.2.1 | PAS Junction Box-1 Field barrier installed | PC | 2 | 606.5574 | 32.4494 | 13.9069 | 90.9836 | 1487.7944 | 743.8972 | [12 empty] | -100% | -2 | -743.8972 | -606.5574 | -743.8972 | -606.5574 |  |  | -1487.7944
1.2.2.2 | SIS Junction Box | PC | 2 | 606.5574 | 32.4494 | 13.9069 | 90.9836 | 1487.7944 | 743.8972 | [12 empty] | -100% | -2 | -743.8972 | -606.5574 | -743.8972 | -606.5574 |  |  | -1487.7944
1.2.2.3 | F & G Junction Box | PC | 2 | 606.5574 | 32.4494 | 13.9069 | 90.9836 | 1487.7944 | 743.8972 | [12 empty] | -100% | -2 | -743.8972 | -606.5574 | -743.8972 | -606.5574 |  |  | -1487.7944
1.2.3 | Cable Marker |  |  |  | 0 | 0 | 0 | 299.7645 | 0 | 1.2.1 | Cable Marker | [5 empty] | 1033760 | 3389.38
1.2.3.1 | PVC Conductor and cable markers, 3 -3.7 mm, 12 x 4.6 mm, White Cable Mark ( 0,1,A,B,C,D,E,G,I,M,P,S,T,V,X,Z,” -“) | PCK | 20 | 11.7835 | 0.63039 | 0.27017 | 1.7675 | 289.0323 | 14.4516 | 1.2.1.1 | PVC Conductor and cable markers, 3 -3.7 mm, 12 x 4.6 mm, White Cable Mark ( 0,1,A,B,C,D,E,G,I,M,P,S,T,V,X,Z,” -“) | PCK | 20 | 35000 | 10500 | 45500 | 910000 | 2983.61 | 1.2.3.1 | 1.2.1.1 | 0 | 932.3% | 0 | 100.3025 | 102.9706 | 134.7287 | 137.3968 |  |  | 2694.5777
1.2.3.2 | Stainless Steel Cable Markers (W *L: 15 mm * 90mm) | PCK | 1 | 8.7508 | 0.46815 | 0.20064 | 1.3126 | 10.7323 | 10.7323 | 1.2.1.2 | Stainless Steel Cable Markers (W *L: 15 mm * 90mm) | PCK | 1 | 95200 | 28560 | 123760 | 123760 | 405.77 | 1.2.3.2 | 1.2.1.2 | 0 | 3681% | 0 | 301.3989 | 303.3803 | 395.0382 | 397.0196 |  |  | 395.0377
1.2.4 | Cable Lugs |  |  |  | 0 | 0 | 0 | 2.9067 | 0 | 1.2.2 | Cable Lugs | [5 empty] | 39000 | 127.87
1.2.4.1 | Wire end ferrules with plastic collar-Size _1.0mm², 2.5mm² | PCK | 2 | 1.185 | 0.063395 | 0.027169 | 0.17775 | 2.9067 | 1.4533 | 1.2.2.1 | Wire end ferrules with plastic collar-Size _1.0mm², 2.5mm² | PCK | 2 | 15000 | 4500 | 19500 | 39000 | 127.87 | 1.2.4.1 | 1.2.2.1 | 0 | 4299% | 0 | 47.727 | 47.9953 | 62.4811 | 62.7494 |  |  | 124.9633
1.2.5 | FIRE AND GAS |  |  |  | 0 | 0 | 0 | 84378.0501 | 0
1.2.5.1 | Point gas Detectors – Draeger_ PIR type 334 Part # 68 10 100 | PC | 4 | 3800 | 203.2909 | 87.1247 | 570 | 18641.6622 | 4660.4156 | [12 empty] | -100% | -4 | -4660.4156 | -3800 | -4660.4156 | -3800 |  |  | -18641.6622
1.2.5.2 | Open Path Gas Detector – Draeger_Pulsar2 | PC | 2 | 15000 | 802.464 | 343.9132 | 2250 | 36792.7544 | 18396.3772 | [12 empty] | -100% | -2 | -18396.3772 | -15000 | -18396.3772 | -15000 |  |  | -36792.7544
1.2.5.3 | Manual Call Point -MEDC_ BG2EDC4NR | PC | 2 | 800 | 42.7981 | 18.342 | 120 | 1962.2802 | 981.1401 | [12 empty] | -100% | -2 | -981.1401 | -800 | -981.1401 | -800 |  |  | -1962.2802
1.2.5.4 | Sounder -MEDC_ DBIPBS024ANTNR | PC | 2 | 1500 | 80.2464 | 34.3913 | 225 | 3679.2754 | 1839.6377 | [12 empty] | -100% | -2 | -1839.6377 | -1500 | -1839.6377 | -1500 |  |  | -3679.2754
1.2.5.5 | Beacon -MEDC_ XB15B02406BND+TR | PC | 2 | 9500 | 508.2272 | 217.8117 | 1425 | 23302.0778 | 11651.0389 | [12 empty] | -100% | -2 | -11651.0389 | -9500 | -11651.0389 | -9500 |  |  | -23302.0778
1.2.6 | CONTROL SYSTEM |  |  |  | 0 | 0 | 0 | 0 | 0
1.2.6.1 | PAS |  |  |  | 0 | 0 | 0 | 25128.0076 | 0 | 1.2.4 | DCS | [5 empty] | 11692654.16 | 38336.57
1.2.6.1.1 | Analog Input - DeltaV Analog Input cards - Part No. - VE4003S2B3 | Nos. | 6 | 2079.6926 | 111.2586 | 47.6822 | 311.9539 | 15303.5235 | 2550.5872 | [12 empty] | -100% | -6 | -2550.5872 | -2079.6926 | -2550.5872 | -2079.6926 |  |  | -15303.5235
1.2.6.1.2 | Digital Input - DeltaV Digital Input cards - Part No. - VE4001S2T2B4 | Nos. | 4 | 2002.6669 | 107.1379 | 45.9162 | 300.4 | 9824.4842 | 2456.121 | [12 empty] | -100% | -4 | -2456.121 | -2002.6669 | -2456.121 | -2002.6669 |  |  | -9824.4842
[9 empty] | 0 | 1.2.4.1 | Redundant H1 Fieldbus I/O Interface Cards with Integrated Segment Power; Two wide Termination Block with Connections for 2 H1 Segments (Model No. SE4037P1) | SET | 1 | 7493850 | 2248155 | 9742005 | 9742005 | 31941 |  |  | 1 |  | 1 | 24570 | 24570 | 31941 | 31941 |  |  | 31941
[9 empty] | 0 | 1.2.4.2 | Fieldbus Segment Protector R2, 12 Outputs, DIN rail mounted (Model No. R2-SP-N4) | SET | 1 | 691740 | 207522 | 899262 | 899262 | 2948.4 |  |  | 1 |  | 1 | 2268 | 2268 | 2948.4 | 2948.4 |  |  | 2948.4
[9 empty] | 0 | 1.2.4.3 | Control Network Cable 100 meters (VE6102) | ROLL | 2 | 864.68 | 259.4 | 1124.08 | 2248.16 | 7.37 |  |  | 2 |  | 2 | 2.835 | 2.835 | 3.6855 | 3.6855 |  |  | 7.37
[9 empty] | 0 | 1.2.4.4 | 10BaseT Cable Connector Kit with Crimp Tool (VE6103C1) | SET | 2 | 403515 | 121054.5 | 524569.5 | 1049139 | 3439.8 |  |  | 2 |  | 2 | 1323 | 1323 | 1719.9 | 1719.9 |  |  | 3439.8
1.2.6.2 | SIS |  |  |  | 0 | 0 | 0 | 32351.0382 | 0 | 1.2.5 | SIS | [5 empty] | 15684628.05 | 51425.01
1.2.6.2.1 | Analog Input - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 2 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 10783.6794 | 5391.8397 | [12 empty] | -100% | -2 | -5391.8397 | -4396.3871 | -5391.8397 | -4396.3871 |  |  | -10783.6794
1.2.6.2.2 | Digital Output - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 2 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 10783.6794 | 5391.8397 | [12 empty] | -100% | -2 | -5391.8397 | -4396.3871 | -5391.8397 | -4396.3871 |  |  | -10783.6794
1.2.6.2.3 | Digital Input - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 2 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 10783.6794 | 5391.8397 | [12 empty] | -100% | -2 | -5391.8397 | -4396.3871 | -5391.8397 | -4396.3871 |  |  | -10783.6794
[9 empty] | 0 | 1.2.5.1 | Redundant Logic Solver (VS3202) | PC | 1 | 5533920 | 1660176 | 7194096 | 7194096 | 23587.2 |  |  | 1 |  | 1 | 18144 | 18144 | 23587.2 | 23587.2 |  |  | 23587.2
[9 empty] | 0 | 1.2.5.2 | SISNet Terminator Assembly (VS6051) | SET | 1 | 190228.5 | 57068.55 | 247297.05 | 247297.05 | 810.81 |  |  | 1 |  | 1 | 623.7 | 623.7 | 810.81 | 810.81 |  |  | 810.81
[9 empty] | 0 | 1.2.5.3 | Redundant SISNet Repeater (VS6002) | PC | 1 | 3746925 | 1124077.5 | 4871002.5 | 4871002.5 | 15970.5 |  |  | 1 |  | 1 | 12285 | 12285 | 15970.5 | 15970.5 |  |  | 15970.5
[9 empty] | 0 | 1.2.5.4 | 2-Wide Power/Controller Carrier (VE3051C0) | PC | 1 | 317047.5 | 95114.25 | 412161.75 | 412161.75 | 1351.35 |  |  | 1 |  | 1 | 1039.5 | 1039.5 | 1351.35 | 1351.35 |  |  | 1351.35
[9 empty] | 0 | 1.2.5.5 | 8-Wide I/O Interface Carrier with Carrier Shield Bar, Single Enhanced Carrier Extender Cable, and Redundant SISNet Coax Cables (VE4050E1C2) | PC | 1 | 1268190 | 380457 | 1648647 | 1648647 | 5405.4 |  |  | 1 |  | 1 | 4158 | 4158 | 5405.4 | 5405.4 |  |  | 5405.4
[9 empty] | 0 | 1.2.5.6 | System Power Supply, 24 Vdc Input (SE5009) | PC | 1 | 1008787.5 | 302636.25 | 1311423.75 | 1311423.75 | 4299.75 |  |  | 1 |  | 1 | 3307.5 | 3307.5 | 4299.75 | 4299.75 |  |  | 4299.75
1.2.6.3 | FGS |  |  |  | 0 | 0 | 0 | 64702.0764 | 0 | 1.2.6 | FGS | [5 empty] | 15699615.75 | 51474.15
1.2.6.3.1 | Analog Input - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 6 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 32351.0382 | 5391.8397 | [12 empty] | -100% | -6 | -5391.8397 | -4396.3871 | -5391.8397 | -4396.3871 |  |  | -32351.0382
1.2.6.3.2 | Digital Output - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 4 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 21567.3588 | 5391.8397 | [12 empty] | -100% | -4 | -5391.8397 | -4396.3871 | -5391.8397 | -4396.3871 |  |  | -21567.3588
1.2.6.3.3 | Digital Input - DeltaV SLS Redundant Logic Solver - Part No. - VS3202 | Nos. | 2 | 4396.3871 | 235.1962 | 100.7984 | 659.4581 | 10783.6794 | 5391.8397 | [12 empty] | -100% | -2 | -5391.8397 | -4396.3871 | -5391.8397 | -4396.3871 |  |  | -10783.6794
[10 empty] | 1.2.6.1 | Redundant Logic Solver (VS3202) | PC | 1 | 5533920 | 1660176 | 7194096 | 7194096 | 23587.2 |  |  | 1 |  | 1 | 18144 | 18144 | 23587.2 | 23587.2 |  |  | 23587.2
[10 empty] | 1.2.6.2 | SISNet Terminator Assembly (VS6051) | SET | 1 | 201757.5 | 60527.25 | 262284.75 | 262284.75 | 859.95 |  |  | 1 |  | 1 | 661.5 | 661.5 | 859.95 | 859.95 |  |  | 859.95
[10 empty] | 1.2.6.3 | Redundant SISNet Repeater (VS6002) | PC | 1 | 3746925 | 1124077.5 | 4871002.5 | 4871002.5 | 15970.5 |  |  | 1 |  | 1 | 12285 | 12285 | 15970.5 | 15970.5 |  |  | 15970.5
[10 empty] | 1.2.6.4 | 2-Wide Power/Controller Carrier (VE3051C0) | PC | 1 | 317047.5 | 95114.25 | 412161.75 | 412161.75 | 1351.35 |  |  | 1 |  | 1 | 1039.5 | 1039.5 | 1351.35 | 1351.35 |  |  | 1351.35
[10 empty] | 1.2.6.5 | 8-Wide I/O Interface Carrier with Carrier Shield Bar, Single Enhanced Carrier Extender Cable, and Redundant SISNet Coax Cables (VE4050E1C2) | PC | 1 | 1268190 | 380457 | 1648647 | 1648647 | 5405.4 |  |  | 1 |  | 1 | 4158 | 4158 | 5405.4 | 5405.4 |  |  | 5405.4
[10 empty] | 1.2.6.6 | System Power Supply, 24 Vdc Input (SE5009) | PC | 1 | 1008787.5 | 302636.25 | 1311423.75 | 1311423.75 | 4299.75 |  |  | 1 |  | 1 | 3307.5 | 3307.5 | 4299.75 | 4299.75 |  |  | 4299.75
[25 empty] | Total Variance in Price FUSD |  |  |  |  | 8391.644

## Eng and Design (hidden)
Company Estimate
[9 empty] | ITEM NO. | DESCRIPTION |  | UoM | QTY | UNIT COST | Profit, O/H | Total Unit Cost | TOTAL COST, IN NAIRA | TOTAL COST IN USD |  |  | Qty Variance
ITEM NO. | DESCRIPTION | UoM | QTY | UNIT COST US$ | TOOLS & EQUIPMENT$ | Man-power $ | Contractors Mark-UP $ | Total cost USD |  |  |  |  | a | b | c | d = b + c | e = d x a | f = e / 305 | SPDC | METS | METS - SPDC | (METS - SPDC)/SPDC | Qty Variance (METS - SPDC) | unit cost variance with out mark up | unit cost variance with mark up | Total Cost Variance NGN | Variance USD | Variance FUSD | % of total variance (NGN)
1.3 | ENGINEERING & DESIGN SCOPE OF WORKS | MH | 566 |  |  |  |  | 0 | 2 | ENGINEERING & DESIGN SCOPE OF WORKS, 1 man-day consits of the following: 1 No. Engineering Manager x 10% 1 No. Discipline Lead x 20% 1 No. Discipline Engineer x 40% 1 No. Designer / AutoCAD Operator x 100% | MH | MANDAYS | 399 | - |  |  | 12582763 | 41254.96
1.3.1 | Instruments & Controls |  | 266 | 883.9279 |  |  |  | 9973.9462 | 2.1 | EI&C | 1665 |  | 208 | 31516 |  |  | 6559267.5 | 21505.8 |  |  |  | 115.6% | [5 empty] | 11531.8538 | 56.95%
1.3.1.1 | Consolidated Instrument Cable Schedule (SDA-S17893-AGBG1-IN-4308-00002) |  | 10 | 33.259 |  |  | 4.9889 | 382.4787 | 2.1.1 | Consolidated Instrument Cable Schedule (SDA-S17893-AGBG1-IN-4308-00002) | 32 |  | 4 |  |  |  | - | - | 1.3.1.1 | 2.1.1 | -6 |  | -6
1.3.1.16 | Fire & Gas Cable Schedule |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2.1.2 | Fire & Gas Cable Schedule (SDA-S17893-AGBG1-IN-4308-00001) | 8 |  | 1 |  |  |  | - | - | 1.3.1.16 | 2.1.2 | 0 |  | -7
1.3.1.27 | Fire & Gas Junction Box Instrument Termination Diagram |  | 16 | 31.9803 |  |  | 4.797 | 588.438 | 2.1.4 | Instrument Junction Box Termination (SDA-S17893-AGBG1-IN-2389-00004) | 25 |  | 3 |  |  |  | - | - | 1.3.1.27 | 2.1.4 | -13 |  | -13
1.3.1.15 | Field Auxiliary Under FAR Cable Route / Tray lay-out |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2.1.5 | Cable Routing Diagram (SDA-S17893-AGBG1-IN-8801-00001-001, 002) | 80 |  | 10 |  |  |  | - | - | 1.3.1.15 | 2.1.5 | 2 |  | 2
1.3.1.4 | PAS Loop Wiring Drawing (SDA-S17893-AGBG1-IN-2347-00003-001) |  | 12 | 31.9803 |  |  | 4.797 | 441.3285 | 2.1.6 | PAS Loop Wiring Diagram (SDA-S17893-AGBG1-2347-00003-001) | 100 |  | 13 |  |  |  | - | - | 1.3.1.4 | 2.1.6 | 1 |  | 1
1.3.1.5 | SIS-FGS Loop Wiring (SDA-17893-AGBG1-IN-2347-00004-0001) |  | 8 | 31.9803 |  |  | 4.797 | 294.219 | 2.1.7 | SIS-FGS Loop Wiring System Drawing (SDA-S17893-AGBG1-IN-2347-00004-001) | 50 |  | 6 |  |  |  | - | - | 1.3.1.5 | 2.1.7 | -2 |  | -2
1.3.1.8 | Emergeny & Safety System Block Diagram (SDA-S17893-AGBG1-IN-0980-00001-XXX) |  | 16 | 31.9803 |  |  | 4.797 | 588.438 | 2.1.8 | Emergeny & Safety System Block Diagram (SDA-S17893-AGBG1-IN-0980-00001-001) | 32 |  | 4 |  |  |  | - | - | 1.3.1.8 | 2.1.8 | -12 |  | -12
1.3.1.9 | Overall System Architecture Drawing (SDA-17893-AGBG1-IN-0901-00003-001) |  | 16 | 31.9803 |  |  | 4.797 | 588.438 | 2.1.9 | Overall System Architecture Drawing (SDA-17893-AGBG1-IN-0901-00003-001) | 32 |  | 4 |  |  |  | - | - | 1.3.1.9 | 2.1.9 | -12 |  | -12
1.3.1.10 | I/O Range, alarm and trip setting reports / consolidated, alarm, trip and setting list (SDA-S17893-AGBG1-IN-4302-00001 |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2010-01-02 | I/O Range, alarm and trip setting reports / consolidated, alarm, trip and setting list (SDA- S17893-AGBG1-IN-4302-00001 | 16 |  | 2 |  |  |  | - | - | 1.3.1.10 | 2.1.10 | -6 |  | -6
1.3.1.11 | Cause and Effect Matrix (SDA-S17893-AGBG1-IN-6604-00001-001) |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2011-01-02 | Consolidated Cause and Effect Matrix (SDA-S17893-AGBG1-IN-6604-00001-001) | 20 |  | 3 |  |  |  | - | - | 1.3.1.11 | 2.1.11 | -5 |  | -5
1.3.1.17 | Fire & Gas & Effect |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2012-01-02 | Fire & Gas Cause and Effect Matrix (SDA-S17893-AGBG1-IN-6604-00001-002) | 20 |  | 3 |  |  |  | - | - | 1.3.1.17 | 2.1.12 | -5 |  | -5
1.3.1.12 | Consolidated Instrument Index (SDA-S17893-AGBG1-IN-6612-00005) |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2013-01-02 | Consolidated Instrument Index (SDA-S17893-AGBG1-IN-6612-00003) | 20 |  | 3 |  |  |  | - | - | 1.3.1.12 | 2.1.13 | -5 |  | -5
1.3.1.18 | Fire & Gas Instrument Index |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2014-01-02 | Fire & Gas Instrument Index | 16 |  | 2 |  |  |  | - | - | 1.3.1.18 | 2.1.14 | -6 |  | -6
1.3.1.13 | PAS I/O List |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2015-01-02 | PAS I/O List (SDA-S17893-AGBG1-IN-6612-00003) | 16 |  | 2 |  |  |  | - | - | 1.3.1.13 | 2.1.15 | -6 |  | -6
1.3.1.14 | SIS-FGS I/O List |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | 2016-01-02 | SIS I/O List (SDA-S17893-AGBG1-IN-6612-00004) | 20 |  | 3 |  |  |  | - | - | 1.1.3.14 | 2.1.16 | -5 |  | -5
[9 empty] | 2.1.3 | Controls Narrative (SDA-S17893-AGBG1-IN-5680-00001) | 16 |  | 2 |  |  |  | - | - |  |  | 16 |  | 2
1.3.1.2 | Instrument Termination Diagram (SDA-S17893-AGBG1-IN-2389-00006-XXX |  | 8 | 31.9803 |  |  | 4.797 | 294.219 | [14 empty] | -8
1.3.1.3 | Instrument Location and Cable Routing Diagram (SDA-S17893-AGBG1-IN-8801-00001-001,002) |  | 12 | 31.9803 |  |  | 4.797 | 441.3285 | [14 empty] | -12
1.3.1.6 | PAS System Cabinet & Marshalling Layout Drawing (SDA-S17893-AGBG1-4004-00006-001) |  | 8 | 31.9803 |  |  | 4.797 | 294.219 | [14 empty] | -8
1.3.1.7 | SIS System Cabinet & Marshalling Layout Drawing (SDA-S17893-AGBG1-4004-00007-001) |  | 24 | 31.9803 |  |  | 4.797 | 882.657 | [14 empty] | -24
1.3.1.19 | Fire & Gas I/O List |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | [14 empty] | -8
1.3.1.20 | Fire & Gas Zone Lay-out |  | 8 | 31.9803 |  |  | 4.797 | 294.219 | [14 empty] | -8
1.3.1.21 | Fire & Gas Detector Lay-out |  | 8 | 31.9803 |  |  | 4.797 | 294.219 | [14 empty] | -8
1.3.1.22 | Instrument Datasheet-Beacon |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | [14 empty] | -8
1.3.1.23 | Instrument Datasheet-Sounder |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | [14 empty] | -8
1.3.1.24 | Instrument Datasheet-Manual Call Point |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | [14 empty] | -8
1.3.1.25 | Instrument Datasheet-Open Path Gas Detector |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | [14 empty] | -8
1.3.1.26 | Instrument Datasheet-Pont Gas Detector |  | 8 | 33.259 |  |  | 4.9889 | 305.983 | [14 empty] | -8
[9 empty] | 2017-01-02 | Fire & Gas Cable Device Instrument Details (SDA-S17893-AGBG1-IN8801-0001-001 to 009 | 40 |  | 5 |  |  |  | - | - |  |  | 5 |  | 5
[9 empty] | 2018-01-02 | SIS, FGS, & PAS Panel Wiring Drawing | 40 |  | 5 |  |  |  | - | - |  |  | 5 |  | 5
[9 empty] | 2019-01-02 | SIS, FGS, & PAS Panel Layout Drawing | 40 |  | 5 |  |  |  | - | - |  |  | 5 |  | 5
[9 empty] | 2020-01-02 | Overall Earthing Layout Drawing | 120 |  | 15 |  |  |  | - | - |  |  | 15 |  | 15
[9 empty] | 2021-01-02 | Cable MCT Diagram | 60 |  | 8 |  |  |  | - | - |  |  | 8 |  | 8
[9 empty] | 2022-01-02 | Interface Detail Drawing between the AG Compressor, Agbada AG and Agbada Flowstation | 50 |  | 6 |  |  |  | - | - |  |  | 6 |  | 6
[9 empty] | 2023-01-02 | Cabinet Termination Drawing | 60 |  | 8 |  |  |  | - | - |  |  | 8 |  | 8
[9 empty] | 2024-01-02 | Cause & Effect Matrix (AG Compressor & AGG) | 70 |  | 9 |  |  |  | - | - |  |  | 9 |  | 9
[9 empty] | 2025-01-02 | Robershaw Hook up drawing update | 60 |  | 8 |  |  |  | - | - |  |  | 8 |  | 8
[9 empty] | 2026-01-02 | Instrument I/O List | 30 |  | 4 |  |  |  | - | - |  |  | 4 |  | 4
[9 empty] | 2027-01-02 | Building Overall Architectural Lay-out Drawings | 160 |  | 20 |  |  |  | - | - |  |  | 20 |  | 20
[9 empty] | 2028-01-02 | Building Structural Calculation Report | 120 |  | 15 |  |  |  | - | - |  |  | 15 |  | 15
[9 empty] | 2021-01-02 | Building Structural General Arrangement Drawing | 120 |  | 15 |  |  |  | - | - |  |  | 15 |  | 15
[9 empty] | 2022-01-02 | Structural Detailed Drawings | 192 |  | 24 |  |  |  | - | - |  |  | 24 |  | 24
1.3.2 | Pipe Design Works |  | 200 | 255.8426 |  |  | 38.3764 | 7355.4754 | 2.2 | Pipe Design Works |  |  | 176 | 31516 |  |  | 5550755.5 | 18199.2 |  |  |  | 147.4% | -24 |  |  |  |  | 10843.7246 | 53.56%
1.3.2.1 | Isometrics |  | 50 | 31.9803 |  |  | 4.797 | 1838.8689 | 2.2.1 | Isometrics | 378 |  | 47 |  |  |  | - | - | 1.3.2.1 | 2.2.1 | -3 |  | -3
1.3.2.2 | Piping GA |  | 20 | 31.9803 |  |  | 4.797 | 735.5475 | 2.2.2 | Piping GA | 322 |  | 40 |  |  |  | - | - | 1.3.2.2 | 2.2.2 | 20 |  | 20
1.3.2.3 | Pipe Support Drawings |  | 10 | 31.9803 |  |  | 4.797 | 367.7738 | 2.2.3 | Pipe Support Drawings | 322 |  | 40 |  |  |  | - | - | 1.3.2.3 | 2.2.3 | 30 |  | 30
1.3.2.4 | 3D Model |  | 40 | 31.9803 |  |  | 4.797 | 1471.0951 | 2.2.4 | 3D Model | 72 |  | 9 |  |  |  | - | - | 1.3.2.4 | 2.2.4 | -31 |  | -31
1.3.2.5 | Plot Plan |  | 16 | 31.9803 |  |  | 4.797 | 588.438 | 2.2.5 | Plot Plan | 35 |  | 4 |  |  |  | - | - | 1.3.2.5 | 2.2.5 | -12 |  | -12
1.3.2.6 | Stress Analysis |  | 40 | 31.9803 |  |  | 4.797 | 1471.0951 | 2.2.6 | Stress Analysis | 80 |  | 10 |  |  |  | - | - | 1.3.2.6 | 2.2.6 | -30 |  | -30
1.3.2.7 | Tie-in Schedule |  | 8 | 31.9803 |  |  | 4.797 | 294.219 | 2.2.7 | Tie-in Schedule | 28 |  | 4 |  |  |  | - | - | 1.3.2.7 | 2.2.7 | -4 |  | -4
1.3.2.8 | MTO's |  | 16 | 31.9803 |  |  | 4.797 | 588.438 | 2.2.8 | MTO's | 50 |  | 6 |  |  |  | - | - | 1.3.2.8 | 2.2.8 | -10 |  | -10
[9 empty] | 2.2.9 | Review of critical Line List | 10 |  | 1 |  |  |  | - | - |  |  | 1 |  | 1
[9 empty] | 2010-02-02 | Site Visit / Report | 112 |  | 14 |  |  |  | - | - |  |  | 14 |  | 14
1.3.3 | Civil Design Works |  | 100 | 31.9803 |  |  | 4.797 | 3677.7377 | 2.3 | Civil Design Works | 120 |  | 15 | 31516 |  |  | 472740 | 1549.97 | 1.3.3 | 2.3 | -85 | -57.86% | -85 |  |  |  |  | -2127.7677 | -10.51%
[23 empty] | 0 |  |  |  |  | 0
[8 empty] | 21007.1593 | [13 empty] | 96.39% | TOTAL VARIANCE IN USD |  |  |  |  | 20247.8107

## Site works (hidden)
Company Estimate | [8 empty] | ITEM NO. | DESCRIPTION | MH | UoM | QTY | UNIT COST | Profit, O/H | Total Unit Cost | TOTAL COST, IN NAIRA | TOTAL COST IN USD |  |  | Qty Variance
[13 empty] | a | b | c | d = b + c | e = d x a | f = e / 305 | SPDC | METS | METS - SPDC (USD) | (METS - SPDC)/SPDC | Qty Variance (METS - SPDC) | unit cost variance with out mark up | unit cost variance with mark up | Total Cost Variance NGN | Variance USD | Variance FUSD | % of total variance (NGN)
ITEM NO. | DESCRIPTION | UoM | QTY | UNIT COST US$ | TOOLS & EQUIPMENT$ | Man-power $ | Contractors Mark-UP $ | Total cost USD | 3 | Site Works / Construction | [6 empty] | 192033933.67 | 629619.45
1.4 | Site Works - Civil and Fabrication Scope of Works | [6 empty] | 0 | 3.1 | Site Works - Civil and Fabrication Scope of Works | [6 empty] | 14910852.99 | 48888.04
1.4.1 | Survey works | lot | 1 | 568.0656 |  |  |  | 568.0656 | 3.1.1 | Survey works |  | lot | 1 | 750000 |  |  | 750000 | 2459.02 | 1.4.1 | 3.1.1 | 1890.9544 | 332.9% | [5 empty] | 1890.9544 | 0.3206%
1.4.2 | Fabrication & Installation of Pipe Support | lot | 1 | 4718.8173 | 6445.8197 | 4234.7541 | 707.8226 | 16107.2136 | 3.1.2 | Fabrication & Installation of Pipe Support (including manpower, equipment, tools & materials) |  | lot | 1 | 3400000 |  |  | 3400000 | 11147.54 | 1.4.2 | 3.1.2 | -4959.6736 | -30.79% | [5 empty] | -4959.6736 | -0.8408%
1.4.3 | Foundation Works | lot | 1 | 3342.3141 |  |  |  | 3342.3141 | [13 empty] | -100% | [5 empty] | -3342.3141 | -0.5666%
1.5 | Testing Inspection, Pre-com and Commissioning & Pipe Stress Analysis | [6 empty] | 0 | 4 | Testing Inspection, Pre-com and Commissioning & Pipe Stress Analysis | [6 empty] | 4200000 | 13770.49
1.5.1 | Testing Inspection, Pre-com and Commissioning | lot | 1 | 5850.4262 |  |  | 877.5639 | 6727.9902 | 4.1.1 | Testing Inspection, Pre-com and Commissioning |  | lot | 1 | 3000000 |  |  | 3000000 | 9836.07 |  |  |  | 46.2% | [5 empty] | 3108.0798 | 0.5269%
1.5.2 | Pipe Stress Analysis | lot | 1 |  |  |  | 0 | 0 | 4.1.2 | Pipe Stress Analysis |  | lot | 1 | 1200000 |  |  | 1200000 | 3934.43 | 1.5.2 | 4.1.2 | 3934.43 | [6 empty] | 3934.43 | 0.667%
[9 empty] | 3.2 | Site Works - Mechanical Works | [6 empty] | 18155589.18 | 59526.52 |  | 3.2
|  |  |  | Site Works/Construction/Pre-com |  |  |  | 26745.5835 | 3.2.2 | Fabrication & Installation of Mechanical Bulks (equipment, tools & manpower) |  | lot | 1 | 18155589.18 |  |  | 18155589.18 | 59526.52 |  | 3.2.2 | 32780.9365 | [6 empty] | 32780.9365 | 5.557%
[9 empty] | 3.3 | Site Works - EI&C | [6 empty] | 158967491.5 | 521204.89 |  | 3.3
[9 empty] | 3.3.1 | Fabrication & Installation of El&C Bulks (equipment tools & materials) |  | lot | 1 | 158967491.5 |  |  | 158967491.5 | 521204.89 |  | 3.3.1 | 521204.89 | [6 empty] | 521204.89 | 88.35%
[9 empty] | 3.1.4 | Field Auxiliary Room (6x4.5M) |  | lot | 1 | 10760852.99 |  |  | 10760852.99 | 35281.49 |  | 3.1.4 | 35281.49 | [6 empty] | 35281.49 | 5.981%
0
[12 empty] | Site Works/Construction/Testing/Pre-com | [5 empty] | 643389.94 |  |  | total % variance | 2206% |  | Total Variance in Price FUSD |  |  |  | 589898.793

## Other components (hidden)
[10 empty] | ITEM NO. | DESCRIPTION | MH | UoM | QTY | UNIT COST | Profit, O/H | Total Unit Cost | TOTAL COST, IN NAIRA | TOTAL COST IN USD |  |  | Qty Variance
ITEM NO. | DESCRIPTION | UoM | QTY | UNIT COST US$ | TOOLS & EQUIPMENT$ | Man-power $ | Contractors Mark-UP $ | Total cost USD | [5 empty] | a | b | c | d = b + c | e = d x a | f = e / 305 | SPDC | METS | METS - SPDC | (METS - SPDC)/SPDC | Qty Variance (METS - SPDC) |  | unit cost variance with out mark up |  | unit cost variance with mark up | Total Cost Variance NGN | Variance USD | % of total variance (NGN)
2.1.5 | OTHER COMPONENTS |  |  |  | 0 | 0 | 0 | 99689.4558 |  | 1.2.7 | OTHER COMPONENTS | [6 empty] | 497525471.26 | 1631231.05 | 2.1.5 | 1.2.7
2.1.5.1 | Control Cable, Lapp kabel 1.5 mm2, White, TBD | ROLL | 200 | 1.6472 | 0.216 | 0.11631 | 0.24707 | 445.3099 | 2.2265 | 1.2.7.1 | Control Cable, Lapp kabel 1.5 mm2, White, TBD |  | ROLL | 200 | 28822.5 | 8646.75 | 37469.25 | 7493850 | 24570 | 2.1.5.1 | 1.2.7.1 | 0 | 5418% | 0 | 92.2735 | 92.8528 | 120.6235 | 121.2028 |  | 24124.6901 | 1.575%
2.1.5.2 | Non Ex Relay module, Output in fail-safe technology, Up to SIL3, Single Channel, KFD0-RSH-1 | PC | 8 | 472.819 | 62.0035 | 33.3865 | 70.9228 | 5113.0549 | 639.1319 | 1.2.7.2 | Non Ex Relay module, Output in fail-safe technology, Up to SIL3, Single Channel, KFD0-RSH-1 |  | PC | 8 | 1671705 | 501511.5 | 2173216.5 | 17385732 | 57002.4 | 2.1.5.2 | 1.2.7.2 | 0 | 1015% | 0 | 4841.8681 | 5008.181 | 6486.1681 | 6652.481 |  | 51889.3451 | 3.388%
2.1.5.3 | DI 1-channel isolated barrier, 24v DC (Power Rail), Dry contact or NAMUR inputs, Relay contact output, LFD, Reversible mode of operation, upto SIL2, KFD2-SR2- Ex1.W.LB | PC | 30 | 87.6907 | 11.4994 | 6.192 | 13.1536 | 3556.072 | 118.5357 | 1.2.7.3 | DI 1-channel isolated barrier, 24v DC (Power Rail), Dry contact or NAMUR inputs, Relay contact output, LFD, Reversible mode of operation, upto SIL2, KFD2-SR2- Ex1.W.LB |  | PC | 38 | 1959930 | 587979 | 2547909 | 96820542 | 317444.4 | 2.1.5.3 | 1.2.7.3 | 8 | 8827% | 8 | 6307.4643 | 6338.3093 | 8235.2643 | 8266.1093 |  | 313888.328 | 20.49%
2.1.5.4 | K-System Intrinsic Safety Seperately Powered Isolated Barriers – Analog Input 2 /3 Wire Transmitters, KFD2-STC4- Ex1-Y122583 | PC | 38 | 106.6509 | 13.9858 | 7.5308 | 15.9976 | 5478.2731 | 144.1651 | 1.2.7.4 | K-System Intrinsic Safety Seperately Powered Isolated Barriers – Analog Input 2 /3 Wire Transmitters, KFD2-STC4- Ex1-Y122583 |  | PC | 45 | 3228120 | 968436 | 4196556 | 188845020 | 619164 | 2.1.5.4 | 1.2.7.4 | 7 | 11202% | 7 | 10439.8349 | 10477.3491 | 13615.0349 | 13652.5491 |  | 613685.7269 | 40.07%
2.1.5.5 | AO 1-channel isolated barrier, 24v DC (Power Rail), Current output up to 700 Ω load, HART I/P and valve positioner, LFD, upto SIL2, KFD2 SCD2- Ex1.LK | PC | 5 | 655.0842 | 85.905 | 46.2565 | 98.2626 | 4427.5418 | 885.5084 | 1.2.7.5 | AO 1-channel isolated barrier, 24v DC (Power Rail), Current output up to 700 Ω load, HART I/P and valve positioner, LFD, upto SIL2, KFD2-SCD2- Ex1.LK |  | PC | 5 | 864675 | 259402.5 | 1124077.5 | 5620387.5 | 18427.5 | 2.1.5.5 | 1.2.7.5 | 0 | 316.2% | 0 | 1949.4916 | 2179.9158 | 2799.9916 | 3030.4158 |  | 13999.9582 | 0.9141%
2.1.5.6 | Power Feed Module, KFD2-EB2 | PC | 3 | 187.2316 | 24.5528 | 13.2207 | 28.0847 | 759.2694 | 253.0898 | 1.2.7.6 | Power Feed Module, KFD2-EB2 |  | PC | 3 | 224815.5 | 67444.65 | 292260.15 | 876780.45 | 2874.69 | 2.1.5.6 | 1.2.7.6 | 0 | 278.6% | 0 | 484.0102 | 549.8684 | 705.1402 | 770.9984 |  | 2115.4206 | 0.1381%
2.1.5.7 | Universal Power Rail (2m, )UPR-03 | PC | 3 | 396.9784 | 52.0581 | 28.0313 | 59.5468 | 1609.8434 | 536.6145 | 1.2.7.7 | Universal Power Rail (2m, )UPR-03 |  | PC | 3 | 247873.5 | 74362.05 | 322235.55 | 966706.65 | 3169.53 | 2.1.5.7 | 1.2.7.7 | 0 | 96.88% | 0 | 276.0855 | 415.7217 | 519.8955 | 659.5316 |  | 1559.6866 | 0.1018%
2.1.5.8 | End Cap for Universal power rail, UPR-E | PC | 3 | 42.7363 | 5.6043 | 3.0177 | 6.4104 | 173.3061 | 57.7687 | 1.2.7.8 | End Cap for Universal power rail, UPR-E |  | PC | 3 | 28822.5 | 8646.75 | 37469.25 | 112407.75 | 368.55 | 2.1.5.8 | 1.2.7.8 | 0 | 112.7% | 0 | 36.7313 | 51.7637 | 65.0813 | 80.1137 |  | 195.2439 | 0.01275%
2.1.5.9 | Isolated FF power conditioner; 28 -30VDC @ 500 mA, HD2-FBPS- 1.500 | PC | 22 | 1074.8041 | 140.9453 | 75.8936 | 161.2206 | 31963.0002 | 1452.8636 | 1.2.7.9 | Isolated FF power conditioner; 28 -30VDC @ 500 mA, HD2-FBPS- 1.500 |  | PC | 22 | 3746925 | 1124077.5 | 4871002.5 | 107162055 | 351351 | 2.1.5.9 | 1.2.7.9 | 0 | 999.2% | 0 | 10832.1364 | 11210.1959 | 14517.6364 | 14895.6959 |  | 319387.9998 | 20.85%
2.1.5.10 | Motherboard for Redundant Power Conditioners hub (Power supply of four FOUNDATION Fieldbus H1 segments), MB-FB-4R | PC | 1 | 1232.8015 | 161.6644 | 87.0501 | 184.9202 | 1666.4362 | 1666.4362 | 1.2.7.10 | Motherboard for Redundant Power Conditioners hub (Power supply of four FOUNDATION Fieldbus H1 segments), MB-FB-4R |  | PC | 1 | 259402.5 | 77820.75 | 337223.25 | 337223.25 | 1105.65 | 2.1.5.10 | 1.2.7.10 | 0 | -33.65% | 0 | -815.9362 | -382.3015 | -560.7862 | -127.1515 |  | -560.7862 | -0.03662%
2.1.5.11 | Diagnostic Module, HD2-DM-B | PC | 1 | 217.5093 | 28.5233 | 15.3587 | 32.6264 | 294.0176 | 294.0176 | 1.2.7.11 | Diagnostic Module, HD2-DM-B |  | PC | 1 | 51880.5 | 15564.15 | 67444.65 | 67444.65 | 221.13 | 2.1.5.11 | 1.2.7.11 | 0 | -24.79% | 0 | -123.9176 | -47.4093 | -72.8876 | 3.6207 |  | -72.8876 | -0.004759%
2.1.5.12 | Modular Surge Protector for Fieldbus System, DP-LBF-1.34 | PC | 2 | 13.1789 | 1.7282 | 0.93058 | 1.9768 | 35.6291 | 17.8146 | 1.2.7.12 | Modular Surge Protector for Fieldbus System, DP-LBF-1.34 |  | PC | 2 | 172935 | 51880.5 | 224815.5 | 449631 | 1474.2 | 2.1.5.12 | 1.2.7.12 | 0 | 4038% | 0 | 549.1854 | 553.8211 | 719.2854 | 723.9211 |  | 1438.5709 | 0.09393%
2.1.5.13 | Base Module- Surge Protector, DB-LB | PC | 2 | 60.0627 | 7.8764 | 4.2411 | 9.0094 | 162.3792 | 81.1896 | 1.2.7.13 | Base Module- Surge Protector, DB-LB |  | PC | 2 | 63409.5 | 19022.85 | 82432.35 | 164864.7 | 540.54 | 2.1.5.13 | 1.2.7.13 | 0 | 232.9% | 0 | 126.7104 | 147.8373 | 189.0804 | 210.2073 |  | 378.1608 | 0.02469%
2.1.5.14 | Surge Protector, SD32X | PC | 100 | 154.9628 | 20.3212 | 10.9422 | 23.2444 | 20947.063 | 209.4706 | 1.2.7.14 | Surge Protector, SD32X |  | PC | 100 | 86467.5 | 25940.25 | 112407.75 | 11240775 | 36855 | 2.1.5.14 | 1.2.7.14 | 0 | 75.94% | 0 | 74.0294 | 128.5372 | 159.0794 | 213.5872 |  | 15907.937 | 1.039%
2.1.5.15 | Surge Protector Dual Channel, SLP32D | PC | 50 | 267.9946 | 35.1437 | 18.9235 | 40.1992 | 18113.0486 | 362.261 | 1.2.7.15 | Surge Protector Dual Channel, SLP32D |  | PC | 50 | 209827.8 | 62948.34 | 272776.14 | 13638807 | 44717.4 | 2.1.5.15 | 1.2.7.15 | 0 | 146.9% | 0 | 325.699 | 419.9654 | 532.087 | 626.3534 |  | 26604.3514 | 1.737%
2.1.5.16 | ISP7000 Insulating SpacersI, SP7000 | PC | 25 | 43.8454 | 5.7497 | 3.096 | 6.5768 | 1481.6967 | 59.2679 | 1.2.7.16 | ISP7000 Insulating SpacersI, SP7000 |  | PC | 25 | 99149.4 | 29744.82 | 128894.22 | 3222355.5 | 10565.1 | 2.1.5.16 | 1.2.7.16 | 0 | 613% | 0 | 265.8121 | 281.2346 | 363.3361 | 378.7586 |  | 9083.4033 | 0.5931%
2.1.5.17 | Relay socket mounting, PYF08A-E | PC | 8 | 5.2718 | 0.69132 | 0.37225 | 0.79077 | 57.0089 | 7.1261 | 1.2.7.17 | Relay socket mounting, PYF08A-E |  | PC | 8 | 14411.25 | 4323.38 | 18734.63 | 149877 | 491.4 | 2.1.5.17 | 1.2.7.17 | 0 | 762% | 0 | 40.1239 | 41.9782 | 54.2989 | 56.1532 |  | 434.3911 | 0.02836%
2.1.5.18 | Clip, PYC-A1 | PC | 8 | 0.71632 | 0.093936 | 0.050581 | 0.10745 | 7.7463 | 0.96829 | 1.2.7.18 | Clip, PYC-A1 |  | PC | 8 | 720.56 | 216.17 | 936.73 | 7493.85 | 24.57 | 2.1.5.18 | 1.2.7.18 | 0 | 217.2% | 0 | 1.3942 | 1.6462 | 2.103 | 2.3549 |  | 16.8237 | 0.001098%
2.1.5.19 | Endplate, PFP-M | PC | 6 | 1.3491 | 0.17691 | 0.095261 | 0.20236 | 10.9418 | 1.8236 | 1.2.7.19 | Endplate, PFP-M |  | PC | 6 | 1919.58 | 575.87 | 2495.45 | 14972.71 | 49.09 | 2.1.5.19 | 1.2.7.19 | 0 | 348.6% | 0 | 4.4701 | 4.9446 | 6.3582 | 6.8327 |  | 38.1482 | 0.002491%
2.1.5.20 | Plug-in Relay, MY2N-D2- DC24S | PC | 8 | 20.265 | 2.6575 | 1.4309 | 3.0398 | 219.1453 | 27.3932 | 1.2.7.20 | Plug-in Relay, MY2N-D2- DC24S |  | PC | 8 | 21616.88 | 6485.06 | 28101.94 | 224815.5 | 737.1 | 2.1.5.20 | 1.2.7.20 | 0 | 236.4% | 0 | 43.4819 | 50.61 | 64.7443 | 71.8725 |  | 517.9547 | 0.03382%
2.1.5.21 | 24VDC 40 Amp Bulk Power Supply for DeltaV, TBD | PC | 1 | 232.5822 | 30.4999 | 16.423 | 34.8873 | 314.3924 | 314.3924 | 1.2.7.21 | 24VDC 40 Amp Bulk Power Supply for DeltaV, TBD |  | PC | 1 | 749385 | 224815.5 | 974200.5 | 974200.5 | 3194.1 | 2.1.5.21 | 1.2.7.21 | 0 | 916% | 0 | 2142.6076 | 2224.4178 | 2879.7076 | 2961.5178 |  | 2879.7076 | 0.188%
2.1.5.22 | 12VDC 40 Amp Bulk Power Supply for DeltaV, TBD | PC | 1 | 232.5822 | 30.4999 | 16.423 | 34.8873 | 314.3924 | 314.3924 | 1.2.7.22 | 12VDC 40 Amp Bulk Power Supply for DeltaV, TBD |  | PC | 1 | 317047.5 | 95114.25 | 412161.75 | 412161.75 | 1351.35 | 2.1.5.22 | 1.2.7.22 | 0 | 329.8% | 0 | 725.1076 | 806.9178 | 1036.9576 | 1118.7678 |  | 1036.9576 | 0.06771%
2.1.5.23 | Redundancy Module (Oring Diode)40 Amp Bulk Power Supply for DeltaV & SIS, TBD | PC | 0 | 193.3344 | 0 | 0 |  |  | 193.3344 | 1.2.7.23 | Redundancy Module (Oring Diode)40 Amp Bulk Power Supply for DeltaV & SIS |  | PC | 1 | 500000 | 150000 | 650000 | 650000 | 2131.15 | 2.1.5.23 | 1.2.7.23 | 1 | [7 empty] | 2131.15 | 0.1392%
2.1.5.24 | 24VDC 40 Amp Bulk Power Supply for DeltaVSIS/FGS, TBD | PC | 1 | 232.5822 | 30.4999 | 16.423 | 34.8873 | 314.3924 | 314.3924 | 1.2.7.24 | 24VDC 40 Amp Bulk Power Supply for DeltaVSIS/FGS |  | PC | 1 | 396500 | 118950 | 515450 | 515450 | 1690 | 2.1.5.24 | 1.2.7.24 | 0 | 437.5% | 0 | 985.6076 | 1067.4178 | 1375.6076 | 1457.4178 |  | 1375.6076 | 0.08982%
2.1.5.25 | 24-port singlemode LC/SC duplex fiber optic patch panel, TBD | PC | 1 | 135.9535 | 17.8284 | 9.5999 | 20.393 | 183.7748 | 183.7748 | 1.2.7.25 | 24-port singlemode LC/SC duplex fiber optic patch panel |  | PC | 1 | 366000 | 109800 | 475800 | 475800 | 1560 | 2.1.5.25 | 1.2.7.25 | 0 | 748.9% | 0 | 1016.2252 | 1064.0465 | 1376.2252 | 1424.0465 |  | 1376.2252 | 0.08986%
2.1.5.26 | 27U cabinet to install the fiber optic patch panel, TBD | PC | 1 | 860.3173 | 112.8184 | 60.7484 | 129.0476 | 1162.9317 | 1162.9317 | 1.2.7.26 | 27U cabinet to install the fiber optic patch panel, TBD |  | PC | 1 | 640500 | 192150 | 832650 | 832650 | 2730 | 2.1.5.26 | 1.2.7.26 | 0 | 134.8% | 0 | 937.0683 | 1239.6827 | 1567.0683 | 1869.6827 |  | 1567.0683 | 0.1023%
2.1.5.27 | Fibre Optic to Ethernet converter, TBD | PC | 1 | 594.4176 | 77.9495 | 41.9728 | 89.1626 | 803.5025 | 803.5025 | 1.2.7.27 | Fibre Optic to Ethernet converter |  | PC | 1 | 122000 | 36600 | 158600 | 158600 | 520 | 2.1.5.27 | 1.2.7.27 | 0 | -35.28% | 0 | -403.5025 | -194.4176 | -283.5025 | -74.4176 |  | -283.5025 | -0.01851%
2.1.5.28 | Network switch, TBD | PC | 1 | 55.6955 | 7.3037 | 3.9327 | 8.3543 | 75.2862 | 75.2862 | 1.2.7.28 | Network switch |  | PC | 1 | 114375 | 34312.5 | 148687.5 | 148687.5 | 487.5 | 2.1.5.28 | 1.2.7.28 | 0 | 547.5% | 0 | 299.7138 | 319.3045 | 412.2138 | 431.8045 |  | 412.2138 | 0.02691%
2.2 | ENGINEERING & DESIGN SCOPE OF WORKS | MH | 445 | 159.9016 | 0 | 0 | 23.9852 | 81829.6639
2.3 | Testing Inspection & Pre-com and Commissioning | LOT | 1 | 8025.6393 | 0 | 0 | 1203.8459 | 9229.4852
1.2.7.29 | [9 empty] | 1.2.7.29 | SERVER | [6 empty] | 38556180 | 126413.7
1.2.7.29.1 | [9 empty] | 1.2.7.29.1 | Power Edge T610 Tower Server; English Win Server 2008 Std Image Included; Xeon 5530 2.4 GHz CPU; 20-inch LCD Monitor; 146GB Drive; Raid 0; 4 GB RAM; DVD+/- RW Drive; RD1000 Back-up Unit; 4 Ethernet Ports (AGG Control Room) |  | SET | 1 | 648000 | 194400 | 842400 | 842400 | 2761.97 |  |  | 1 |  | 1 | 2124.5902 | 2124.5902 | 2761.9672 | 2761.9672 |  | 2761.97 | 0.1803%
1.2.7.29.2 | [9 empty] | 1.2.7.29.2 | Monitoring Module (Analog and Discrete) |  | EA | 100 | 198000 | 59400 | 257400 | 25740000 | 84393.44 |  |  | 100 |  | 100 | 649.1803 | 649.1803 | 843.9344 | 843.9344 |  | 84393.44 | 5.51%
1.2.7.29.3 | [9 empty] | 1.2.7.29.3 | Simple Control Module |  | EA | 25 | 81000 | 24300 | 105300 | 2632500 | 8631.15 |  |  | 25 |  | 25 | 265.5738 | 265.5738 | 345.2459 | 345.2459 |  | 8631.15 | 0.5636%
1.2.7.29.4 | [9 empty] | 1.2.7.29.4 | Intermediate Control Modules |  | EA | 20 | 35280 | 10584 | 45864 | 917280 | 3007.48 |  |  | 20 |  | 20 | 115.6721 | 115.6721 | 150.3738 | 150.3738 |  | 3007.48 | 0.1964%
1.2.7.29.5 | [9 empty] | 1.2.7.29.5 | OPC SCADA Modules |  | EA | 100 | 64800 | 19440 | 84240 | 8424000 | 27619.67 |  |  | 100 |  | 100 | 212.459 | 212.459 | 276.1967 | 276.1967 |  | 27619.67 | 1.803%
[26 empty] | Total Variance inUSD |  |  |  | 1531541.6042

## SUMMARY (hidden)
Variance |  | % of total variance (USD)
Total Variance | 2162700.997 | -
PROCUREMENT | 21012.7891 | 0.9716%
ENGINEERING & DESIGN SCOPE OF WORKS | 20247.8107 | 0.9362%
Site Works / Construction | 589898.793 | 27.28%
Other components | 1531541.6042 | 70.82%