## Cadence Schedule
PU RTO Project Scope/Actions | Start Date | End Date
§ Update Production Universe RTO models with currently available data. | August 2nd 2017 | 16th August 2017
§Engage and obtain GHV data for NAG wells from Production Chemistry. | 17th August 2017 | 21st August 2017
§Engage operations, WRFM and sub surface teams to validate current data by executing MRT of GBARAN NAG wells. | 7th September | 30th September
§Calibrate the PU RTO models with validated data and run optimization. | 10th October 2017 | 30th October 2017
§Engage relevant disciplines to review model outcomes. | 31st October 2017 | 7th November 2017
§Deploy the optimization outcome in the field and monitor and report expected outcomes. | 31st October 2017 | Continous