## Sheet1
HIGH LEVEL TIME LINE
2018-10-01
S/N | Description of Activities | Duration | 8th | 9th | 10th | 11th | 15th
Days
1 | Inspect W64T bean box and confirm availability of replacement | 1
2 | Secure funding for the activity
3 | Mobilize team to Cluster and set upl scaffold on Estuary Cluster -52 | 1
4 | Replace eroded bean box with adjustale choke | 1
5 | Dismantle scaffold on Cluster 52 | 1
6 | Open up Well 64T when rig moves out of Cluster | 1
v