## Sheet1
HIGH LEVEL TIME LINE
|  |  | 2018-09-01 |  |  |  | 2018-10-01
S/N | Description of Activities | Duration | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4
Days
1 | Develop scope of work | 1 | bar: 2018-09-01 WK1
2 | Mobilize to site | 1 | bar: 2018-09-01 WK2
3 | Carryout flowline replacement | 25 | bar: 2018-09-01 WK3 to 2018-10-01 WK3
4 | Carryout CWI dewaxing activities | 5 | bar: 2018-10-01 WK4
5 | Flow well | 1 | bar: 2018-10-01 WK4
6 | Demobilze from site | 1 | bar: 2018-10-01 WK4