## Sheet1
HIGH LEVEL TIME LINE
2018-11-01
S/N | Description of Activities | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Days
1 | Inspect W114S, confirm no plug in hole, able to flow, and any existing integrity issues. | 1 | bar: 2018-11-01 1
2 | Source for and replace defective survey cap | 2 | bar: 2018-11-01 1 to 2018-11-01 3
3 | Provide Well Control Panel, serviced and send to site for installation | 7 | bar: 2018-11-01 1 to 2018-11-01 3
4 | Mobilize team to W114S and install Well Control Panel | 1 | bar: 2018-11-01 3 to 2018-11-01 6
5 | Engage PMT/Ptech/CWI and agree on open up, optimum adjustable choke size for gas lift | 3 | bar: 2018-11-01 4 to 2018-11-01 12
6 | Open up Well 114S and test flow performance | 3 | bar: 2018-11-01 5 to 2018-11-01 7