## FYIP OFFSHORE ACTIVITY OPT (hidden)
S/N | Description | Action Party(ies) | Precursor | Duration (Weeks) | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER
 | time axis 2018-07-02 to 2019-09-30
1 | FORC-64 WO CLUSTER 52 | Tien, W |  | 4 Weeks | bar: 2018-07-09 to 2018-09-17
2 | FORC-37 WO CLUSTER 1 | Tien, W | 1 | 4 Weeks | bar: 2018-09-24 to 2018-10-22
3 | FORC-NAG CLUSTER JB | Tien, W | 2 | 10 Weeks | bar: 2018-10-29 to 2018-12-31
4 | FORC-66 WO CLUSTER 3 | Tien, W | 3 | 6 Weeks | bar: 2019-01-07 to 2019-02-11
4 | FORC-73 WO CLUSTER 3 | Tien, W | 3 | 6 Weeks | bar: 2019-02-18 to 2019-03-25
5 | CWI UPFRONT FLM ACTIVITIES 51A | Okolomma, E | 11,12 | 1 Week | bar: 2018-10-29
6 | CWI UPFRONT FLM ACTIVITIES 52A | Okolomma, E | 5 | 1 Week | bar: 2018-11-05
7 | CWI UPFRONT FLM ACTIVITIES 3A | Okolomma, E | 6 | 2 Weeks | bar: 2018-11-12 to 2018-11-19
8 | CWI STIMULATE,CLEAN & LIFT 3A | Okolomma, E | 7 | 5 Weeks | bar: 2018-11-26 to 2018-12-24
9 | CWI STIMULATE,CLEAN & LIFT 52A | Okolomma, E | 8 | 2 Weeks | bar: 2018-12-31 to 2019-01-07
10 | CWI STIMULATE,CLEAN & LIFT 51A | Okolomma, E | 9 | 2 Weeks | bar: 2019-01-14 to 2019-01-21
11 | FYIP PREWORKS 51A | Balogun, G |  | 3 Weeks | bar: 2018-09-17 to 2018-10-01
12 | FYIP PREWORKS 52A | Balogun, G | 11 | 2 Weeks | bar: 2018-10-08 to 2018-10-15
13 | FYIP ANCHOR BARGE WORK 3A | Balogun, G |  | 8 Weeks | bar: 2018-09-24 to 2018-11-12
14 | FYIP ANCHOR BARGE WORK 52A | Balogun, G | 13 | 4 Weeks | bar: 2018-11-26 to 2018-12-17
15 | FYIP ANCHOR BARGE WORK 51A | Balogun, G | 14 | 4 weeks | bar: 2018-12-31 to 2019-01-21
16 | FORC-37 FLOWLINE & HOOKUP | Balogun, G |  | 9 Weeks | bar: 2018-12-10 to 2019-02-04
17 | FY-NAG FLOWLINE & HOOKUP | Balogun, G |  | 15 Weeks | bar: 2019-02-11 to 2019-05-20
WELL OSD
Note on R3: FORC -64 OSD
Note on AM6: FORC -66 OSD
Note on AS7: FORC -73 OSD
Note on AL19: FORC-37 OSD
Note on BA20: FY-NAG OSD

## FYIP OFFSHORE ACTIVITY OPT1
FYIP AND WELLS TEAMS INTEGRATED ACTITY SCHEDULE IN FORCADOS ESTUARY
S/N | Description | Action Party(ies) | Duration (Weeks) | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | Comments
 | time axis 2018-07-02 to 2019-09-30
1 | FORC-64 WO CLUSTER 52 | Tien, W | 4 Weeks | 2018-08-20: SHENGRI-LI
2 | FORC-66 WO CLUSTER 3 | Tien, W | 17 Weeks | 2018-09-24: SHENGRI-LI
3 | FORC-37 WO CLUSTER 1 | Tien, W | 7 Weeks | 2019-01-14: SHENGRI-LI
4 | FORC-NAG CLUSTER JA | Tien, W | 13 Weeks | 2019-03-04: SHENGRI-LI
5 | CWI UPFRONT FLM ACTIVITIES 51A | Okolomma, E | 1 Week | bar: 2019-03-04
6 | CWI UPFRONT FLM ACTIVITIES 52A | Okolomma, E | 1 Week | bar: 2019-03-11
7 | CWI STIMULATE,CLEAN & LIFT 51A | Okolomma, E | 2 Weeks | bar: 2019-03-18 to 2019-03-25
8 | CWI STIMULATE,CLEAN & LIFT 3A | Okolomma, E | 5 Weeks | 2019-04-08: CWI JUB
9 | CWI STIMULATE,CLEAN & LIFT 52A | Okolomma, E | 2 Weeks | bar: 2019-05-13 to 2019-05-20
10 | FYIP PREWORKS 52A | Balogun, G | 3 Weeks | 2019-01-28: JUB W21
11 | FYIP PREWORKS 3A | Balogun, G | 4 Weeks | 2018-11-19: To be done on AW barge
12 | FYIP OTHER WORKS 51A | Balogun, G | 3 Weeks | 2019-02-18: JUB W21
13 | FYIP ANCHOR BARGE WORK 51A | Balogun, G | 4 weeks | 2019-01-14: African Worker
14 | FYIP ANCHOR BARGE WORK 3A | Balogun, G | 8 Weeks | 2019-02-18: African Worker | Concurrent topside and riser installation spread
15 | FYIP ANCHOR BARGE WORK 52A | Balogun, G | 4 Weeks | 2019-04-22: African Worker | Concurrent topside and riser installation spread
16 | FYIP ANCHOR BARGE WORK JB | Balogun, G | 5 weeks | 2019-05-27: African Worker | Concurrent topside and riser installation spread
17 | FYIP ANCHOR BARGE WORK NEFS | Balogun, G | 7 weeks | 2019-07-08: African Worker | Concurrent topside and riser installation spread; This may slip to next construction window - November 2019
18 | CWI STIMULATE,CLEAN & LIFT JB | Okolomma, E | 5 Weeks | 2019-08-26: CWI JUB | Subject to completion of OEFS & NEFS Bulking and LP debottlenecking at SB
19 | FORC-37 FLOWLINE & HOOKUP | Balogun, G | 4 Weeks | 2019-03-04: Hookup of FORC 037 delayed by 3 mths; 2019-05-06: Laybarge | 2x 500m flowline; Depending on Sapura availability, this may be given priority over FYNAG, which then misses this construiction window.
20 | CWI STIMULATE,CLEAN & LIFT FORC 037 | Okolomma, E | 2 Weeks | bar: 2019-06-03 to 2019-06-10
21 | FY-NAG FLOWLINE OFFSHORE PIPE LAY | Agbo, K | 10 Weeks | 2019-02-25: Laybarge | Critical to commence laying of DSS linepipe from JA b4 thr rig spuds, else FYNAG pipelay may be pushed to next season
22 | FY-NAG RISER INSTALLATION & HOOKUP AT JA | Agbo, K | 4 Weeks | 2019-06-03: Laybarge
23 | FY-NAG ONSHORE PIPELAY AND CPF END FACILITIES | Agbo, K | 11 Weeks | 2019-02-25: Micharry Onshore Crew
ShowStopper - For going FY-NAG first after FORC 66
1. Chrome Liner Hanger delivery date – 24 weeks ( Expedition brings down to 20 weeks)
2. One off PO/Minor contract preparation for Waste management – 1 month
3. Installation of Waste management equipment – 3 weeks
4. Cost impact to FORC73 and 37 for having waste management equipment on standby for EA - $
5. Hole opener - 3 weeks
6. 5.5" Open Hole EXR Packer - no back up
What is Okay?
1. OCTG, WH and Completion are ready
2. HP riser. Riser for diverter

## FYIP OFFSHORE ACTIVITY OPT2 (hidden)
S/N | Description | Action Party(ies) | Precursor | Duration (Weeks) | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER
 | time axis 2018-07-02 to 2019-09-30
1 | FORC-64 WO CLUSTER 52 | Tien, W |  | 4 Weeks | bar: 2018-07-09 to 2018-09-17
2 | FORC-66 WO CLUSTER 3 | Tien, W | 3 | 11 Weeks | bar: 2018-09-24 to 2018-12-03
3 | FORC-73 WO CLUSTER 51 | Tien, W | 1 | 7 Weeks | bar: 2018-12-10 to 2019-01-21
4 | FORC-37 WO CLUSTER 1 | Tien, W | 2 | 7 Weeks | bar: 2019-01-28 to 2019-03-11
5 | FORC-NAG CLUSTER JB | Tien, W | 3 | 6 Weeks | bar: 2019-03-18 to 2019-05-20
6 | CWI UPFRONT FLM ACTIVITIES 51A | Okolomma, E | 11,12 | 1 Week | bar: 2019-02-04
7 | CWI UPFRONT FLM ACTIVITIES 52A | Okolomma, E | 5 | 1 Week | bar: 2019-02-11
8 | CWI STIMULATE,CLEAN & LIFT 51A | Okolomma, E | 9 | 2 Weeks | bar: 2019-02-18 to 2019-02-25
9 | CWI STIMULATE,CLEAN & LIFT 52A | Okolomma, E | 8 | 2 Weeks | bar: 2019-03-04 to 2019-03-11
10 | CWI STIMULATE,CLEAN & LIFT 3A | Okolomma, E | 7 | 5 Weeks | bar: 2019-03-18 to 2019-04-15
11 | FYIP PREWORKS 52A | Balogun, G | 11 | 2 Weeks | bar: 2018-10-29 to 2018-11-12
12 | FYIP PREWORKS 3A | Balogun, G | bar: 2018-11-19 to 2018-12-10
13 | FYIP PREWORKS 51A | Balogun, G |  | 3 Weeks | bar: 2018-12-17 to 2018-12-31
14 | FYIP ANCHOR BARGE WORK 51A | Balogun, G | 14 | 4 weeks | bar: 2018-11-12 to 2018-12-03
15 | FYIP ANCHOR BARGE WORK 52A | Balogun, G | 13 | 4 Weeks | bar: 2018-12-17 to 2019-01-07
16 | FYIP ANCHOR BARGE WORK 3A | Balogun, G |  | 8 Weeks | bar: 2019-01-21 to 2019-03-11
17 | FORC-37 FLOWLINE & HOOKUP | Balogun, G |  | 9 Weeks | bar: 2019-01-28 to 2019-03-25
18 | FY-NAG FLOWLINE & HOOKUP | Balogun, G |  | 15 Weeks | bar: 2019-04-01 to 2019-07-08
HOOK-UP & WELL OSD
Note on R3: FORC -64 OSD
Note on AE4: FORC -66 OSD
Note on BA7: FORC-73 OSD
Note on AO10: CLUSTER-51A OSD (1 WELLS)
Note on AQ11: CLUSTER-52A OSD (1 WELLS)
Note on AV12: CLUSTER-3A OSD (6 WELLS)
Note on AS19: FORC-37 OSD
Note on BH20: FORC-NAG OSD